## Session_Log
When | Topic | What Happened / Finding | Resolution / Current Status
2026-09-02 late | RLS audit (backend-dev, read-only) | feat/rls: 10 tables + notifications RLS policies registered, app factory wired, migration chain clean, no conflicts. 18-test suite exists but NEVER RUN (needs real Postgres, not sqlite). NOT MERGED. | Blocked pending Postgres test run + NOBYPASSRLS confirmation
2026-09-02 late | P1 Pagliano intake full cycle | Verified locally: intake -> contact+case in ws9, Pagliano sees it, Romanelli does not. Nothing deployed. | Closed / confirmed
2026-09-02 late | P3 Netlify deploy button | Fix pushed (f1ad2d3) but Netlify auto-deploy not triggering; missing NETLIFY_AUTH_TOKEN. | Pending token/config
2026-09-02 night | LexFlow ws7 'all sections empty' scare | /admin empty, Kanban invisible, matter/45 download broken - suspected regression from RLS/webhook work. | RESOLVED: was expired login credentials, not a bug. No regression audit needed.
2026-09-02 night | Webhook auth hole | Chatbot webhooks unauthenticated, hardcoded default secret, NULL workspace_id events possible. | FIXED and deployed (commit a2781f5): signature mandatory, fail-closed, workspace_id enforced.
2026-09-02 night | Google Calendar OAuth | 403 access_denied - app in Google Testing mode, user not in test users list. | User added self as test user in Google Console - resolved by user action, not code.
2026-09-03 AM | Intake manual name entry bug | Name field was autofill-locked, no manual entry possible. | FIXED and confirmed by user.
2026-09-03 AM | Cross-section reflection table v1 | Operator-Installer proposed intake->Contacts/Kanban/Cases reflection table. | Reviewed against Clio Grow/HubSpot/Lawmatics, upgraded with legal-specific stages + suppression logic + WhatsApp channel.
2026-09-03 AM | Automation tech clarification | User asked correct term for '3-day follow-up' automation. | Clarified: event-driven delayed task (Postgres scheduled_actions + worker, or Celery/Redis at scale), NOT simple cron.
2026-09-03 AM | Smart/adaptive email trend research | User asked about 'smart reflective emailing' AI trend. | Confirmed 2026 trend: agentic/adaptive email automation. Planned Phase 6, end of September, plug-in layer on scheduled_actions.
2026-09-03 AM | Delegation + skill-gap assessment request | User asked Hermes to self-assess: busy or free, can delegate, missing skill/tool. | Added as explicit requirement - awaiting Hermes response.
2026-09-03 AM | Contacts redesign requested | User wants HubSpot/Salesforce/Clio-style table view + bulk marketing actions. | Delegated to backend-dev (plan first). In progress.
2026-09-03 AM | Agentic JSON roadmap file created | Machine-readable task/status/dependency file for Hermes + future Kanban integration. | Delivered, sent to Hermes for feasibility assessment of /kanban/roadmap integration.
2026-09-03 PM | Romanelli cl1-cl10 local test | Admin sees all sub-tenants, each cl sees only own contacts/cases/calendar. | PASS locally, not deployed.
2026-09-03 PM | Return to Main Site bug found+fixed | cl1/cl2 sub-tenants had no way back to Romanelli main site. | Fixed locally (base.html, kanban.html, crm/init.py). NOT deployed - deploy now GATED (see Open_Decisions).
2026-09-03 PM | User resolved 6 open decisions | Deploy gate tightened; repoint scope confirmed Romanelli-only; matters limit still pending; internal contacts model DECIDED (Persona/Type field); WhatsApp assigned to backend-dev. | See Open_Decisions sheet for full detail - user says re-confirm before final JSON+prompt.

## Open_Decisions
Decision Needed | User's Answer / Status | Detail / Instruction
Deploy Return-to-Main-Site fix for cl1/cl2? | CONDITIONAL - NOT immediate go. | New deploy gate process: (1) backend-dev reports full audit; (2) ONLY IF report shows zero bugs / all clean -> Operator-Installer gives local link; (3) user picks 'weak spots' (highest conflict/bug risk areas) for targeted audit; (4) ONLY after targeted audit passes -> commit + deploy. No blind go on any pending fix from now on.
Repoint/fallback logic scope | CONFIRMED correct - do NOT generalize now. | Scope stays Romanelli-only. Test fully with Romanelli first, then replicate/correct pattern per-firm individually (e.g. separate access for Dima and Kirill inside LexFlow). Action titles/notes of what each sub-agent/user does must be visible in LexFlow Kanban (titles only, not full content).
Matters-per-client limit | STILL PENDING - not decided this round. | Re-raise explicitly next round: leave unlimited, or set a limit (and what number).
Contacts model for Romanelli admin (internal vs client-facing) | DECIDED: YES - separate internal contacts, via Persona/Type attribute (industry best practice, not a fully separate table). | Romanelli admin/paralegal must see staff (lawyers/assistant/office phone) plus each client-of-client's own contacts, filtered by workspace. Best practice (HubSpot/Salesforce): single Contact object + 'Type' field (Client/Lawyer/Assistant/Office) with automatic suppression of internal types from marketing sends. Build main Romanelli workspace contact table adapted for marketing use. Consider a JSON descriptor + web-plugin per app section so agents can navigate the app fast (extends the agentic-JSON concept app-wide, not only for task tracking).
Cross-section reflection table - approve to code? | NOT YET final - re-confirmation requested by user before code. | Do not let Operator-Installer code yet. User will re-confirm in next message, then JSON + final prompt follow.
WhatsApp integration - who builds it? | ASSIGNED. | Assigned to backend-dev.

## Contacts_Model_BestPractice
Object | Definition (industry standard - HubSpot/Salesforce) | Applies to LexFlow as
Contact | An individual person record - name, email, phone, role. The only object marketing emails can be sent to (HubSpot/Salesforce standard). | Client-of-client's own contacts (cl1, cl2...) AND Romanelli staff, in the SAME Contact table
Company | The organization a contact belongs to; one company has many contacts (one-to-many relationship). | Romanelli Studio = Company; each client-of-client = related Company/Account under it
Persona / Type attribute | A property on the Contact record marking role (e.g. Client, Employee, Lawyer, Assistant). Used to segment AND to auto-suppress internal contacts from marketing sends. | New field: contact_type = client ¦ lawyer ¦ assistant ¦ office. Filtered by workspace_id AND this new type field
Suppression list | Automatic exclusion of internal/employee-type contacts from all marketing campaigns and bulk sends. | Any drip/WhatsApp/bulk campaign must exclude contact_type != 'client'
Engagement/Activity log | All interactions (calls, emails, notes) attached to the contact record, visible team-wide. | Extend existing Activity timeline to log which sub-agent/user performed which action (title only, visible in Kanban)

## CrossSection_Reflection
Trigger Event | Status/Condition | Appears In | Action Triggered | Suppression Rule
New intake submitted | status = New Lead | Contacts, Kanban (New Lead column) | Auto-acknowledgment email + WhatsApp confirmation; internal task 'review lead' (owner, +1 day) | None (first-touch)
No response | 24h since last touch, no reply | Kanban stays, Activity log | Follow-up email #1 (24h) + optional WhatsApp nudge | Suppress if client replied
No response | 72h since last touch | Activity log | Follow-up email #2 (72h) | Suppress if replied or status changed
No response | 7 days since last touch | Activity log | Final check-in email + WhatsApp + flag to owner | Suppress if replied; mark 'Cold' if no reaction
Consultation booked | status = Consult Scheduled | Calendar, Kanban column move | Calendar invite + email reminder 24h before + WhatsApp reminder 2h before | None
Case opens, conflict check needed | status = Pending Conflict Check | Kanban (gated column) | BLOCK engagement letter until manually cleared | Hard gate - no auto-progress
Conflict cleared, retainer sent | status = Retainer Out | Matters, Kanban | Engagement letter auto-generated + WhatsApp 'document sent' notice | None
Retainer signed | status = Signed / Active Client | Contacts (promoted), Matters, dashboard | Welcome email + WhatsApp welcome + client portal access | Lock - no more lead-nurture emails
Case status changes | any transition | Kanban move, Activity timeline | Portal notification + WhatsApp status update (opt-in) + log entry | Only fire on real transitions
Task/deadline created | linked to case | Tasks + Calendar | Calendar event + email + WhatsApp to assigned avvocato | None
Hearing/court date approaching | 48h before hearing | Calendar, Dashboard alert | Email + WhatsApp to avvocato and client | Suppress if date changed/cancelled
Document uploaded | new file attached | Matters, Activity timeline | WhatsApp/email notice to relevant party | Suppress internal-only docs

## Automation_Architecture
Task Type | Trigger Model | Recommended Tech | Effort (MVP) | When to Upgrade
Immediate acknowledgment email | Event-driven (instant) | Direct Resend API call in request handler | ~1 hr | N/A
Delayed follow-up (24h/72h/7d) | Event-driven + delay | Postgres scheduled_actions + Railway worker (MVP) -> Celery+Redis (scale) | ~1-2 days (table approach) | Upgrade at >500 scheduled actions/day or need retries
Recurring reminders (hearing dates) | Time-based (cron) | Railway worker daily scan | ~4-6 hrs | N/A - cron correct here
WhatsApp notifications | Event-driven | WhatsApp Business API (Twilio or Meta Cloud API) | ~1-2 days (new integration) | N/A
Future: AI adaptive follow-up | Event-driven + AI decision layer | AI agent reads activity_log + notifications, decides next action | Planned end of Sept - do not build now | Build once scheduled_actions exists

## Delegation_Tracking
Task | Status | Assigned Agent | Effort Estimate | Notes
P1 - Intake manual name entry | DONE / deployed | Operator-Installer | - | Confirmed fixed by user
P2 - Cross-section reflection (base) | NOT approved yet - re-confirmation pending | Operator-Installer | TBD by Hermes | User wants to re-confirm before code, not final go yet
P2b - Conflict-check gate | Backlog (Phase 2) | Operator-Installer + backend-dev | TBD | Legal-specific hard gate requirement
P2c - Drip sequence (24h/72h/7d) | Backlog (Phase 3) | backend-dev | TBD | Needs scheduled_actions table first
WhatsApp integration | ASSIGNED | backend-dev | TBD | New channel, parallel-safe once scoped
Full app audit (read-only) + proactive suggestions | In progress - GATING further deploys | backend-dev | TBD | Must report clean/bug-found status BEFORE any local link is requested or deploy considered
Contacts redesign (HubSpot/Salesforce/Clio style) | In progress - model decided | backend-dev -> frontend-dev | TBD | DECIDED: Persona/Type field approach (Employee/Lawyer/Assistant vs Client), not separate table. See Contacts_Model_BestPractice sheet. Must support marketing use (bulk send, suppression).
Resend email test (Pagliano only) | In progress | LexFlow Head Admin | TBD | Isolated to ws9
Romanelli cl1-cl10 local isolation test | DONE locally | Operator-Installer | - | PASS - admin sees all, each cl sees only own data. NOT deployed.
Return-to-Main-Site bug (cl1/cl2) | FIXED locally - deploy GATED | Operator-Installer | - | New rule: deploy only after backend-dev confirms clean audit -> local link -> user picks weak spots -> targeted audit passes -> THEN commit+deploy
Full inventory (all tenants + repos + creds) | Requested, not yet delivered in full | Operator-Installer | - | Must precede further fixes; future shortcut command 'inventory'
RLS merge (feat/rls) | BLOCKED - do not merge | backend-dev | - | Wait for 18 tests on real Postgres + NOBYPASSRLS confirmation
Skill/tool gap self-assessment for delegation | Requested, awaiting Hermes answer | Operator-Installer (self) + crew | - | Part of automation task brief: is Hermes busy, can delegate, missing skill/tool
Agentic JSON roadmap / Kanban integration | Delivered, feasibility pending | Operator-Installer to assess | TBD | Awaiting Hermes feasibility + time estimate. Consider extending to per-section navigation JSON (see Contacts model decision)
Per-tenant staff access (Dima, Kirill inside LexFlow) | NEW - noted, not yet scoped | Operator-Installer | TBD | User wants to give separate access to named individuals inside LexFlow; their actions must show as titles in Kanban
AI adaptive email agent | Planned end of September | Unassigned - future | TBD | Architecture (scheduled_actions) must support as plug-in, no rewrite

## Master_Roadmap
Phase | Scope | Owner | Status
Phase 1 (Now) | Basic cross-section reflection (pending re-confirmation) + manual name entry (done) + Romanelli sub-tenant isolation fix (deploy gated) | Operator-Installer | In progress / gated
Phase 2 (Next sprint) | Conflict-check gate + first follow-up email (24h) + WhatsApp build (assigned) | Operator-Installer + backend-dev | Planned
Phase 3 | Full drip (24h/72h/7d) + suppression rules + scheduled_actions table | backend-dev | Planned
Phase 4 | Client portal notifications + WhatsApp status updates | backend-dev + frontend-dev | Planned
Phase 5 | Contacts redesign (Persona/Type model, table view, bulk marketing actions) | backend-dev + frontend-dev | In progress - model decided
Phase 6 (End of September target) | AI adaptive/reflective email agent on top of scheduled_actions | TBD | Planned