## Master Index
Project | Type | Local path | GitHub repo | Deploy platform | Live URL | Status (verified 2026-09-16)
LexFlow CRM (aLEXy intake & status suite) | Flask app, multi-tenant, RLS in progress | ~/Desktop/projects/services/LEGAL/LEXFLOW Production/lexflow-crm | Ole00007/lexflow-crm (pushed 2026-09-04) | Railway | https://web-production-031a6.up.railway.app/ | LIVE (200). Serves title 'aLEXy - Legal Intake & Status Suite'. /login?ws=lexflow 200, /admin/panel 200, /kanban 200. Public intake contract NOT enabled (POST /api/public/intake 404).
LexFlow Web-Site (marketing, EN/IT/RU) | Static HTML + generated it/ru, agent surface | ~/Desktop/projects/services/LEGAL/LEXFLOW Production/LEXFLOW Web-Site | NONE | NONE CHOSEN | not deployed | NOT DEPLOYED. HEAD 88f6cc9, 31 modified files in flight, 74 files hold lexflow.example.com placeholder. Blocked on domain + host (Ole -> Cloudflare).
LexFlow legacy landing page (LP) | Single-page HTML + Alessia widget | ~/Projects/LEGAL_backup/LexFlow-landing (git → Ole00007/LexFlow-landing, HEAD 47ed616, netlify.toml; old ~/LexFlow-landing path no longer exists) | Ole00007/LexFlow-landing (pushed 2026-09-02) | Netlify | https://poetic-kleicha-28d058.netlify.app/ | LIVE (200) - 'LexFlow - Studio Legale X'. Frozen by Ole, reference only. Older docs drop the -28d058 suffix, which is why poetic-kleicha.netlify.app 404s. Live deploy sha256 == origin/main:index.html; CTAs point at /login?ws=lexflow&back=<landing>.
LexFlow Chatbot (empathic secretary) | Flask, POST /chat | ~/Projects/LEGAL_backup/LexFlow-Chatbot (server.py + Procfile; old ~/LexFlow-Chatbot path no longer exists) | Ole00007/LexFlow-Chatbot (pushed 2026-05-19) | Railway | https://lexflow-chatbot-production.up.railway.app/ | LIVE (200); /health 200, /chat 405 (POST-only). Not wired to the new site (chatbotUrl path 404s).
LexFlow-MVP (first CRM iteration) | Flask + admin, Procfile + railway.toml | ~/Desktop/projects/services/LEGAL/LexFlow-MVP (branch main, HEAD f1ad2d3, dirty) | Ole00007/LexFlow-MVP (pushed 2026-09-02) | Railway | https://lexflow-mvp-production.up.railway.app/ | SUPERSEDED. Root returns 404 (service answers, no root route). Old docs calling this 'the backend' are stale.
RLS hardening work | Alembic migration + 18 cross-tenant tests | ~/Desktop/projects/services/LEGAL/lexflow-rls (branch feat/rls) | not pushed | n/a | n/a | BUILT, NOT MERGED. 11 RLS tables + 2 uncovered gap tables (contact_relationship, firm_team_member); 5 Alembic risks documented (card t_4637a500).
LexFlow saved-views worktree | Flask work copy | ~/Desktop/projects/services/LEGAL/lexflow-savedviews | not pushed | n/a | n/a | Working copy, no remote.
avibe-hindsight (memory backend) | Python service, bank avibe-hq | ~/Projects/avibe-hindsight (HEAD bfbe48e) | Ole00007/avibe-hindsight (pushed 2026-08-30) | Railway | https://avibe-hindsight-production.up.railway.app/health | HEALTHY (200). LLM = OpenRouter, FREE models only (Ole decision 2026-08-30).
Hermes roster | 24 independent profiles, operator-installer orchestrates | ~/.hermes/profiles/* | n/a | local | n/a | ACTIVE. operator-installer moved to OpenRouter deepseek/deepseek-v4.1-flash (resolved Nous-auth blocker).
Hermes Kanban boards | Inter-profile work channel (default + lexflow-learning) | ~/.hermes/kanban.db | n/a | local | n/a | ACTIVE, dispatcher running.
Obsidian vault | Knowledge layer (PARA + _Inbox, AGENT_RULES v2.2) | ~/Obsidian | github.com/Ole00007/obsidian-vault (private) | local git + GitHub | n/a | git repo; wikilink graph 210/226 notes, per-folder hubs. Hindsight syncs this layer.
AVIBE agency assets | Brand / site / proposal material | ~/Desktop/projects/services/AVIBE AGENCY | not pushed | n/a | n/a | Local (site placeholder, style book, agentic-architecture-package-v2).
lexflow_saas_factory deck | SaaS-factory deck + plan (HTML/PPTX/XLSX) | LEXFLOW Production/Lexflow Ecosystem & Saas Factory/ | not pushed | n/a | n/a | Local source material for this index.
Avv-Pagliano site / CRM | Client site + CRM tenant ws=pagliano | ~/Desktop/projects/services/LEGAL/LEXFLOW Production + vault Avvocato-Pagliano | Ole00007/Avv-Pagliano (pushed 2026-05-25) | Netlify + Railway tenant | https://verdant-crumble-021449.netlify.app/ | LIVE (200). Tenant /login?ws=pagliano on the CRM 200. Canary for the UX rollout order (Pagliano -> LexFlow -> Romanelli).
Romanelli-studio site | Client site + SEO audit LP | LEGAL/Romanelli 4page site_with Avv Pics + romanelli-studio SEO Audit LP | Ole00007/Romanelli-studio (pushed 2026-08-31) | ? | no URL recorded | Client site exists; live URL not recorded anywhere I could verify.
9 generated vertical sites | Templates from gen_site.py | ~/Obsidian/01-Projects/sites/ | not on GitHub | n/a | local only | bar-del-porto, beauty-studio, firenze-segreta, genova-segreta, liguria-viaggi, mare-fiori.it, massage-studio, nail-studio, parruchiere (+ .json configs, sites-INDEX.md).
Alena-Krot | SEO/AEO client (bilingual RU/IT) | ~/Desktop/projects/services/ALENA KROT/Alena Krot SEO | not on GitHub | ? | no URL recorded | Active client; vault hub 01-Projects/Alena-Krot-Med-Expert.
Carrozzeria 2DI | Auto-body client | ~/Desktop/projects/services/2DI Catrozzeria | not on GitHub | ? | no URL recorded | Client project material.
Commercialista-Client | Accounting client | vault 01-Projects/Commercialista-Client | not on GitHub | ? | no URL recorded | Client project material.

## Live Endpoints (Verified)
URL | Method | Code | Verdict / note
https://web-production-031a6.up.railway.app/ | GET | 200 | Live CRM (title: aLEXy - Legal Intake & Status Suite)
https://web-production-031a6.up.railway.app/login | GET | 200 | Login page
https://web-production-031a6.up.railway.app/login?ws=lexflow | GET | 200 | CORRECT CTA TARGET - workspace deep link
https://web-production-031a6.up.railway.app/login?ws=pagliano | GET | 200 | Pagliano tenant login
https://web-production-031a6.up.railway.app/admin/panel | GET | 200 | Superadmin surface
https://web-production-031a6.up.railway.app/kanban | GET | 200 | Board
https://web-production-031a6.up.railway.app/api/contacts | GET | 200 | Returns [] for anonymous by design (not a data leak)
https://web-production-031a6.up.railway.app/api/contacts | POST | 401 | Auth required - the reason site intake is unwired
https://web-production-031a6.up.railway.app/api/chatbot | GET | 404 | Route does not exist
https://web-production-031a6.up.railway.app/api/public/intake | GET | 404 | CONTRACT-DEFINED, NOT IMPLEMENTED
https://web-production-031a6.up.railway.app/api/public/intake | POST | 404 | Same - not implemented
https://web-production-031a6.up.railway.app/api/health | GET | 404 | Route does not exist - do NOT use as healthcheck
https://web-production-031a6.up.railway.app/robots.txt | GET | 404 | Not served
https://lexflow-chatbot-production.up.railway.app/ | GET | 200 | Chatbot service live
https://lexflow-chatbot-production.up.railway.app/health | GET | 200 | Chatbot healthcheck OK
https://lexflow-chatbot-production.up.railway.app/chat | GET | 405 | POST-only endpoint
https://lexflow-mvp-production.up.railway.app/ | GET | 404 | Service answers, no root route (superseded service)
https://avibe-hindsight-production.up.railway.app/health | GET | 200 | Memory backend HEALTHY
https://poetic-kleicha-28d058.netlify.app/ | GET | 200 | LIVE legacy LexFlow LP (Alessia widget)
https://poetic-kleicha.netlify.app/ | GET | 404 | Stale URL in older docs (missing -28d058)
https://lexflow-landing.netlify.app/ | GET | 404 | Stale URL in older docs
https://lexflow-lp.netlify.app/ | GET | 404 | Never deployed
https://lexflow.netlify.app/ | GET | 401 | Site EXISTS behind Netlify password protection - ownership/contents unverified
https://verdant-crumble-021449.netlify.app/ | GET | 200 | Avv. Diego Pagliano client site (old CRM CORS origin)
https://muzloto-apr-1f8f19.netlify.app/ | GET | 200 | LexTaskFlow architecture schema - not a LexFlow product surface
https://lexflow.pages.dev/ | GET | 200 | NOT OURS - South African legal-admin company. No LexFlow deployment on Cloudflare Pages
https://alexy.it/ | GET | 200 | Resolves with empty body; ownership unconfirmed - treat as unknown

## GitHub Repos (Live)
Repo | Visibility | Language | Last push | Note
LexFlow-MVP | public | Python | 2026-09-02 | First CRM iteration; superseded by the live services
LexFlow-landing | public | HTML | 2026-09-02 | Legacy LP -> Netlify poetic-kleicha-28d058
lexflow-crm | public | Python | 2026-09-04 | CANONICAL CRM repo (local aLEXy/ folder tracks it, branch lexflow_hermes_v1)
LexFlow-Chatbot | public | Python | 2026-05-19 | Chatbot -> Railway, live
aLEXy | public | Python | 2026-08-03 | Sister CRM product
avibe-hindsight | public | Python | 2026-08-30 | Memory backend
Avv-Pagliano | public | n/a | 2026-05-25 | Client site/CRM
Romanelli-studio | public | HTML | 2026-08-31 | Client site
obsidian-vault | public | HTML | 2026-08-30 | Vault sync repo (knowledge backup)
(private repos) | not enumerable | - | - | gh CLI not authenticated, no GH_TOKEN: private repos invisible to this audit. v2 listed avibe-agency-mvp + lextaskflow-e953c3e7 as private - existence unconfirmed.

## Local Repos
Path | Git remote | Branch / HEAD | State
~/Desktop/projects/services/LEGAL/LexFlow-MVP | Ole00007/LexFlow-MVP | main @ f1ad2d3 (2026-09-02) | Dirty (deleted csvs, modified db + pagliano/index.html). Has Procfile + railway.toml
~/Desktop/projects/services/LEGAL/aLEXy | Ole00007/lexflow-crm | lexflow_hermes_v1 @ 8ea18c2 (2026-07-20) | Dirty (.venv junk staged as deleted)
~/Desktop/projects/services/LEGAL/lexflow-rls | none | feat/rls | RLS work, unmerged
~/Desktop/projects/services/LEGAL/lexflow-savedviews | none | n/a | Work copy
~/Desktop/projects/services/LEGAL/LEXFLOW Production/LEXFLOW Web-Site | NONE - no remote | main @ 88f6cc9 | 31 modified files (CTA wiring card t_198870bd in flight). No deploy config
~/Desktop/projects/services/LEGAL/LEXFLOW Production/lexflow-crm | unknown (work copy) | n/a | Flask app copy
~/Desktop/projects/services/LEGAL/LEXFLOW Production/lexflow-calendar | none | n/a | Archive/work copy
~/Desktop/projects/services/LEGAL/LEXFLOW Production/lexflow-attachments | none | n/a | Archive/work copy
~/Projects/avibe-hindsight | Ole00007/avibe-hindsight | HEAD bfbe48e | free-only OpenRouter fallback chain
~/Projects/LEGAL_backup/LexFlow-landing | Ole00007/LexFlow-landing | main @ 47ed616 | Relocated here 2026-09; has netlify.toml; live sha256 == origin/main:index.html
~/Projects/LEGAL_backup/LexFlow-Chatbot | Ole00007/LexFlow-Chatbot | n/a | server.py + Procfile
~/Projects/LEGAL_backup/ | mixed | n/a | Also holds aLEXy/, Romanelli-studio/, pagliano_backup_readonly/, lexflow-landing-visual/
~/Projects/avibe-flowershop | none | n/a | Local, no git
~/LexFlow-landing | n/a | n/a | PATH NO LONGER EXISTS - repo relocated to ~/Projects/LEGAL_backup/LexFlow-landing
~/LexFlow-Chatbot | n/a | n/a | PATH NO LONGER EXISTS - repo relocated to ~/Projects/LEGAL_backup/LexFlow-Chatbot

## Obsidian Vault
Item | Path | State (2026-09-16)
Vault root | ~/Obsidian | PARA + _Inbox; git repo
Rules | ~/Obsidian/_Meta/AGENT_RULES.md (v2.2) + symlink ~/Obsidian/AGENT_RULES.md | Vault boundary + git/deployment boundary
LexFlow hub | 01-Projects/LexFlow/LexFlow-INDEX.md | Hub linking every LexFlow note
LexFlow notes added by this pass | _Inbox/LexFlow-Web-Site-Agent-Surface-2026-09-15.md, _Inbox/LexFlow-Web-Site-Session-Recap-Batch2-2026-09-13.md, _Inbox/LexFlow-Ecosystem-Index-v3-2026-09-16.md | New files land in _Inbox per AGENT_RULES
Legacy LexFlow folder | 01-Projects/AVibe-CRM/LexFlow/ | Older mirror (July material) - do not confuse with 01-Projects/LexFlow
Client hubs | 01-Projects/{Alena-Krot-Med-Expert, Avvocato-Pagliano, Studio-Romanelli, Carrozzeria-2DI, Commercialista-Client, sites} | Per-client folders
Daily notes | 05-Daily/YYYY-MM-DD.md | 2026-09-16 entry appended by this pass
Wikilink graph | scripts/vault_autolink.py, vault_graph_extract.py | 210/226 notes linked, 409 edges (2026-08-26 retrofit)
Hindsight | bank avibe-hq (Railway) | Vault sync = long-term memory layer

## Gaps & Blockers
# | Gap | Owner | Impact
1 | Web-site has no host, no remote, no domain | Ole (Cloudflare decision) | Site cannot deploy; 74 files hold lexflow.example.com placeholder
2 | POST /api/public/intake not implemented; POST /api/contacts 401 | backend-dev / operator-installer | Website lead capture dead-ends; intake falls back to WhatsApp
3 | llms.txt line 18 says calendar/cloud/notifications NOT shipping, contradicting faq_a15 | frontend-developer | Published factual contradiction on the site
4 | 27 webhook URLs null; intakeEndpoint null; WhatsApp digits unconfirmed | Ole + frontend-developer | Silent failures / possibly wrong contact number
5 | IT/RU article bodies pending | Ole | Articles stay English unless registered in templates/article_content.py
6 | RLS built but unmerged; 2 uncovered tables | backend-dev (t_4637a500) | Multi-tenant safety not enforced at DB level
7 | lexflow.netlify.app password-protected site ownership unknown | Ole | Possible orphaned deploy holding the 'lexflow' Netlify name
8 | GH_TOKEN/gh unauthenticated; railway CLI binary missing; no netlify token | Ole | No agent can enumerate private repos or platform dashboards
9 | Repo-root migration to ~/projects unapproved | Ole | Agents keep hitting Desktop TCC permission walls
10 | Pilot figures (34% faster, 2.4x billable, 91% WAU) unverifiable from CRM schema | Ole | Marketing claims need confirm-or-replace