## Overview
LexFlow CRM — Multi-Tenant Rollout Tracker
Generated: 2026-09-03 ¦ Owner: Olesia Rasing ¦ v2 — surgical update
Sheet Index
Roster | People, testing customers, AI agents — status & workspace mapping
Delegation_Tracking | Global rules + delegated tasks + Parallel Tracking board
Contact_Model | Internal vs client-facing contact model, fields, best-practice source
Decisions_Log | Open/closed decisions (seat limits, matters cap, Elisa go-live)
Elisa_Access_Plan | 4-phase gated access plan for Elisa integration (Stefano)
Key Open Decisions
• Matters (cases) per tenant: UNLIMITED for now — tracking mechanism TBD.
• Memory/storage per tenant: UNLIMITED for now — same tracking mechanism TBD.
• Seat limit per tenant: DECIDED = 5 seats/tenant, starting now. Reconfigurable later via config value.
• Elisa (LexFlow PA agent): 4-phase gated plan approved (Sandbox→Read-Only→Staging→Production). See Elisa_Access_Plan sheet.
• Internal vs client-facing contacts: approved as TWO separate models — implementation plan pending backend-dev proposal.
• QASkills.sh: verified safe, APPROVED to install now (see Delegation_Tracking).