## Overview
LexFlow Agentic Architecture v3.1
Cloudflare-expert nickname roster + non-schema-inventing interoperability + parallel roadmap
This revision
• Admy, Smoothy, Backy, Fronty each hold an explicit expert-level Cloudflare Workers specialization
• Prompts (PROMPT_ADMY.md, PROMPT_SMOOTHY.md) and both roadmap PNGs are delivered separately, not in this ZIP
• No new CRM schema — every field remains <TBD-audit> pending Admy's verified confirmation
• Parallel backlog and risk register carried over from v3, unchanged in structure
Sheet | Purpose | Update mode
Agent Roster | Nickname-first roles + Cloudflare expertise | Append/version
Building Skill Matrix | Cloudflare expert-skill proof, 4 building agents | Append
Parallel Backlog | Concurrent tasks by agent swimlane | Update status
Interfaces v3 | Placeholder contracts pending audit | Replace after audit
Risks v3 | Risk register | Append; never erase
Decisions | ADR-001 to ADR-017 | Append-only
Generated | 2026-09-17

## Agent Roster
Nickname | Role | Primary Skills (multifunctional, overlap intended) | Status vs. prior session | Source / trust signal
Admy | CEO / Head Admin | Architecture coordination, delegation, approval orchestration, release decisions; business/legal/accountancy oversight (with Smarty); QA & Critic oversight of the whole roster. Cloudflare Workers expert focus: multi-project Workers-for-Platforms patterns, Service Bindings across Workers, cross-account cost/quota governance, AI Gateway policy ownership, Wrangler, compatibility-date/flag discipline, final security sign-off on any Worker reaching production. | Existing — name fixed; scope expanded | Cross-agent; oversees all
Smoothy | Operational Director / Operator-Installer | Orchestration, planning, security gatekeeper, merge/deploy approval, release-gate owner across any active project. Cloudflare Workers expert focus: Wrangler CLI (dev/deploy/tail/secret/versions), Workers Builds CI/CD, staged/preview/production promotion, Durable Objects lifecycle and hibernation, Queues + Workflows durability patterns, Turnstile + edge rate limiting, Workers Observability/logpush, rollback procedures for any deploy. | Existing — name fixed | cloudflare/skills bundle (Wrangler + Durable Objects + Workers best practices, Cloudflare-maintained, live-doc-synced); Claude Code Security Review action for pre-merge gates
Backy | Full-stack (backend-leaning) | Backend API design across Flask and any modern backend stack a project needs; delegated QA/testing lead for the crew. Cloudflare Workers expert focus: Workers runtime fundamentals (V8 isolates, fetch handler, ctx.waitUntil), D1 (SQL binding), Hyperdrive (pooled Postgres/MySQL access), KV, R2, Queues consumers, Workflows step functions, MCP server implementation on Workers, Cloudflare Agents SDK (Durable Object-backed agent state), Workers AI bindings/function calling, service-to-service auth between Workers and existing Flask API. | Existing — name fixed; scope widened beyond Flask-only | petrkindlmann/qa-skills (cross-agent QA standard); API Security Testing skill (OWASP API Top 10 coverage)
Fronty | Full-stack (frontend-leaning) | Frontend and gateway work across any modern frontend framework a project needs. Cloudflare Workers expert focus: Workers Static Assets and the Pages-to-Workers migration path, legacy Workers Sites patterns, HTMLRewriter, Cache API, KV-backed feature flags/edge personalization, Turnstile widget integration, SSR framework adapters on Workers (Next.js/Astro/Remix), asset bindings + wrangler.jsonc configuration, custom domains/routes. | Existing — name fixed; scope widened beyond one framework | cloudflare/skills bundle (same Cloudflare-owned Worker/Pages skill set)
Daty | AI/Data — growth analytics, SEO/AEO, CRM intelligence | Hermes-powered; SEO/AEO, UTM attribution, CTA experiments, personalization, campaign analytics (content creation delegated to Mr. Beast) | Existing — name fixed; content duties split to Mr. Beast | AgricIDaniel/claude-seo (25 sub-skills, 18 specialist agents); Cloudflare Agents SDK native Session API for conversation state
Crunchy | QA & Critic / Tester (independent gate) | Security, regression, API contracts, tenant isolation, rollback, performance, agent testing; UX/UI review from agentic and human perspective; independent from Backy's delegated lead | New nickname added | Same QA-skill sources as Backy, applied as independent critic/gate
Memo | Memory Curator | Agent memory governance; CRM/Obsidian/Hindsight sync; decision-history and audit continuity; reports to Admy/Smoothy and directly to the user | Existing — kept separate from Daty for clean audit trails | Cloudflare Agents SDK Session/state APIs; cron-driven sync jobs
Sally | Sales Funnels & CRM | Customer relations, chatbot control, lead capture, customer activity tracking, pipeline automation, segmentation, personalized email/messaging workflows | New nickname added | Cloudflare Agents SDK for chatbot/session state; MCP tools for CRM actions
Mr. Beast | Content Creator | Copywriting, content creation and publishing, coordinating with Daty on SEO/AEO and campaign rollout | New nickname added (split from Daty) | Content-adjacent skill packs; keyword/attribution alignment with Daty
Smarty | Legal & Accountancy Expert | Regulatory compliance, runbooks, P&L build/read/control, investment-pitch prep, legal review of CRM data handling | New nickname added | Domain-expert profile; works with Admy on business/legal/accountancy oversight

## Building Skill Matrix
Agent | Workers runtime (isolates/fetch) | Wrangler CLI | Durable Objects | D1 / Hyperdrive | KV | R2 | Queues | Workflows | Agents SDK | MCP servers | Workers AI / AI Gateway | Static Assets & Pages migration | Turnstile & rate limiting | Observability / logpush | Service Bindings | Security review
Admy | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert
Smoothy | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert
Backy | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert
Fronty | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert | Expert

## Parallel Backlog
task_id | track | task | lead_agent | supporting_agents | start | finish | depends_on | priority | status | notes
LF3-001 | Audit | Read-only audit: Flask models, migrations, routes, serializers, permissions | Admy | Backy;Fronty | 2026-09-18 | 2026-09-23 |  | P0 | not_started | Blocks every other track
LF3-002 | Audit | Read-only audit: current Cloudflare Pages/Workers config, domains, bindings | Smoothy | Fronty | 2026-09-18 | 2026-09-22 |  | P0 | not_started | Parallel with LF3-001
LF3-003 | Audit | Confirm real field names to replace INTEROP_CONTRACTS placeholders | Admy | Backy | 2026-09-23 | 2026-09-25 | LF3-001 | P0 | not_started | Gate before any contract work
LF3-010 | Gateway | Scaffold staging Worker gateway (no schema change) | Smoothy | Backy;Fronty | 2026-09-24 | 2026-09-29 | LF3-002;LF3-003 | P0 | not_started | Parallel with LF3-011/012
LF3-011 | Gateway | Add Turnstile + rate limiting + schema validation on gateway | Fronty | Crunchy | 2026-09-24 | 2026-09-29 | LF3-002 | P1 | not_started | Runs concurrently with LF3-010
LF3-012 | Gateway | Wire staging lead form to gateway using existing intake endpoint | Backy | Sally | 2026-09-26 | 2026-10-01 | LF3-003;LF3-010 | P1 | not_started | Uses real endpoint only
LF3-020 | MCP | Define narrow-but-not-too-narrow MCP tools mapped to real endpoints | Backy | Admy;Crunchy | 2026-09-26 | 2026-10-02 | LF3-003 | P1 | not_started | Grouped by business action
LF3-021 | MCP | Read-only MCP tools for Daty/Sally in test workspace | Fronty | Daty;Sally | 2026-10-01 | 2026-10-06 | LF3-020 | P1 | not_started | Parallel with LF3-022
LF3-022 | MCP | Guarded write tool: activity.log with idempotency + audit | Backy | Crunchy;Memo | 2026-10-01 | 2026-10-08 | LF3-020 | P1 | not_started | First guarded write tool
LF3-030 | CRM Workflow | Sally: chatbot + lead capture + segmentation via existing intake flow | Sally | Backy;Daty | 2026-10-02 | 2026-10-10 | LF3-012;LF3-021 | P1 | not_started | Parallel with LF3-031/032
LF3-031 | Marketing | Daty: UTM attribution + CTA experiment via edge KV | Daty | Fronty;Mr. Beast | 2026-10-02 | 2026-10-10 | LF3-011 | P1 | not_started | Edge-only state
LF3-032 | Content | Mr. Beast: content/copy pipeline on site Worker+Assets preview | Mr. Beast | Fronty | 2026-10-02 | 2026-10-09 | LF3-002 | P2 | not_started | No CRM data involved
LF3-040 | Personalization | Sally + Daty: personalized follow-up draft workflow (draft-only) | Sally | Daty;Crunchy | 2026-10-08 | 2026-10-16 | LF3-030;LF3-031 | P1 | not_started | No send permission by default
LF3-041 | Governance | Memo: continuous audit/event sync | Memo | Admy | 2026-10-06 | 2026-10-16 | LF3-022;LF3-030 | P1 | not_started | Runs alongside everything
LF3-050 | Legal | Smarty: regulatory/PII review of intake + agent tool data flows | Smarty | Admy;Crunchy | 2026-09-26 | 2026-10-10 | LF3-001 | P1 | not_started | Parallel with build tracks
LF3-051 | Business | Smarty + Admy: P&L visibility and investment-pitch prep | Smarty | Admy | 2026-10-01 | 2026-10-15 |  | P2 | not_started | Independent of technical tracks
LF3-060 | QA Gate | Crunchy: independent review of gateway + MCP + workflows before merge | Crunchy | Backy | 2026-10-09 | 2026-10-17 | LF3-012;LF3-022;LF3-030;LF3-031 | P0 | not_started | 5/5 confidence required
LF3-061 | Approval | Admy + Smoothy: staging cutover decision (final plan pending) | Admy | Smoothy;Crunchy | 2026-10-18 | 2026-10-18 | LF3-060;LF3-050 | P0 | not_started | Human approval gate
LF3-070 | Site Hybrid | Fronty: Workers+Static Assets preview parity vs current Pages | Fronty | Backy;Crunchy | 2026-10-02 | 2026-10-14 | LF3-002 | P2 | not_started | Parallel; no cutover yet

## Interfaces v3
interface_id | kind | name | producer | consumer | auth | source_of_truth | pii | side_effect | status | notes
IF3-01 | HTTP | existing-intake-endpoint (name TBD-audit) | Existing Flask API | Worker gateway | service token | Existing PostgreSQL | TRUE | TRUE | pending-audit | Must confirm real route name
IF3-02 | MCP | <TBD-audit>.search | MCP tool layer | Daty;Sally;Crunchy | OAuth/service + workspace scope | Existing PostgreSQL via Flask API | TRUE | FALSE | pending-audit | Read-only
IF3-03 | MCP | activity.log (underlying table TBD-audit) | MCP tool layer | Sally;Backy | OAuth/service + approval policy | Existing PostgreSQL via Flask API | TRUE | TRUE | pending-audit | Guarded write, idempotent
IF3-04 | Event | cta.viewed / utm.attributed | Worker gateway | Daty;Queue | service binding | Edge KV (not CRM DB) | FALSE | FALSE | planned | Edge-only, no CRM write
IF3-05 | Static | site-assets-v2 preview | Workers Builds | Browser;Mr. Beast | public | Git | FALSE | FALSE | planned | Preview beside existing Pages site

## Risks v3
risk_id | category | risk | likelihood | impact | mitigation | trigger | owner_nickname | status
R3-01 | Governance | Placeholder schema fields get treated as real by mistake | medium | critical | Admy personally signs off every placeholder replacement; Crunchy checks before merge | Contract file still contains TBD-audit at merge time | Admy | open
R3-02 | Scope | Overlapping building-agent skills cause duplicate/conflicting parallel work | medium | medium | Smoothy tracks file/contract locks before dispatching parallel tasks | Two agents editing same file/contract | Smoothy | open
R3-03 | Data | New Flask endpoint silently introduces a field not reviewed by Admy/Crunchy | medium | critical | All new endpoints require Admy+Crunchy sign-off before merge | Undocumented field in serializer | Crunchy | open
R3-04 | Governance | Memo's audit trail falls behind fast parallel shipping | medium | high | Memo syncs continuously, not at phase end | Merge without matching audit entry | Memo | open
R3-05 | Legal | PII/legal-data handling reviewed too late in fast-parallel model | medium | critical | Smarty's review runs from week one | New data flow shipped before Smarty review | Smarty | open

## Decisions
decision_id | title | status | decision | rationale
ADR-015 | Building agents formally certified as Cloudflare Workers experts | accepted | Admy/Smoothy/Backy/Fronty each get a distinct Workers specialization plus shared baseline fluency | User required best-expert Workers competence across all four
ADR-016 | Prompts must eliminate guessing | accepted | Prompts rewritten with definitions, procedures, and mandatory escalation triggers | Reduce ambiguity-driven agent errors
ADR-017 | Roadmap visuals delivered separately from ZIP | accepted | Prompts and PNGs delivered standalone; ZIP holds registries/workbook only | User explicitly requested this split for faster review