## 00 Start Here
LexFlow SaaS Software Factory
A free-first, evidence-gated implementation plan adapted from Ras Mic’s Isolate → Build → Prove → Ship method and your actual CRM, SEO, Obsidian, Airtable, deployment and cron work.
Workbook index
00 Start Here
01 Catalog Data
02 Routing Matrix
03 Factory Plan
04 Cronjobs
05 Reliability Cost
06 30-Day Rollout
Decision | Your operating standard
Objective | Finish LexFlow safely while reducing AI spend and avoiding blocked work from API/OAuth failures.
Factory rule | Never build on main. One task = one brief + one worktree + one branch + one evidence bundle + one PR.
Model rule | No-agent script first → FREE model for sanitized low-risk work → promo model for build → Claude/premium only for critical review.
Permission rule | Agents may not write CRM/Airtable, send email, change personal appointments, merge, or deploy production without explicit approval.
Privacy rule | No legal-client content, OAuth tokens, calendar bodies, private notes or production data in anonymous/rotating free models.
Reliability rule | Every agent job has timeout, retry cap, preflight, checkpoint, fallback provider and resumable worktree.
Initial capacity | Start with 2 parallel worktrees; rise to 4 after 10 clean PRs. Do not copy the podcast’s 15-agent scale immediately.
Completion target | 7 days to install the factory; 30 days to validate it on 10–20 real CRM tasks.
When | Action
Day 1 | Create six markdown control files and protected main branch
Day 2 | Install/test worktree command and one small feature
Day 3 | Add deterministic tests and before/after evidence
Day 4 | Add independent review and PR template
Day 5 | Deploy no-agent health/backup/credit cronjobs
Days 6–7 | Run two parallel low-risk tickets
Weeks 2–4 | Measure cost, cycle time, escaped defects and provider failures; tune routing

## 01 Catalog Data
Nous catalog snapshot
User-provided live snapshot, 2026-09-15. Includes every active promo, every named free model, and every row shown on page 1 of 7 (1–50 of 322). Prices: USD per 1M tokens.
Promo model | Model ID | Input $/1M | Output $/1M | List input | List output | Discount | Blended cost: 5M in + 1M out
Inception: Mercury 2.5 | inception/mercury-2.5 | 0.04 | 0.15 | 0.2 | 0.75 | 80%
Qwen: Qwen3 Coder 480B A35B | qwen/qwen3-coder | 0.22 | 1.8 | 0.97 | 4.88 | 77%
Qwen: Qwen3 Coder 30B A3B Instruct | qwen/qwen3-coder-30b-a3b-instruct | 0.07 | 0.27 | 0.29 | 1.46 | 76%
Google: Gemma 4 26B A4B | google/gemma-4-26b-a4b-it | 0.04 | 0.22 | 0.15 | 0.6 | 72%
Upstage: Solar Pro 4 | upstage/solar-pro4 | 0.09 | 0.36 | 0.3 | 1.2 | 70%
Qwen: Qwen3.8 27B | qwen/qwen3.8-27b | 0.15 | 1.88 | 0.42 | 2.55 | 65%
Qwen: Qwen3 30B A3B Instruct 2507 | qwen/qwen3-30b-a3b-instruct-2507 | 0.05 | 0.19 | 0.13 | 0.52 | 63%
Qwen: Qwen3 Coder Next | qwen/qwen3-coder-next | 0.12 | 0.8 | 0.3 | 1.5 | 60%
Qwen: Qwen3 14B | qwen/qwen3-14b | 0.1 | 0.22 | 0.23 | 0.91 | 56%
Qwen: Qwen3.5-35B-A3B | qwen/qwen3.5-35b-a3b | 0.08 | 0.75 | 0.16 | 1.3 | 51%
DeepSeek: DeepSeek V4.1 Flash | deepseek/deepseek-v4.1-flash | 0.15 | 0.6 | 0.3 | 1.2 | 50%
Google: Gemini 3.8 Flash | google/gemini-3.8-flash | 0.75 | 3.75 | 1.5 | 7.5 | 50%
Z.ai: GLM 5.3 Flash | z-ai/glm-5.3-flash | 0.07 | 0.25 | 0.15 | 0.5 | 50%
Google: Gemini 3.7 Flash | google/gemini-3.7-flash | 0.75 | 3.75 | 1.5 | 7.5 | 50%
OpenAI: GPT-5.6 Sol Pro | openai/gpt-5.6-sol-pro | 2 | 10 | 4 | 20 | 50%
OpenAI: GPT-5.6 Sol | openai/gpt-5.6-sol | 2 | 10 | 4 | 20 | 50%
Qwen: Qwen3 235B A22B Instruct 2507 | qwen/qwen3-235b-a22b-2507 | 0.09 | 0.35 | 0.15 | 0.6 | 41%
Poolside: Laguna XS 2.1 | poolside/laguna-xs-2.1 | 0.06 | 0.12 | 0.1 | 0.2 | 40%
MoonshotAI: Kimi K2.6 | moonshotai/kimi-k2.6 | 0.57 | 2.4 | 0.95 | 4 | 40%
Z.ai: GLM 5 | z-ai/glm-5 | 0.6 | 1.92 | 1 | 3.2 | 40%
Z.ai: GLM 5.3 | z-ai/glm-5.3 | 0.88 | 2.97 | 1.4 | 4.4 | 37%
MoonshotAI: Kimi K3 | moonshotai/kimi-k3 | 2 | 11.2 | 3 | 15 | 33%
Qwen: Qwen3.6 27B | qwen/qwen3.6-27b | 0.3 | 2 | 0.45 | 2.7 | 33%
Z.ai: GLM 5.1 | z-ai/glm-5.1 | 0.97 | 3.04 | 1.4 | 4.4 | 31%
Xiaomi: MiMo-V2.5-Pro | xiaomi/mimo-v2.5-pro | 0.3 | 0.61 | 0.43 | 0.87 | 30%
DeepSeek: DeepSeek V4 Pro 0813 | deepseek/deepseek-v4-pro-0813 | 0.96 | 2.88 | 1.32 | 3.96 | 27%
Free model | Access | Deployment note | Data boundary
inclusionAI: Ling 3.0 Flash Fin | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
inclusionAI: Ling 3.0 Flash Sante (free) | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
Meituan: LongCat 2.0 | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
Poolside: Laguna S 2.1 | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
Poolside: Laguna XS 2.1 | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
StepFun: Step 3.7 Flash | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
Upstage: Solar Pro 4 | FREE | Use exact FREE catalog entry; some names also have paid routes | Sanitized/public/non-critical only
Rank shown | Model | Type | Access | Input $/1M | Output $/1M | Discount
1 | Meituan: LongCat 2.0 | Text | FREE
2 | Upstage: Solar Pro 4 | Text | FREE
3 | DeepSeek: DeepSeek V4 Flash 0731 | Text | PAID | 0.04 | 0.1
4 | DeepSeek: DeepSeek V4.1 Flash | Text | PROMO | 0.15 | 0.6 | 50%
5 | Poolside: Laguna S 2.1 | Text | FREE
6 | Z.ai: GLM 5.3 Flash | Text | PROMO | 0.07 | 0.25 | 50%
7 | DeepSeek: DeepSeek V4 Flash 0423 | Text | PAID | 0.05 | 0.14
8 | inclusionAI: Ling 3.0 Flash Fin | Text | FREE
9 | inclusionAI: Ling 3.0 Flash Sante (free) | Text | FREE
10 | DeepSeek: DeepSeek V4 Pro 0423 | Text | PAID | 0.96 | 1.91
| Z.ai: GLM 5.2 | Text | PAID | 0.9 | 2.83
| Claude Sonnet 5 | Other | PAID | 2 | 10
| OpenAI: GPT-5.6 Luna | Text | PAID | 0.2 | 1.2
| Anthropic: Claude Fable 5.1 | Text | PAID | 10 | 50
| DeepSeek: DeepSeek V4 Pro 0813 | Text | PROMO | 0.96 | 2.88 | 27%
| OpenAI: GPT-5.6 Luna Pro | Text | PAID | 0.2 | 1.2
| Poolside: Laguna XS 2.1 | Text | FREE
| Z.ai: GLM 5.3 | Text | PROMO | 0.88 | 2.97 | 37%
| Google: Gemini 3.8 Flash | Text | PROMO | 0.75 | 3.75 | 50%
| Qwen: Qwen3.8 Flash | Text | PAID | 0.15 | 0.47
| Claude Opus 5 | Other | PAID | 5 | 25
| DeepSeek: DeepSeek V4 Flash Latest | Text | PAID | 0.04 | 0.1
| OpenAI: GPT-5.6 Sol | Text | PROMO | 2 | 10 | 50%
| MoonshotAI: Kimi K3 | Text | PROMO | 2 | 11.2 | 33%
| OpenAI: GPT-6 Astra | Text | PAID | 10 | 50
| Claude Opus 4.8 | Other | PAID | 5 | 25
| MiniMax: MiniMax M3 | Text | PROMO | 0.23 | 0.96 | 23%
| Tencent: Hy3 | Text | PROMO | 0.1 | 0.43 | 20%
| xAI: Grok 4.6 | Text | PAID | 2 | 6
| Google: Gemini 3.7 Flash | Text | PROMO | 0.75 | 3.75 | 50%
| Z.ai: GLM 5.3 Flash | Text | PAID | 0.25 | 0.83
| Tencent: Hy4 preview | Text | PAID | 0.83 | 2.5
| OpenAI: GPT-6 Astra Flex | Text | PAID | 5 | 25
| Xiaomi: MiMo-V2.5-Pro | Text | PROMO | 0.3 | 0.61 | 30%
| OpenAI: GPT-5.6 Terra | Text | PAID | 2 | 12
| Qwen: Qwen3.8 Max (0902) | Text | PAID | 2 | 6
| OpenAI: GPT-5.6 Sol Pro | Text | PROMO | 2 | 10 | 50%
| Claude Fable 5 | Other | PAID | 10 | 50
| OpenAI: GPT-5.4 Mini | Text | PAID | 0.75 | 4.5
| OpenAI: GPT-6 Astra Pro | Text | PAID | 10 | 50
| Z.ai: GLM 5.3 | Text | PAID | 2.31 | 7.26
| StepFun: Step 3.7 Flash | Text | PROMO | 0.16 | 0.92 | 20%
| Meituan: LongCat 2.0 | Text | PAID | 0.3 | 1.2
| DeepSeek: DeepSeek V4 Flash Vision Exp | Text | PAID | 0.22 | 0.65
| Claude Haiku 4.5 | Other | PAID | 1 | 5
| Claude Sonnet 4.6 | Other | PAID | 3 | 15
| Qwen: Qwen3.7 Flash | Text | PAID | 0.03 | 0.13
| Poolside: Laguna S 2.1 | Text | PROMO | 0.09 | 0.18 | 10%
| Claude Opus 4.6 | Other | PAID | 5 | 25
| MoonshotAI: Kimi K2.7 Code | Text | PAID | 0.68 | 3.4
Source | https://portal.nousresearch.com/models

## 02 Routing Matrix
Model routing for your real tasks
Assignments prioritize zero cost, privacy boundaries, resumability and evidence. “Free first” does not mean free models touch confidential LexFlow/legal data.
Task | Output | Free/no-agent lane | Primary promo/paid | Escalation | Free-lane data | Non-negotiable gate | Fit confidence
Feature intake/spec | Acceptance criteria, non-goals, risks | Solar Pro 4 FREE | Qwen3 235B A22B ($0.09/$0.35) | Claude Sonnet 5 | Public/sanitized | Human approves before code | High
Small Flask fix | Narrow diff + unit test | Laguna XS/S FREE canary | Qwen3 Coder 30B ($0.07/$0.27) | Sonnet 5 | Synthetic fixtures only | No auto-merge | High
Large CRM feature | Service-layer code + migration + tests | Free model only for task decomposition | Qwen3 Coder 480B ($0.22/$1.80) | Sonnet 5; Opus 5 if critical | No production/client data | Independent proof/review | High
Elisa/a-Lexy parity | UI/intake behavior parity | Solar FREE inventories public pages | Qwen3 Coder 480B | Sonnet 5 | Public copy/screens only | Keep two-app boundary until approved | High
OAuth/auth/RLS/payments | Trust-boundary implementation | No anonymous free model | Qwen Coder for test scaffolds | Sonnet 5 build/review; Opus 5 design | Approved private provider only | Least privilege + human approval | High
Debug logs/screenshots | Root-cause, one check at a time | Laguna/Solar FREE after redaction | DeepSeek V4.1 Flash ($0.15/$0.60) | Sonnet 5 complex incident | Redacted only | Backup + verify each command | Medium
Railway/Netlify/Cloudflare | Deploy commands, env diff, rollback | No-agent smoke scripts | Qwen3 Coder 30B | Sonnet 5 blocked deploy | Redacted config/logs | Staging first; production approval | High
SEO/GEO/AEO | GSC/crawl delta + actions | Script first; Solar/Step FREE summarize change | GLM 5.3 Flash ($0.07/$0.25) | Sonnet 5 weekly strategy | Public/aggregate metrics | No LLM on NO_CHANGE | High
Competitive research | Current sourced comparison | Solar FREE first synthesis | Qwen3 235B | Sonnet 5 decision memo | Public web only | URL/date/source required | High
Landing copy/translation | Multilingual drafts and parity | Solar Pro 4 FREE | Qwen3 235B | Sonnet 5 high-stakes wording | Public/non-confidential | Human publishes | High
Obsidian curation | Agent logs separate from personal notes | No-agent link/duplicate scan | Solar FREE summarizes flags | Sonnet 5 taxonomy change | No private vault to anonymous route | Staging folder only | High
Airtable milestones | Approval-ready status diff | No-agent read/delta | GLM 5.3 Flash summary | Sonnet 5 schema redesign | IDs/status if approved | No write without permission | High
Email/calendar | Read, summarize, draft, limited appointment sync | No anonymous free model | Haiku 4.5 for approved low-risk text | Sonnet 5 | Approved account only | Never send unless asked; change only agent/CRM-created events | High
Credit/provider monitoring | Balance, delta, anomaly | No-agent script | Step FREE only if anomaly needs explanation | None | Billing metadata only | Never auto-purchase | High

## 03 Factory Plan
Factory: Intake → Isolate → Build → Prove → Ship
Ras Mic’s four stages are retained; Intake and Observe are added for a privacy-first SaaS. Five or six markdown files make the workflow harness/model independent.
Stage | Markdown control | Model | Copy-paste instruction/command | Done when | Human gate | Time | Gain | Risk | Mitigation
0 Intake | FEATURE.md | Qwen3 235B; Solar FREE if sanitized | Turn request into scope, non-goals, impacted files, risks, acceptance tests, proof plan and rollback. Do not code. | Approved brief | You | 10–30 min | Fewer reworks | Wrong scope | No build before approval
1 Isolate | new-feature.md | No LLM + shell | git fetch origin && git worktree add ../wt-<ID> -b feat/<ID> origin/main | Clean worktree/branch from origin/main | Agent reports path; you inspect | 2–5 min | Conflict-free parallel work | Wrong base | git status + branch check
2 Build | code-structure.md | Qwen3 Coder 30B/480B; Laguna FREE canary | Implement approved scope only. Use service layer, reversible migration, tests, no secrets, no unrelated refactor. | Lint/type/unit green | No prod credentials | 30 min–1 day | Cheap throughput | Sloppy code | Small tickets + CI
3 Prove | evidence-driven-testing.md + before-after.md | Scripts first; Qwen interprets failure; Sonnet validates | Map every acceptance criterion to command, result and artifact. Capture before/after UI or numeric metric. | Evidence bundle complete | You inspect visual proof | 10–60 min | Trust evidence, not claims | False positive | Replay clean environment
4 Ship | ship-review-loop.md | Sonnet 5 gate; Opus 5 critical; Greptile/alternative | Open PR with proof. Resolve review. Repeat Build → Prove → Review until 5/5 and zero unresolved comments. | CI green; 5/5; rollback ready | Human merge only | 15–120 min | Higher quality | Review-loop spend | Iteration cap + escalation
5 Observe | RUNBOOK.md | No-agent cron; GLM/Solar only on material change | If NO_CHANGE output [SILENT]. If changed, cite evidence, severity and next check. Never mutate production. | Material alerts only | Human remediates | 1–5 min/run | Near-zero routine cost | Noise/missed issue | Thresholds + weekly audit
File | Required content
AGENTS.md | Master route: Intake → Isolate → Build → Prove → Ship → Observe; permission/privacy/model escalation rules.
skills/new-feature.md | Creates worktree/branch; checks open PRs and changed files; never touches main or another agent’s worktree.
skills/code-structure.md | Flask service-layer conventions, routes/services/repositories, migrations, error handling, logging and test expectations.
skills/evidence-driven-testing.md | Acceptance-criterion test map, deterministic commands, regression suite and evidence manifest.
skills/before-after.md | Screenshot/video/metric naming, storage and PR embedding rules.
skills/ship-review-loop.md | PR template, independent reviewer, 5/5/zero-comment loop, iteration/cost cap, human merge.
RUNBOOK.md | Deploy, health, backup, rollback, credential/fallback and incident rules.

## 04 Cronjobs
Cronjobs: zero-cost by default
Hermes cron runs each tick in a fresh isolated session: every prompt must be self-contained. Prefer --no-agent scripts and call a free/cheap model only after deterministic CHANGE_DETECTED.
Job | Schedule | Deterministic stage | Model stage | Silence/output rule | Permission boundary | Setup time | Priority
LexFlow health | every 15m | No-agent curl/read-only DB smoke | None until repeated failure | Alert after 3 failures | Read only; no restart/deploy | 45–90 min | High
CRM backup verify | 30 2 * * * | No-agent age/size/restore-test check | None | Alert only failure | Never delete/restore production | 30–90 min | High
Credit/provider delta | 10 7 * * * | No-agent fetch snapshot/delta | Step 3.7 FREE on anomaly | [SILENT] if normal | Never purchase/top-up | 30–60 min | High
SEO/GSC delta | 0 8 * * 1-5 | Script exports GSC/crawl and compares snapshot | Solar FREE; GLM 5.3 Flash fallback | Max 3 evidence-linked actions | Read only; no publishing | 1–3 h | High
Weekly SEO/GEO brief | 0 9 * * 1 | Aggregate seven snapshots | Solar FREE; Qwen3 235B fallback | Never invent metrics | Airtable update remains draft | 45–90 min | High
GitHub/CI triage | 0 20 * * * | Collect only new failures/PR changes | Laguna FREE; Qwen Coder 30B fallback | Return URL/test/next command | No push/merge | 45–90 min | Medium
Obsidian hygiene | 30 21 * * * | No-agent duplicates/broken-links/folder-boundary scan | Solar FREE summarizes flags | Write proposals to staging | Never edit personal/permanent notes | 1–2 h | High
Dependency security | 0 3 * * 0 | No-agent pip-audit/npm-audit | Sonnet only for requested remediation | Alert CVSS/affected/fixed version | No automatic upgrade/deploy | 45–120 min | High
Airtable milestone draft | 0 16 * * 5 | Read approved sources and create diff | Solar FREE; GLM fallback | Draft row changes only | Specific approval before write | 45–90 min | High
Action | Copy-paste commands
Gateway | hermes gateway install hermes gateway start hermes cron status
No-agent job | hermes cron create "every 15m" --no-agent --script ~/.hermes/scripts/lexflow-health.sh --deliver telegram --name "lexflow-health"
Script + model only on change | hermes cron create "0 8 * * 1-5" "If NO_CHANGE, output [SILENT]. If CHANGE_DETECTED, cite evidence and return max 3 actions." --script ~/.hermes/scripts/seo-delta.py --deliver local --name "seo-delta"
Test | hermes cron list hermes cron run <job_id> hermes logs
Free route | hermes model # Select exact FREE Nous entry, or OpenCode Free for public/non-confidential data only
Fallback | hermes fallback # Add a separately authenticated provider/model, then test on a non-critical job

## 05 Reliability Cost
Cost, stability and subscription decision
Use direct-key or Nous Portal routes inside Hermes; use Claude subscription natively in Claude Code. Do not assume a consumer subscription funds Hermes/API use.
Dimension | Nous / free stack | Claude | Decision
Parallel volume | Nous/free: many low-cost workers | Claude subscription: shared plan limits | Nous workers + queue cap
Daily interactive coding | More routing/setup | Claude Code is lower friction | Claude Sonnet for your hands-on session
Confidential LexFlow data | Avoid anonymous/rotating free routes | Use approved commercial/API account | Classify data before model selection
OAuth/API failure | Multiple layers may fail | Fewer native layers, still rate/usage limits | Preflight + direct key + fallback chain
Best economics | Free/no-agent and Qwen/GLM promos | Premium quality when it prevents rework | Escalate by risk, not habit
Merge/deploy authority | Never | Never | Human only
Suggested subscription | Nous credits for batch | Claude Pro for daily Claude Code; Max only after measured need | Start hybrid; review after 30 days
Editable API cost scenario
Tasks | 100
Input tokens/task | 50000
Output tokens/task | 10000
Claude review share | 20%
Route | Input $/1M | Output $/1M | 100-task batch $ | Use
FREE | 0 | 0 |  | Low-risk/sanitized only
Qwen Coder 30B | 0.07 | 0.27 |  | Small build/test
Qwen Coder 480B | 0.22 | 1.8 |  | Large build
GLM 5.3 Flash | 0.07 | 0.25 |  | Changed cron summary
Claude Haiku 4.5 | 1 | 5 |  | Approved triage
Claude Sonnet 5 | 2 | 10 |  | Premium coding/review
Claude Opus 5 | 5 | 25 |  | Critical escalation
Control | Implementation
Preflight | Before every batch: provider auth, model existence, quota, one tiny completion, required tools.
Fallback | Hermes config.yaml fallback_providers: separate provider and credential; auth 401/403 fails over immediately.
Checkpoint | Every task writes state, commands, artifacts and next action to its worktree; never depend on chat memory.
Retry | Max 2 transient retries with exponential delay; zero blind retries on auth errors.
Budget | Per-task token/time/iteration ceiling; stop and escalate instead of looping.
Recovery | Keep worktree; switch provider/model; resume from FEATURE.md and evidence manifest.

## 06 30-Day Rollout
30-day implementation plan
Completion target: core factory in 7 days, validated routing and cron reliability in 30 days. Start reversible and scale only from measured evidence.
When | Action | Deliverable | Time | Model/cost lane | Main risk | Mitigation
Day 1 | Inventory repos, active branches, tests, deployments, secrets and cronjobs | Repository map + redacted risk list | 2–3 h | None | Unknown dependencies | No code change
Day 2 | Create six factory markdown files and PR template | Committed operating manual | 3–5 h | Solar FREE/Qwen3 235B | Bad generic SOP | Customize to Flask/SQLite/LexFlow
Day 3 | Protect main; build worktree helper; run dry test | Repeatable isolate command | 2–4 h | No LLM | Branch mistakes | Dry-run on disposable branch
Day 4 | Choose one tiny CRM bug; build with Qwen Coder 30B | First isolated PR | 2–5 h | Qwen 30B | Poor implementation | Synthetic data + tests
Day 5 | Add before/after evidence and independent review | Evidence-complete PR | 2–4 h | Sonnet 5 review | Reviewer spend | One iteration cap
Day 6 | Deploy health, backup and credit no-agent jobs | 3 durable cronjobs | 3–5 h | No LLM | False alerts | Manual trigger and log inspection
Day 7 | Run two parallel low-risk features | 2 worktrees, 2 PRs | 0.5–1 day | Qwen 30B/480B | Conflicts/overload | Concurrency = 2
Week 2 | Add SEO delta, Obsidian hygiene, CI triage | Free-first cron layer | 1–2 days | Solar/Laguna/Step FREE | Privacy/noise | Data boundaries + thresholds
Week 3 | Handle one medium CRM feature and one deploy | End-to-end factory proof | 2–4 days | Qwen 480B + Sonnet gate | Escaped defect | Staging and rollback
Week 4 | Review 10–20 tasks; tune routing/concurrency | Routing v1 + KPI baseline | 2–3 h | No LLM for metrics | Premature scaling | Scale to 4 only if gates pass
KPI | Definition | 30-day gate | Cadence
Cycle time | Brief approved → evidence-complete PR | Baseline then reduce 20% | Weekly
First-pass proof rate | PRs passing acceptance criteria without rebuild | ≥70% by day 30 | Weekly
Review escape rate | Merged PRs causing rollback/hotfix | 0 critical | Monthly
Free/no-agent share | Eligible routine runs using no paid LLM | ≥70% | Weekly
Provider failure recovery | Blocked jobs resumed via fallback/checkpoint | 100% tested | Monthly drill
AI cost/task | Total model cost / completed accepted tasks | Track median and P90 | Weekly
Human approval compliance | Restricted actions with explicit approval record | 100% | Weekly audit