## This Week
Day | Task | Owner | Time (est.) | Status | Notes
Wed Aug 26 | Send merged prompt to Hermes (memory-curator + Hindsight audit) | Ole | 5 min | Pending
Wed Aug 26 | Hermes: report status on already-implemented items (no redo) | Hermes | auto | Pending
Thu Aug 27 | Review memory-curator dry-run report | Ole | 10 min | Pending
Thu Aug 27 | Review Hindsight Phase 1 audit report | Ole | 10 min | Pending
Fri Aug 28 | Approve/reject memory-curator first live pass | Ole | 5 min | Pending
Fri Aug 28 | Approve/reject Hindsight Phase 2 fixes | Ole | 5 min | Pending
Sat Aug 29 | Check Telegram reports — confirm no missed runs | Ole | 5 min | Pending
Sun Aug 30 | Weekly review: KPI dashboard + profile count audit | Ole | 20 min | Pending
Sun Aug 30 | Memory-curator self-improvement report due (weekly) | Hermes | auto | Pending

## Recurring Checklist
Frequency | Check | Owner | Channel/Method
Daily | Telegram run report received (even null-activity) | Hermes → Ole | Telegram
Daily | Any infra-change proposals awaiting approval? | Ole | Telegram
Weekly | Review conflict backlog (_Inbox/_Conflicts) — clear or resolve | Ole | Obsidian
Weekly | Credit spend review vs. budget | Ole | Dashboard/report
Weekly | Memory-curator self-improvement report review | Ole | Telegram
Weekly | KPI dashboard update (this sheet, tab 3) | Ole | Excel
Bi-weekly | Active Hermes profile count audit (target ~5-6) | Ole | hermes profile list
Monthly | Full Hindsight E2E stability check (3x pass over 30 min) | Hermes | curl test + report
Monthly | Review/update AGENT_RULES.md and vault boundary tiers | Ole | Obsidian _Meta
Quarterly | Full credential/secrets audit across all repos + Railway | Ole + backend-dev | Manual

## KPI Dashboard
KPI | Target | This Week Actual | Status (auto/manual) | Trend Notes
Downloads folder size | <500MB after each run |  | Manual check
Duplicate auto-delete accuracy | 100% hash-verified, 0 false deletes |  | Hermes report
Conflict backlog age | Reviewed within 48h |  | Manual check
Hindsight E2E test | 3x consecutive pass / 30 min |  | Hermes report
Telegram report delivery rate | 100% of scheduled runs |  | Manual check
Weekly credit spend | Within set budget (define €/week) |  | Hermes report
Active Hermes profiles | ~5-6 (down from 23-24) |  | Manual check
Manual triage time (Ole) | Trending toward 0 min/week |  | Manual estimate
Escalations requiring Ole's input | Decreasing week over week |  | Hermes report
Memory-curator self-improvement items shipped | ≥1 meaningful refinement/week |  | Hermes report

## Self-Improvement Log
Week Of | Agent | Observation/Pattern Found | Rule/Workflow Change Proposed | Ole Approval | Status