## Overview
LexFlow CRM — Multi-Tenant Rollout Tracker
Generated: 2026-09-03 ¦ Owner: Olesia Rasing
Sheet Index
Roster | People, testing customers, AI agents — status & workspace mapping
Delegation_Tracking | Global rule set + delegated tasks (backend-dev, QA, memory-curator)
Contact_Model | Internal vs client-facing contact model, fields, best-practice source
Decisions_Log | Open/closed decisions (seat limits, matters cap, Elisa go-live)
Elisa_Rollout_Plan | Sandbox-to-production staged plan for Elisa (LexFlow PA agent)
Key Open Decisions (see Decisions_Log for full detail)
• Matters (cases) per tenant: UNLIMITED for now — tracking mechanism TBD (see Decisions_Log).
• Memory/storage per tenant: UNLIMITED for now — same tracking mechanism TBD.
• Seat limit per tenant: SMALL limit approved as starting point — exact number pending research.
• Elisa (LexFlow PA agent): built, isolated sandbox, NO production data access until explicit approval.
• Internal vs client-facing contacts: approved as TWO separate models — implementation plan pending backend-dev proposal.

## Project_Roadmap
Project Roadmap — Step Flow
For Olesia and delegated agents (Hermes, backend-dev, Elisa)

## Roster
Roster — People, Testing Customers, AI Agents
Status, workspace mapping, access scope
Name | Category | Role | Status | Workspace ID | Access / Notes
Olesia (you) | Owner | Superadmin | Active | ws7 (LexFlow) | Full access all tenants
Romanelli Studio | Testing customer | Law firm tenant | Active, live | ws10 + cl1, cl2 (client-of-client external clients) | Need to ADD internal users (lawyers/assistant/office) — separate internal contact model required, see Contact_Model sheet
Pagliano | Testing customer | Law firm tenant | Active, live | ws9 | —
Tommaso Ferro | Testing customer | Law firm tenant | Listed, workspace exists (like AVIBE Agency & aLEXy) | Workspace ID exists — website not linked yet, not tested yet | ASK HERMES: confirm exact workspace ID + link status in inventory table
AVIBE Agency | Testing customer | Tenant | Workspace exists, not tested | TBD — ask Hermes to confirm | Website not linked yet
aLEXy | Testing customer / own product | Tenant | Workspace exists, not tested | TBD — ask Hermes to confirm | Website not linked yet
Dima | Collaborator | Backend developer | Partially wired | LexFlow (ws7) — role scope pending | Needs separate access inside LexFlow; audits + fixes; add to Delegation_Tracking
Kirill | Collaborator | Design & content creation | Not yet wired | LexFlow (ws7) — Kanban only | Should see action titles only (not internal notes) in shared LexFlow Kanban
Stefano | Collaborator | AI agent integration | Active — building Elisa | Isolated sandbox (no tenant data) | Building Elisa (LexFlow PA); see Elisa_Rollout_Plan sheet
Elisa | AI Agent | Personal LexFlow-legal-CRM assistant (LexFlow PA) | Built, sandboxed | Fully isolated sandbox — NO real tenant data access | See Elisa_Rollout_Plan for staged go-live logic
backend-dev (AI agent) | AI Agent | Backend audits, cron tasks | Already running | Cross-tenant (read/audit scope) | Already executing scheduled/cron + audit tasks per Delegation_Tracking
Operator-Installer (Hermes) | AI Agent | Central orchestrator | Already running | Cross-tenant (full deploy scope) | Executes all deploys/fixes; gated by explicit approval per rules
QA/Test-Debug Agent (proposed) | AI Agent | Test generation + evidence-based debugging | Not yet installed — proposed | N/A | See Delegation_Tracking for skill links (QASkills.sh + debug skill)
Memory-Curator Agent (proposed) | AI Agent | Curates/archives Obsidian vault + skill profiles | Not yet installed — proposed | N/A | To be delegated by Operator-Installer; see Delegation_Tracking

## Delegation_Tracking
Delegation Tracking
Global rules apply to ALL future deploys, not just-this-once
GLOBAL RULE (confirmed permanent)
Any 'fixed'/'done' report must state explicitly: (a) LOCAL — not deployed, with a direct clickable preview link, OR (b) DEPLOYED — with live/staging URL + commit hash. Never state 'fixed' without one of these two. This rule is GLOBAL, applies to every future deploy, not a one-time exception.
Task / Fix | Assigned To | Status | Local Link / Deploy URL | Tested On (workspaces) | Notes
Backend-dev report review | backend-dev | Pending | N/A | N/A | Wait for clean report FIRST. If clean → request local link. If bugs found → audit weak spots first, only then commit+deploy.
Intake name field manual entry | Operator-Installer | Pending | — | ws7, ws9, ws10+cl1+cl2 | Must allow manual override of autofill
New contact from intake → appears in Contacts | Operator-Installer | Pending | — | ws7, ws9, ws10+cl1+cl2 | Cross-section reflection requirement
Cross-section data reflection (Contacts/Calendar/Kanban/Cases) | Operator-Installer | Pending | — | All active tenants | Test each section individually, report per-tenant not generic PASS
RLS merge (feat/rls) | backend-dev | On hold | — | N/A | REMINDER before merge: run 18 tests on real Postgres + confirm NOBYPASSRLS on Railway DATABASE_URL role. Do not merge until both confirmed.
Seat limit research + proposal | Operator-Installer | Pending | N/A | N/A | Research small-firm norms (e.g. 3-5 seats), propose number, get sign-off before implementing
Internal vs client-facing contact model design | backend-dev | Pending — approval required before code | N/A | Romanelli first | Approve table structure, then request implementation plan before Operator-Installer codes it
Contacts redesign (HubSpot/Salesforce/Clio-style table) | Operator-Installer + Kirill | Pending | N/A | Romanelli first, then replicate | Table view, status field, bulk-action ready (marketing/email). Isolated frontend feature, can start in parallel.
Agentic AI-personalized email automation | Operator-Installer | NOT YET IN PLAN — new item | N/A | N/A | Missing from current backlog. Needs own spec: trigger logic + template engine + Resend integration + per-contact personalization.
QA / Test-Debug Agent | Operator-Installer | Proposed, not installed | https://qaskills.sh | N/A | QASkills.sh — install via npx @qaskills/cli add <skill>. Complementary: standalone 'debug' skill (hypothesize-then-test workflow) by Ronnie Schaniel — enforces reproduction test before fix.
Memory-Curator Agent | Operator-Installer | Proposed, not installed | TBD | N/A | Delegate to a memory-curator agent to save tester/debugger profile + skills into Obsidian vault + working folders.
Elisa sandbox → production staging | Stefano + Operator-Installer | In sandbox, isolated | N/A — isolated dev env | None yet — no real tenant data access | See Elisa_Rollout_Plan sheet for staged criteria
Congestion tracking (matters + memory, unlimited for now) | Operator-Installer | Pending — mechanism needed | N/A | N/A | Matters/case count + memory/storage per tenant: unlimited for now. Hermes must propose HOW to monitor usage (dashboard/alerts) and AT WHAT THRESHOLD limits get set.

## Contact_Model
Contact Model — Internal vs Client-Facing
Best-practice field sets, approved as TWO separate models
Logic Summary
Romanelli admin/paralegal needs visibility into BOTH: (1) their own internal staff directory (lawyers, assistants, office phone) — NOT client-facing, and (2) client-facing contacts including the client-of-client's own contacts. These are separate data models filtered by workspace_id, not one shared table.
Model A — Internal Contacts (Staff Directory)
Field | Type | Required | Notes
Full Name | Text | Yes | —
Role/Title | Text | Yes | Lawyer, Paralegal, Assistant, Office Manager
Office Phone | Text | No | Shared/desk line
Direct Phone | Text | No | Personal/mobile
Email (internal) | Text | Yes | Firm domain email
Workspace ID | FK | Yes | Filters visibility to Romanelli ws10 only
Employment Status | Dropdown | Yes | Active / On leave / Departed
Bar/License Number | Text | No | For lawyers only, legal compliance field
Visible To | Multi-select | Yes | Admin, Paralegal roles (not client-facing users)
Model B — Client-Facing Contacts (Marketing-Ready)
Field | Type | Required | Notes
Full Name / Company Name | Text | Yes | Person or entity
Contact Type | Dropdown | Yes | Individual / Client-of-client / Organization
Email | Text | Yes | Primary marketing/comm channel
Phone | Text | No | —
Case/Matter Link | FK | No | Links to active case(s)
Lifecycle Stage | Dropdown | Yes | Lead / Active / Passive / Closed (per earlier decision)
Marketing Consent | Boolean | Yes | GDPR — required for EU clients (Italy)
Tags/Segments | Multi-select | No | For bulk email targeting/segmentation
Last Contacted | Date | No | Auto-updated, used for campaign timing
Workspace ID | FK | Yes | Filters visibility per tenant (ws9, ws10, cl1, cl2, etc.)
Source | Dropdown | No | Intake / Referral / Website / Manual entry
Implementation Notes
• Likely needs a JSON schema file per tenant to define which fields are active/required (small firms may not need Bar Number, etc.).
• Consider a lightweight web plugin/JSON config so agents (Elisa, backend-dev) can navigate the CRM contact structure quickly without hardcoding field names.
• GDPR note: Marketing Consent field is mandatory for Italy-based clients (Romanelli, Pagliano) — do not enable bulk email without it.
• APPROVAL GATE: This table structure is approved as-is. Before Operator-Installer writes any code, backend-dev must submit an implementation plan (migration steps, affected files, rollback path) for sign-off.

## Decisions_Log
Decisions Log
Open and closed decisions, with rationale
Decision Item | Status | Decision / Answer | Rationale / Next Step
Matters (cases) cap per tenant | CLOSED — for now | Unlimited | No cap for now. Hermes must define HOW usage is tracked (dashboard/query) and AT WHAT threshold a limit gets set. Revisit at scale.
Memory/storage cap per tenant | CLOSED — for now | Unlimited | Same as above — tracked together, revisit when congestion signals appear.
Seat limit per tenant | CLOSED — direction only | Small limit (exact number TBD) | Start with a small limit per small-firm best practice. Operator-Installer to research and propose exact number (e.g. 3-5) for sign-off.
Internal vs client-facing contact models | CLOSED — approved as-is | Two separate models | See Contact_Model sheet. Implementation plan required from backend-dev before coding.
Elisa production access | OPEN | Read-only access during development; full production TBD | See Elisa_Rollout_Plan sheet for staged criteria and test plan.
Global 'local vs deployed' reporting rule | CLOSED | Confirmed global, not just-this-once | Applies to every future deploy/fix report, permanently.
RLS merge timing | OPEN — reminder only | Do not merge until 18 tests pass on real Postgres + NOBYPASSRLS confirmed | No new deadline set; reminder persists in Delegation_Tracking.
Ferro / AVIBE / aLEXy workspace confirmation | OPEN | Workspace IDs reportedly exist, unconfirmed | Ask Hermes to confirm in inventory table — websites not linked, not tested yet.
QA/Test-Debug agent adoption | OPEN | Identified candidate: QASkills.sh + debug skill | Add to roster/Delegation_Tracking; not yet installed/activated.
Memory-Curator agent for Obsidian vault | OPEN | To be delegated by Operator-Installer | Save tester-debugger profile/skills to working folders + Obsidian vault via memory-curator agent.
Agentic AI-personalized email automation | OPEN — new item | Not yet scoped | Add as new backlog item, separate from Contacts redesign.

## Elisa_Rollout_Plan
Elisa (LexFlow PA) — Sandbox to Production Plan
Built by Stefano's dev pipeline, currently fully isolated
Current State
Elisa exists, generated and trained by Stefano's dev process. Lives in a fully isolated sandbox environment with NO access to real tenant data. This is the correct posture for an untested AI agent that will eventually read/write case data.
Recommended Staged Access Plan
Stage | Data Access | Approval Gate | Test Method
Stage 0 (current) | None — fully isolated sandbox, synthetic/dummy data only | N/A — already in place | Unit tests on synthetic case/contact data; verify no external API calls reach real DB
Stage 1 | Read-only access to ONE non-critical test tenant (e.g. Pagliano or a dedicated Elisa-test workspace) | Explicit approval from Olesia required before enabling | Shadow mode: Elisa processes real read queries but her outputs are logged only, never shown to real users or written back
Stage 2 | Read-only across all test tenants (Romanelli, Pagliano, Ferro) | Explicit approval, only after Stage 1 shows zero data leakage/errors for a defined period | Parallel-run: compare Elisa's suggested actions against what a human would do manually; no autonomous writes
Stage 3 | Write access, but ONLY within her own scoped actions (e.g. drafting reminders, not modifying case status) | Explicit approval + human-in-the-loop confirmation required per write action initially | Supervised writes: every write requires a one-click human confirm before committing
Stage 4 (production) | Full production access per her defined role | Explicit final approval after Stage 3 track record reviewed | Ongoing monitoring + audit log review; rollback plan defined before go-live
Reasoning: Why Not Jump Straight to Read-Only Real Data
• Read-only access during early development IS acceptable in principle, but only inside a scoped, monitored test tenant — not general production data — because even read-only agents can leak data through logs, model outputs, or third-party API calls (e.g. if Elisa uses an external LLM API, real client data could leave your infrastructure).
• Recommendation: create ONE dedicated 'Elisa-test' workspace with realistic but synthetic data first (Stage 0-1 boundary) before touching any real Romanelli/Pagliano/Ferro data — this fully de-risks the earliest testing phase.
• Only grant real tenant read access (Stage 1) once Elisa's data-handling (logging, retention, external API calls) has been audited by backend-dev — same audit discipline already applied to RLS/webhooks.
• Explicit production approval (Stage 4) should require: zero data incidents in Stage 1-3, a defined rollback/kill-switch, and sign-off from Olesia specifically — not automatic progression.