## Session Summary
Session Summary — LexFlow CRM/Flask/Railway (2026-07-31)
Section | Detail
Topic | CORS & Domain critical issue on LexFlow CRM (Flask, Railway) + LP deployment check
Project | LexFlow MVP (CRM/Task management) — repo Ole00007/LexFlow-MVP
Date | 2026-07-31
Core Issue | Landing page (frontend origin) submits intake data via browser fetch to Flask CRM API hosted on Railway (web-production-ab54f.up.railway.app). Browser blocks cross-origin request unless Flask returns correct CORS headers (Access-Control-Allow-Origin) for that exact origin.
What CORS means (general) | Browser security mechanism blocking JS from calling a different origin (scheme+host+port) than the page's own, unless the target server explicitly allows it via response headers.
What 'Domain' means here | The exact origin the browser compares: the landing page's domain vs the Railway-hosted Flask API's domain. Mismatch = blocked request.
Where fix must live | Server-side in Flask app code (e.g. flask-cors package or manual after_request headers), committed to GitHub repo main branch — NOT in Railway dashboard settings, NOT in frontend code.
Deployment pipeline | GitHub repo Ole00007/LexFlow-MVP, branch 'main', auto-deploy enabled on Railway. Push to main triggers automatic redeploy.
Deployment status checked | Latest deployment ACTIVE / successful ~10h ago: "fix: intake accepts practice_area/message alias..." via GitHub. LP live and rendering correctly at web-production-ab54f.up.railway.app.
Hermes reasoning assessment | Could not be verified directly — Hermes chat session (Avv Pagliani Landing Page Flask Integration #19, 555 msgs) failed to load (session.resume timeout, Gateway status Off). Assessment given is generic best-practice guidance, not a review of Hermes's actual proposed code/diff.
Recommended approach | Whitelist exact landing-page origin (not wildcard *), enable credentials only if cookies/auth used, explicitly handle OPTIONS preflight requests, verify header present on error responses too.
Alternatives considered | 1) Reverse-proxy API calls through same domain as LP (no CORS needed). 2) Route submissions through serverless/backend-for-frontend instead of hitting CRM API directly from browser. 3) Narrow CORS whitelist (simplest, chosen default).
Key risks flagged | Wildcard origin + credentials = security exposure of CRM lead data. Fix committed to wrong branch/file won't reach Railway's auto-deploy. Forgetting explicit OPTIONS handling is a common miss.
Open questions for Hermes | 1) Which exact file/route patched, flask-cors or manual headers? 2) Is allowed origin exact match (incl. www variant)? 3) Are OPTIONS preflight requests explicitly handled? 4) Is patched branch the one wired to Railway auto-deploy? 5) Does submission need credentials/cookies? 6) Was fix verified via real browser request post-deploy?
Action items | 1) Retrieve/paste actual Flask CORS diff from Hermes session for precise review. 2) Confirm allowed origin list matches exact LP domain. 3) Test live form submission end-to-end after deploy. 4) Re-check Hermes Gateway connectivity (was Off) to restore session history access.

## Deployment & Infra Status
Field | Value
Service Name | web (Railway)
Live URL | web-production-ab54f.up.railway.app
Project | compassionate-trust / production environment
GitHub Repo | Ole00007/LexFlow-MVP
Connected Branch | main
Auto-Deploy on Push | Enabled
Wait for CI | Not confirmed — check Railway Settings > Source
Latest Deployment Commit | fix: intake accepts practice_area/message alias...
Latest Deployment Trigger | via GitHub push
Latest Deployment Status | ACTIVE / Deployment successful
Latest Deployment Age (at check time) | ~10 hours ago
Previous Deployment 1 | fix: LP form fetches production intake endpoint (status: REMOVED/superseded)
Previous Deployment 2 | fix: intake accepts /api/intake and /api/intake/ (status: REMOVED/superseded)
LP Visual Check | Confirmed rendering correctly: 'LexFlow — Legal Intake & Status Suite' homepage live with Start secure intake / Staff workspace CTAs
Deployment Region | US West
Runtime | python@3.13.14
Replicas | 1
Manual Deploy Needed? | No — pipeline is auto-deploy; only needed if new local commits are pending push
How to trigger new deploy (manual, user-side) | 1) git add . && git commit -m "message" 2) git push origin main 3) Railway auto-builds and redeploys
How to force redeploy w/o code change | In Railway UI: Deployments tab > latest deployment > (...) menu > Redeploy

## Open Questions & Action Items
# | Owner | Question / Action | Status | Notes
1 | Hermes / User | Which exact Flask file/route was patched for CORS — flask-cors package or manual headers? | Open | Needed to verify correctness of implementation
2 | Hermes / User | Is allowed origin an exact match to LP domain (incl. www variant)? | Open | Avoid wildcard * for security
3 | Hermes / User | Are OPTIONS preflight requests explicitly handled in Flask? | Open | Common miss causing silent failures
4 | User | Is the patched branch the one wired to Railway auto-deploy (main)? | Confirmed | Verified: branch = main, auto-deploy = Enabled
5 | User | Does the CRM submission require credentials/cookies? | Open | Determines if Access-Control-Allow-Credentials is relevant
6 | User | Was the fix verified via a real browser request from the live LP post-deploy? | Open | Curl/Postman tests don't reflect real browser CORS enforcement
7 | User | Retrieve/paste actual Flask CORS diff from Hermes session for precise review | Open | Hermes session failed to load (session.resume timeout, Gateway Off)
8 | User | Restore Hermes Gateway connectivity to access full session history | Open | Gateway status showed 'Off' during this session
9 | User | Confirm latest LP deployment is stable in production | Done | Verified live at web-production-ab54f.up.railway.app, deployment ACTIVE
10 | User | Decide on CORS approach: narrow whitelist vs reverse-proxy vs backend-for-frontend | Open | Narrow whitelist recommended as default; proxy/BFF as alternative for stronger isolation

## CORS Glossary & Reference
Term | Definition
CORS (Cross-Origin Resource Sharing) | Browser security mechanism that blocks a webpage's JS from making requests to a different origin than the one that served the page, unless the target server explicitly allows it via response headers.
Origin | Combination of scheme (http/https) + host (domain) + port. Two URLs are 'same-origin' only if all three match exactly.
Access-Control-Allow-Origin | Response header the server sends to tell the browser which origin(s) are permitted to read the response.
Preflight / OPTIONS request | Automatic browser-sent request before certain cross-origin requests (e.g. POST with JSON), asking the server for permission before sending the real request.
Access-Control-Allow-Credentials | Header required if the cross-origin request needs to send cookies or auth headers; cannot be combined with wildcard (*) origin.
Wildcard origin (*) | Allows any origin to access the resource; convenient but risky for endpoints handling sensitive/lead data.
Why this matters for LexFlow | Landing page (frontend) and Flask CRM API (Railway backend) are different origins. Without correct CORS headers on the Flask side, browser blocks the intake form submission — lead data never reaches the CRM, even though server-to-server tools (curl/Postman) work fine.
Where the fix belongs | Server-side only: Flask app code (flask-cors package or manual after_request headers), committed to the GitHub repo and deployed via Railway's auto-deploy on push to main.