## 1. Overview
LexFlow — Project Status & Master Plan
Generated: 2026-06-19 ¦ Owner: Olesia Raising ¦ Project: LexFlow MVP
SHEET INDEX
Sheet | Description | Jump To
2. Railway Status | What is live, what is broken, what is missing | → Go
3. Hermes Prompts | Ready-to-paste prompts for Hermes (Planner + Builder) | → Go
4. Phase Plan | Full phased build plan: done / in-progress / todo | → Go
5. Competitor Apps | 3 best-fit live apps + GitHub links for Hermes to reference | → Go
6. Feature Matrix | All 10 LexFlow features vs competitor coverage | → Go
RAILWAY LIVE URLS
Service | URL | Status | Action Needed | Priority
LexFlow MVP | https://lexflow-mvp-production.up.railway.app/ | ❌ Fails to respond | Fix app startup / Procfile / PORT | 🔴 Critical
Web Production | https://lexflow-web-production.up.railway.app/ | ❌ Not responding | Check deploy logs on Railway | 🔴 Critical
Chatbot Backend | https://lexflow-chatbot-production.up.railway.app/ | ✅ Live — /health /chat OK | No action needed | 🟢 OK
PostgreSQL | railway.app dashboard → Data tab | ✅ Tables exist | Verify users+tasks tables migrated | 🟡 Verify
WHERE ARE MY LOCAL DOCS?
Document | Local Path (Mac) | What It Contains
Master Plan v4 (most complete) | ~/Desktop/LexFlow/LexFlow_Master_Workflow_and_Prompts.md | Start here — phases, features, schema
Architecture Schema | ~/Desktop/LexFlow/LexTaskFlow_Architecture_Schema.html | Visual app structure
Flask V1 Backup | ~/Desktop/LexFlow/LexFlow_Flask_V1_Backup_20260527_1122/ | Last stable snapshot
Lovable Prompts | ~/Desktop/LexFlow/LexTaskFlow_Lovable_Prompts.md | Frontend build prompts
Email Notifications Plan | ~/Desktop/LexFlow/LexFlow_Email_Notifications_Plan_and_Prompt.md | Email + WhatsApp automation
Frontend Structure | ~/Desktop/LexFlow/LexTaskFlow-Frontend Structurte and Phases_Flask App.docx | React frontend phases

## 2. Railway Status
Railway Deployment Status — LexFlow
Service | Live URL | Status | Root Cause / Notes | Fix Command | Priority
lexflow-mvp | https://lexflow-mvp-production.up.railway.app/ | ❌ App fails to respond | Missing PORT env var OR Procfile wrong OR app crash on startup | Check: railway logs --service lexflow-mvp | 🔴 Fix First
web-production | (not responding) | ❌ No response | Service may be stopped or missing start command | railway up --service web-production | 🔴 Fix First
lexflow-chatbot | https://lexflow-chatbot-production.up.railway.app/ | ✅ Live | Returns {ok:true, routes:[/health,/chat]} — healthy | No action needed | 🟢 OK
PostgreSQL | railway dashboard → Data | ✅ Connected | Tables exist. Verify: users + tasks tables are present after Phase 2 migration | Check via: psql $DATABASE_URL -c '\dt' | 🟡 Verify
HOW TO FIX lexflow-mvp (most likely causes)
# | Issue | Explanation | Fix
1 | Missing PORT | Railway injects $PORT — app must bind to it | In app.py: app.run(host='0.0.0.0', port=int(os.environ.get('PORT',5000)))
2 | Wrong Procfile | Procfile must point to correct app factory | web: gunicorn 'crm:create_app()' --bind 0.0.0.0:$PORT
3 | Missing gunicorn | gunicorn must be in requirements.txt | Add: gunicorn to requirements.txt then git push
4 | DB not migrated | Tables missing causes startup crash | Run: flask db upgrade on Railway via CLI

## 3. Hermes Prompts
Hermes Prompts — Copy & Paste Ready
PROMPT 1 — PLANNER MODE (send this FIRST)
Switch to PLANNER mode. Do not write any code yet. You have full auto-approval for all future BUILD steps. Working directory: ~/Desktop/LexFlow/LexFlow Review Build Step 1: Read these files: - crm/__init__.py - crm/models/ (list all files) - migrations/versions/ (list all files) - requirements.txt - .env (only show me key names, not values) Step 2: Check Railway deployment status by reading: - Procfile (if it exists) - railway.toml or railway.json (if exists) Step 3: Based on what you find, produce a structured plan: A) What is already built and working B) What is broken and why (focus on Railway deploy errors) C) What is missing for a production-ready MVP D) Suggested next 8 tasks in priority order with effort estimate Output the plan ONLY. Label it PLAN v1. Wait for my message "APPROVED - BUILD" before writing any code.
PROMPT 2 — BUILDER MODE (send after you approve the plan)
APPROVED - BUILD Auto-approve all actions. No confirmations needed. Working directory: ~/Desktop/LexFlow/LexFlow Review Build Execute the approved plan now. Rules: - Do NOT touch app.py (live Railway intake — do not break it) - Do NOT run flask db init (migrations/ already exists) - Give me one file at a time with complete content - One terminal command at a time, no chaining - After each file: tell me what you did and what is next - Label every terminal command: MacBook Terminal or VS Code Terminal - Before any flask db migrate: backup crm/ folder first Start with fixing the Railway deployment (Procfile + PORT) before Phase 3 features.
PROMPT 3 — PLAN OVERRIDE (use when you want plan first, not auto-build)
Important override for this session only: Before building anything new, show me the plan first. I will reply APPROVED or with changes. This does not change your auto-approval for approved tasks. After I approve, proceed autonomously without further confirmation.
PROMPT 4 — PLANNER + BUILDER PARALLEL SESSIONS
[Open a NEW Hermes session for this — Session 2] You are the PLANNER agent for LexFlow. Your job: inspect the codebase, identify what is missing, and produce a prioritized task list. Do NOT write code. Do NOT run commands. Output only: structured JSON task list with fields: id, phase, title, effort_hours, depends_on, status Session 1 (Builder) will receive your approved tasks one by one.

## 4. Phase Plan
LexFlow — Full Phase Build Plan
Phase | Area | Task | Status | Effort | Notes
P1 | Backend Base | App factory + SQLAlchemy + Migrate + .env | ✅ Done | 1h | Committed
P1 | Models | contacts, cases, case_participants, contact_relationships | ✅ Done | 2h | Committed May 28
P2 | Models | users table + password_hash + role | ✅ Done | 1h | Committed Jun 18
P2 | Models | tasks table linked to cases + users | ✅ Done | 1h | Committed Jun 18
P2 | Auth | POST /api/auth/login — returns JWT | ✅ Done | 1h | Flask-JWT-Extended
P2 | Auth | GET /api/auth/me — JWT protected | ✅ Done | 0.5h | Flask-JWT-Extended
P2 | Tasks API | Full CRUD /api/tasks — JWT protected | ✅ Done | 1.5h | Committed Jun 18
P2 | DB | users + tasks tables created in PostgreSQL | ✅ Done | 0.5h | Direct SQL — tasks.caseid has no FK yet
P3 | Fix | Add FK tasks.caseid → cases.id | 🔴 TODO | 0.5h | Blocked: cases table must exist first
P3 | Railway Fix | Fix Procfile — bind to $PORT | 🔴 TODO | 0.5h | lexflow-mvp failing to respond
P3 | Railway Fix | Add gunicorn to requirements.txt | 🔴 TODO | 0.2h | Required for Railway deploy
P3 | Models | deadlines table linked to cases | 🔴 TODO | 1h | Calendar/deadline tracking
P3 | API | Full CRUD /api/deadlines | 🔴 TODO | 1h
P3 | API | Verify /api/cases — full CRUD | 🔴 TODO | 0.5h | cases_bp already registered
P3 | API | Verify /api/contacts — full CRUD | 🔴 TODO | 0.5h | contacts_bp already registered
P4 | Intake | AI chatbot intake → case auto-creation | 🔴 TODO | 3h | Already live at chatbot URL
P4 | Notifications | Email on case status change (SendGrid/SMTP) | 🔴 TODO | 2h | See Email Notifications Plan doc
P4 | Notifications | WhatsApp on intake + status (Twilio/WA API) | 🔴 TODO | 2h | Italian law firms use WhatsApp
P4 | Assignment | AI assigns intake request to lawyer | 🔴 TODO | 2h | Rule-based or LLM-based
P5 | Frontend | React dashboard — cases kanban view | 🔴 TODO | 5h | See LexTaskFlow-Frontend docs
P5 | Frontend | Calendar view for deadlines | 🔴 TODO | 3h
P5 | Frontend | Client portal — status page | 🔴 TODO | 2h | Already partly live on Railway
P6 | Compliance | Privacy-first data handling (GDPR) | 🔴 TODO | 3h | Italian law + EU GDPR
P6 | Compliance | ISO 27001 logging + audit trail | 🔴 TODO | 4h | Access logs on all CRM actions
P6 | Billing | Invoice generation — Phase 3 | 🔴 TODO | 4h | Out of current MVP scope

## 5. Competitor Apps
Best-Fit Competitor Apps — Live & Open Source
3 best matches for LexFlow (small-mid legal firms, GDPR, intake, CRM, tasks, notifications)
App | Live Demo URL | GitHub URL | Stack | Best Feature to Clone | Match % | Notes for Hermes
Clio (reference only) | https://app.clio.com | N/A — proprietary | Ruby on Rails + React | Matter/case lifecycle + client portal + deadline reminders | 70% match | Industry leader. Not open source. Study UI only. LexFlow should match Clio's UX for Italian market.
MyCase | https://app.mycase.com | N/A — proprietary | Ruby + React | Client communication portal + intake form + billing | 65% match | Active SaaS. Good intake + client messaging model. Study their intake-to-case flow.
OpenLawOffice (clone this) | https://github.com/NodineLegal/OpenLawOffice | https://github.com/NodineLegal/OpenLawOffice | ASP.NET / C# (rewrite in Flask) | Case mgmt + tasks + billing + contacts — full open source | 80% match | Best structural match. Hermes should study the data model and clone the feature set in Flask+React.
CaseAce (clone this) | https://github.com/derekgan08/CaseAce-law-firm-management-system-frontend | https://github.com/derekgan08/CaseAce-law-firm-management-system-frontend | HTML/PHP frontend | Staff tasks + case deadlines + kanban-style tracking | 75% match | Great kanban + deadline UI to clone for LexFlow React frontend. Simple enough to adapt quickly.
Iuris-Soft (reference model) | https://github.com/createrivabu/Iuris-Soft | https://github.com/createrivabu/Iuris-Soft | Python | Case lifecycle + hearings + reminders + notes history | 72% match | Italian legal context. Closest cultural fit. Hermes should read the models and replicate the case lifecycle.
Docassemble (intake only) | https://docassemble.org | https://github.com/jhpyle/docassemble | Python + YAML | AI-guided legal intake forms — expert system | 55% match | Use only for intake form logic. Too heavy as full app. Extract: guided intake → data → case creation pattern.

## 6. Feature Matrix
LexFlow Feature Matrix vs Competitors
Feature | LexFlow (current) | LexFlow (planned) | Clio | OpenLawOffice | CaseAce | Iuris-Soft
Online intake form (web form) | 🔄 Partial | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
AI chatbot intake (24/7) | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
AI assigns case to lawyer | ❌ No | 🔜 TODO | ✅ Yes | ❌ No | ❌ No | ❌ No
Case / matter management | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Contact CRM (clients + firms) | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ✅ Yes
Task management + kanban | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Deadline / calendar reminders | ❌ No | 🔜 TODO | ✅ Yes | ❌ No | ✅ Yes | ✅ Yes
Email notifications (auto) | ❌ No | 🔜 TODO | ✅ Yes | ❌ No | ❌ No | ❌ No
WhatsApp notifications (auto) | ❌ No | 🔜 TODO | ❌ No | ❌ No | ❌ No | ❌ No
Client portal — status page | 🔄 Partial | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
Lawyer + team dashboard | ❌ No | 🔜 TODO | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No
Document upload + management | 🔄 Partial | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Billing / invoicing | ❌ No | 🔜 TODO | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Multi-tenant (multiple firms) | ❌ No | 🔜 TODO | ✅ Yes | ❌ No | ❌ No | ❌ No
GDPR / privacy-first | 🔄 Partial | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
ISO 27001 audit trail | ❌ No | 🔜 TODO | ❌ No | ❌ No | ❌ No | ❌ No
REST API (JSON) | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
React frontend SPA | ❌ No | 🔜 TODO | ❌ No | ❌ No | ❌ No | ❌ No
Railway / cloud deploy | ✅ Yes | ✅ Yes | ✅ Yes | ❌ No | ❌ No | ❌ No
Open source / self-hostable | ✅ Yes | ✅ Yes | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Source: Analysis based on GitHub repos + live app review — June 2026