## 1 – Hermes Prompt (Pre-Build)
HERMES PRE-BUILD VERIFICATION PROMPT (send BEFORE any code)
Purpose: Diagnose all 6 KimiKa questions before writing a single line of code
DIAGNOSTIC MODE — do not write any code yet. Run the following checks and return a numbered report: 1. DEPLOY ENTRYPOINT a) cat Procfile (or find Procfile -maxdepth 3) b) Show exact start command — is it `gunicorn app:app`, `python app.py`, or something else? c) Does the app object path actually exist? Run: python -c "from app import app; print('OK')" 2. PORT BINDING Search app.py for app.run(). Does it use os.environ.get('PORT', 5000)? If not, show the exact line. Railway REQUIRES dynamic $PORT. 3. ENVIRONMENT VARIABLES a) List all env vars Railway has set (names only, no values). b) Which ones are MISSING vs what .env.example documents? c) Is DATABASE_URL present and pointing to Railway Postgres? 4. VENV & REQUIREMENTS a) Is .venv healthy? Run: .venv\Scripts\python.exe -c "import flask, sqlalchemy; print('OK')" b) Does requirements.txt match what is installed? Run: pip check 5. EXISTING MIGRATIONS a) Run: flask db current b) Run: flask db heads c) Are there any existing migrations that define FK structure? List their filenames. d) Do any existing migrations use tasks.caseid or cases.assignedto? 6. PROCFILE STRATEGY — is forking actually needed? Read the current Procfile. Is the CRM already reachable via the same app:app, or does it truly need a second process? Confirm before proposing fork. 7. SOFT DELETE READINESS Does any model currently have is_deleted / deleted_at columns? Are any CRM records being edited/deleted in the current UI? Yes/No. 8. RAILWAY LOGS (last 50 lines) railway logs --tail 50 Show first error line. Categorise: crash on start ¦ port ¦ missing env ¦ import error ¦ DB connection. Output format: Check ¦ Status (OK / FAIL / UNKNOWN) ¦ Finding ¦ Recommended fix Do NOT fix anything yet. Return the table, then wait.
KimiKa flags addressed in this prompt
KimiKa Question | Why it matters | Check # | Status after run
Is Procfile the REAL blocker, or venv/env vars/start cmd? | Railway crash on start is usually $PORT or missing env — not Procfile forking | Checks 1+2+3+4
Existing migrations depending on current FK structure? | Editing old migrations corrupts Railway Postgres history — must know what exists first | Check 5
'Fork/separate for CRM' = new process, new entrypoint, or new repo? | Three very different changes; only one is the right minimal fix for MVP | Check 6
Is soft-delete Phase 6, or needed NOW for audit trail? | GDPR/legal CRM data may be modified early; missing soft-delete = irreversible data loss | Check 7
Are .env / config / secrets different local vs Railway? | Most 'works local, fails Railway' bugs are env var mismatches | Check 3
Is the broken Python environment affecting Hermes conclusions? | If .venv is broken, all introspection results from Hermes are unreliable | Check 4
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space

## 2 – Decision Points
DECISION POINTS — Hermes vs KimiKa Cross-Check
Source: Hermes PLAN v1 decisions + KimiKa Tutor Space review + Master Plan v4 + AVibe Debug Skill v2
Decision | Hermes Said | Blocker? | KimiKa Challenge | Perplexity Verdict | Risk | Action for Hermes
Procfile strategy Points to app:app | Fork / separate process for CRM | YES — blocks deploy | Is forking the real fix? Could be $PORT missing, bad venv, or wrong start command — all look the same in logs | CONFIRMED BLOCKER — but NOT Procfile forking. Real cause: CRM runs via crm/__init__.py create_app(), intake still points to app:app. Fix: add separate Railway service or start command override pointing to CRM entrypoint. Do NOT touch Procfile — it will break live intake. | HIGH | Add Railway service with start command: gunicorn 'crm:create_app()' Root Dir: LexFlow Review Build Do NOT edit existing Procfile.
tasks.caseid FK None → orphaned | Add ON DELETE CASCADE | YES — data integrity | Are there existing migrations already using this FK? Editing old migrations breaks Railway Postgres history. | CONFIRMED BLOCKER — cases table is completely MISSING from DB. tasks.caseid is a dangling FK pointing to nothing. Must create cases table FIRST, then add FK. | HIGH | Step 1: create migration 001_create_cases_table.py Step 2: new migration add_tasks_caseid_fk (CASCADE) NEVER edit 430ee45 or 7a8b9c0 migrations.
cases.assignedto FK None → advisory | Add FK to users.id | NO — best practice | Does users table exist yet? FK to non-existent table = migration failure. | DEFERRED — correct call. users table confirmed present (migration 7a8b9c0d applied). Add FK after cases table exists. | MED | Add in migration 003_ after cases table created. cases.assignedto → users.id NULLABLE.
Soft vs hard delete Not specified | Soft delete (GDPR) — Phase 6 | NO — for Phase 6 | CRM data may be edited/deleted EARLY. Missing soft-delete = irreversible loss. Legal firms need audit trail from day 1. | CONFIRMED: add NOW, not Phase 6. No is_deleted / deleted_at anywhere in codebase. CRM data will be edited before Phase 6 — irreversible loss risk. | HIGH | Migration 002_add_soft_delete.py: ALTER contacts, cases, tasks, activities: ADD is_deleted BOOLEAN DEFAULT FALSE ADD deleted_at TIMESTAMPTZ nullable
Deadline statuses TBD | 'pending','completed','overdue','waived' | NO — can add later | No conflict — confirm as TEXT column with CHECK constraint in migration. | LOW — no conflict. Safe to add as CHECK constraint in cases migration. | LOW | Include in 001_create_cases_table: status CHECK IN ('pending','completed','overdue','waived')
Deadline search/filter TBD | By case, status, date range | NO — basic first | No conflict — implement as query params on GET /tasks. | LOW — implement after core CRUD confirmed working. | LOW | Phase 3 endpoint: GET /tasks?case_id=X&status=Y&due_before=Z
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space
LexFlow MVP — Updated 2026-06-19 14:09 CEST ¦ Hermes findings applied ¦ v2

## 3 – Deploy Diagnosis
RAILWAY DEPLOY DIAGNOSIS — 4 Services Status
Source: User report + Railway project ID 1fe25c7a-6a68-4c21-b27f-50c3e69daaf3
Service | URL | Current Status | Most Likely Cause | Fix Action | Priority
lexflow-mvp | https://lexflow-mvp-production.up.railway.app/ | ❌ Application failed to respond Request ID: -7b1yyfJTjyfSPSyw9P4nw | CONFIRMED ROOT CAUSE: • cases table missing from DB (no migration) • CRM entrypoint crm/__init__.py not wired to Procfile • intake app:app is correct for intake — CRM needs separate start cmd | 1. Create migration 001_create_cases_table.py 2. Run flask db upgrade on Railway 3. Add Railway service: gunicorn 'crm:create_app()' 4. Do NOT touch Procfile | 🔴 CRITICAL
web-production | https://lexflow-web-production.up.railway.app/ (inferred) | ❌ Not responding at all | 1. Start command wrong (npm start vs node dist/index.js) 2. Build failed — TypeScript compile error 3. Missing RAILWAY_PRIVATE_DOMAIN | Check Railway build logs. Verify package.json start script. Confirm root directory = apps/api | 🔴 CRITICAL
lexflow-chatbot | https://lexflow-chatbot-production.up.railway.app/ | ✅ LIVE — returns {ok:true, routes:['/health','/chat']} | Working correctly | No action needed. Note: /chat endpoint exists — wire to Hermes agent when ready. | 🟢 OK
PostgreSQL | Railway internal — not public | ⚠️ Tables exist but completeness unknown | Tables may be from old migrations. New CRM tables (contacts, cases, tasks, activities) may be missing. | Run: flask db current Run: SELECT table_name FROM information_schema.tables WHERE table_schema='public'; Verify 5 tables exist. | 🟡 VERIFY
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space
LexFlow MVP — Updated 2026-06-19 14:09 CEST ¦ Hermes findings applied ¦ v2

## 4 – What To Check (Full List)
COMPLETE PRE-BUILD CHECKLIST — Hermes + KimiKa combined
Every item must be OK before Hermes writes code. Source: AVibe Debug Skill v2 + KimiKa review + Master Plan v4
# | Check Item | How to verify (exact command) | Expected output | Risk if skipped | Done?
1 | Current deploy entrypoint | cat Procfile find . -name Procfile -maxdepth 3 | web: gunicorn app:app OR python app.py → CONFIRMED: create_app() in crm/__init__.py — confirmed working | App fails to start — Railway shows 'failed to respond' | ✅ OK
2 | Actual Railway start command | Railway dashboard → service → Settings → Start Command | Matches Procfile exactly → CONFIRMED: app.py still uses app:app — CRM needs separate entrypoint | Deploy succeeds locally, fails on Railway | ⚠️ FIX
3 | Flask app object path exists | python -c "from app import app; print('OK')" | OK (no ImportError) → CONFIRMED: DATABASE_URL present and connects | Gunicorn can't import app — crashes on start | ✅ OK
4 | $PORT dynamic binding | grep -n 'app.run' app.py | app.run(port=int(os.environ.get('PORT', 5000))) → CONFIRMED: Python 3.9.6, venv functional, flask+sqlalchemy import OK | Railway assigns random port — app never receives traffic | ✅ OK
5 | DATABASE_URL env var set | railway variables (in Railway dashboard Variables tab) | DATABASE_URL present and starts with postgres:// → CONFIRMED: pip check clean | SQLAlchemy raises OperationalError on startup | ✅ OK
6 | .venv health | .venv\Scripts\python.exe -c "import flask, sqlalchemy, psycopg2; print('OK')" | OK → CONFIRMED: gunicorn not verified in requirements.txt — check before deploy | All Hermes introspection results are wrong if venv is broken | ⚠️ FIX
7 | pip check — no broken deps | pip check | No broken requirements → CONFIRMED: Migrations 65b843c + 7a8b9c0 applied. No branching. | Import errors crash app in Railway build step | ✅ OK
8 | gunicorn in requirements.txt | Select-String -Path requirements.txt -Pattern gunicorn | gunicorn>=20 line present → CONFIRMED: Single head — no divergent branches | Railway cannot find gunicorn — deploy fails silently | ✅ OK
9 | flask db current — migration state | flask db current | A revision hash (e.g. a1b2c3d4e5f6) → CONFIRMED: cases table has ZERO migrations. tasks.caseid is dangling FK. | New migrations may conflict with existing ones — data loss risk | ❌ GAP
10 | flask db heads — no branching | flask db heads | Single head hash (no divergent branches) → CONFIRMED: users table confirmed present (migration 7a8b9c0 applied) | Branched migrations cause flask db upgrade to fail | ✅ OK
11 | Existing FK structure in migrations | Get-Content migrations\versions\*.py ¦ Select-String 'foreign_key¦ForeignKey¦caseid¦assignedto' | Shows which FKs already exist → CONFIRMED: contacts, cases, tasks, activities all missing cases table in DB | Adding duplicate FK = migration error that corrupts DB | ❌ GAP
12 | users table existence | flask db current + SELECT table_name FROM information_schema.tables | users table in list | cases.assignedto FK to users.id fails if users doesn't exist
13 | All 5 CRM tables present in Railway Postgres | SELECT table_name FROM information_schema.tables WHERE table_schema='public'; | contacts, cases, tasks, activities, users (+ matters, documents, events) → CONFIRMED: is_deleted + deleted_at MISSING from all tables — add NOW | Missing tables = 500 errors on every API call | ❌ GAP
14 | CORS configured for Lovable domain | grep -n 'CORS\¦cors\¦ALLOWED_ORIGIN' app.py | flask-cors with ALLOWED_ORIGIN from env var | Lovable frontend blocked by browser CORS policy
15 | Railway logs — last crash reason | railway logs --tail 50 | Identify: crash-on-start ¦ port ¦ missing env ¦ import error ¦ DB connection | Fixing wrong root cause = wasted time
16 | is_deleted column in contacts + cases | SELECT column_name FROM information_schema.columns WHERE table_name='contacts'; | is_deleted and deleted_at columns present | GDPR: hard-deleted legal CRM data cannot be recovered or audited
17 | Local app boots cleanly | python app.py then curl http://localhost:5000/health | {"status":"ok","db":"ok"} | Deploy to Railway before local green = debug in the dark
18 | staging branch deploy before main | git checkout staging && git push origin staging | Railway staging deploy succeeds | Breaking change goes straight to production
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space
LexFlow MVP — Updated 2026-06-19 14:09 CEST ¦ Hermes findings applied ¦ v2

## 5 – Hermes Prompt 2 (Post-Diag)
HERMES PROMPT 2 — Send AFTER diagnosis report received and reviewed
Paste this only after you have read the Check table from Prompt 1 and confirmed there are no surprises
APPROVED — BUILD MODE. Build in this exact order. One step at a time. Show me the file name and diff before saving each file. STEP 1 — Fix Railway deploy blocker (from diagnosis) - Apply only the fix identified in the diagnosis (Procfile / $PORT / env var — whichever failed) - Verify locally: python app.py → curl http://localhost:5000/health → must return {"status":"ok"} - Do NOT touch any other file - Backup first: Copy-Item app.py app.py.bak STEP 2 — Add is_deleted + deleted_at to contacts and cases (GDPR, not Phase 6) - New migration ONLY — never edit existing migration files - Migration name: add_soft_delete_contacts_cases - Columns: is_deleted BOOLEAN DEFAULT FALSE, deleted_at TIMESTAMPTZ nullable - Run locally: flask db migrate -m add_soft_delete_contacts_cases && flask db upgrade STEP 3 — Add tasks.caseid FK (only if no existing migration already defines it) - Add ON DELETE CASCADE (confirmed: legal tasks are children of cases) - New migration: add_tasks_caseid_fk STEP 4 — Add cases.assignedto FK to users.id (ONLY if users table confirmed present in Step 0 diagnosis) - If users table absent: leave assignedto as nullable TEXT — document in CLAUDE.md STEP 5 — Add deadline status CHECK constraint - tasks.status TEXT DEFAULT 'pending' CHECK (status IN ('pending','completed','overdue','waived')) - New migration: add_task_status_constraint STEP 6 — Push to staging branch (NOT main) git checkout staging && git add . && git commit -m 'fix: deploy blocker + schema hardening' git push origin staging Wait for Railway staging deploy — confirm green STEP 7 — Report back For each step: filename changed ¦ test run ¦ result ¦ next risk Rules: - One PowerShell command per line — no chaining - Backup every file before editing: Copy-Item <file> <file>.bak - Never edit existing migration files - Never push to main until staging is green - If any step fails: STOP and report the exact error before continuing
When to use Prompt 2
Condition | Action
All 18 checks in Sheet 4 are OK or explained | Send Prompt 2 — safe to build
Checks 1-4 (Procfile/PORT/env/venv) have any FAIL | Fix those first, re-run checks, THEN send Prompt 2
Check 9/10/11 show branched or conflicting migrations | Ask Hermes to resolve migration state first — separate prompt
Check 16 shows is_deleted missing | It is already in Prompt 2 Step 2 — no extra prompt needed
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space

## 6 – Schema Decisions
SCHEMA DECISION TABLE — aligned to Master Plan v4 + May 28 approved model
Source: Master Plan v4 DB Schema + SchemaUpdate20260528 + KimiKa review
Table | Column / FK | Current State | Hermes Proposed | KimiKa Flag | Verdict | Migration needed? | Migration name
contacts | is_deleted, deleted_at | MISSING | Phase 6 soft delete | Needed NOW — CRM data edited early | ADD NOW | YES — new | add_soft_delete_contacts_cases
cases | is_deleted, deleted_at | MISSING | Phase 6 soft delete | Same — legal audit trail from day 1 | ADD NOW | YES — new | add_soft_delete_contacts_cases
tasks | caseid FK ON DELETE CASCADE | No FK — orphan risk | Add CASCADE | Check for existing migration first | ADD — new migration only | YES — new | add_tasks_caseid_fk
cases | assignedto FK → users.id | Nullable TEXT | Add FK | users table may not exist yet | DEFER until users confirmed | CONDITIONAL | add_cases_assignedto_fk
tasks | status CHECK constraint | Free TEXT | pending/completed/overdue/waived | No conflict — safe to add | ADD NOW | YES — new | add_task_status_constraint
contacts | relationship_capture_status | MISSING per May 28 decision | Add for contact_relationships phase | Approved in May 28 schema session | ADD per approved plan | YES — new | add_relationship_capture_status
case_participants | Full table | NOT YET CREATED | Next schema round | Approved in May 28 session | CREATE — next migration round | YES — new table | create_case_participants
contact_relationships | Full table | NOT YET CREATED | After case_participants | Approved in May 28 session — depends on case_participants | CREATE — after case_participants | YES — after case_participants | create_contact_relationships
LexFlow MVP — Generated 2026-06-19 14:00 CEST ¦ Source: Master Plan v4 + SchemaUpdate20260528 + AVibe Debug Skill v2 + KimiKa Tutor Space

## 7 – Prompt 3 (Final Check)
HERMES PROMPT 3 — Final 5-minute check before writing any code
Send this AFTER Prompt 1 diagnosis. Sharp, minimal, no recheck of already-confirmed items.
FINAL CHECK — 5 minutes. Do not build yet. Answer only these 5 questions: 1. REQUIREMENTS.TXT grep gunicorn requirements.txt Expected: gunicorn>=20.x → if missing: add it now before deploy. 2. CRM BLUEPRINT REGISTERED? grep -n 'register_blueprint\¦from crm' app.py Expected: CRM blueprint NOT in app.py (it uses create_app() separately). If it IS imported in app.py → risk of double-init conflict. Flag it. 3. RAILWAY CRM SERVICE — does it already exist? Open: https://railway.com/project/1fe25c7a-6a68-4c21-b27f-50c3e69daaf3 Q: Is there already a second service for CRM, or only one service (intake)? Answer: yes/no. Do not create it yet. 4. MIGRATION CHAIN INTEGRITY grep -E 'down_revision' migrations/versions/*.py Confirm: 430ee45 → 65b843c → 7a8b9c0 is a clean linear chain. New migration 001_create_cases_table must set down_revision = '7a8b9c0d1e2f'. Confirm the exact last revision hash before I write the migration. 5. RESEND / EMAIL ENV VAR grep -r 'RESEND\¦resend\¦send_email' crm/ --include='*.py' ¦ grep -v '.pyc' If email sending is already wired: confirm RESEND_API_KEY is in Railway Variables. If not wired yet: note it — do not add now. Return a 5-row table: Question ¦ Answer ¦ Blocker? ¦ Action needed Then wait for 'BUILD APPROVED'.
Why these 5 — and nothing else
Question | Why it matters | Risk if skipped
gunicorn in requirements.txt | Railway build step installs from requirements.txt — missing gunicorn = deploy fails silently | App never starts on Railway even if code is perfect
CRM blueprint in app.py | If CRM is already imported in app.py and you add a second Railway service pointing to create_app(), you get double-init and route conflicts | Silent 500s on overlapping routes
Railway CRM service exists? | If a 2nd service already exists but misconfigured, creating another wastes credits and creates routing confusion | Duplicate services, wrong URLs in Lovable
Migration chain last revision | New migration must chain to exact last revision hash — wrong hash = flask db upgrade fails or skips tables | cases table never created despite migration running
Resend/email wired? | If email is already wired but RESEND_API_KEY missing on Railway, every case create will crash the API | Phase 3 API returns 500 on POST /cases
LexFlow MVP — Updated 2026-06-19 14:09 CEST ¦ Hermes findings applied ¦ v2

## 8 – File Paths (Confirmed)
FILE PATHS — confirmed by Hermes pre-build scan
Base: /Users/olesiarasing/Desktop/LexFlow/LexFlow Review Build/
Category | Relative Path | Status | Notes
App entrypoint | app.py | ✅ Live | Intake form — do NOT modify Procfile line
CRM factory | crm/__init__.py | ✅ OK | create_app() confirmed working
CRM cases routes | crm/routes/cases.py | ⚠️ Broken | Expects cases table — table missing from DB
Migration 1 | migrations/versions/430ee4511375_initial_crm_schema.py | ✅ Applied | Initial CRM schema
Migration 2 | migrations/versions/65b843c76b3d_create_contacts_table.py | ✅ Applied | Contacts table
Migration 3 | migrations/versions/7a8b9c0d1e2f_add_users_and_tasks_tables.py | ✅ Applied | Users + tasks — LAST applied revision
MISSING migration | migrations/versions/001_create_cases_table.py | ❌ Missing | Must be created — down_revision=7a8b9c0d1e2f
MISSING migration | migrations/versions/002_add_soft_delete.py | ❌ Missing | is_deleted + deleted_at — add after cases
Prebuild check doc | PREBUILD_CHECK_V1.md | ✅ Created | Created by Hermes — source of truth for this session
Env file | .env | ✅ Present | DATABASE_URL confirmed working — NEVER commit
Env example | .env.example | ⚠️ Verify | Must document all current vars inc RESEND_API_KEY
Requirements | requirements.txt | ⚠️ Verify | gunicorn presence unconfirmed — check Prompt 3 Q1
Alembic config | migrations/env.py | ✅ Present | Standard Flask-Migrate setup
CRM models dir | crm/models/ | ✅ Present | Models confirmed via __tablename__ grep
LexFlow MVP — Updated 2026-06-19 14:09 CEST ¦ Hermes findings applied ¦ v2