## 0_INDEX
LexFlow MVP — Master Session Workbook ¦ June 19 2026
Railway Fix · Build Gap · Docs Map · Competitors · Hermes Prompts · Phase Roadmap
Sheet | Name | What's Inside | Use It When
1 | Railway_Status | 4-service status, root causes, 10-step fix plan, Hermes Prompt 1 | RIGHT NOW — fix the Railway crash before anything else
2 | Build_Gap_Analysis | 21-component gap table: built / partial / missing, completion % | Before starting a Hermes build session — know what exists
3 | Local_Docs_Map | 7-doc hierarchy, Hermes session startup sequence (6 steps) | Every time you start a new Hermes or Claude Code session
4 | Competitor_Apps | Top 3 live apps with links, 5 OSS repos with GitHub links, feature matrix vs Clio | Investor pitch prep, feature prioritization, Hermes clone-study
5 | Hermes_Prompts | Q5 answer, Prompt 1 (PLANNER), Prompt 2 (BUILD), VS Code env fix | Copy-paste prompts into Hermes at session start
6 | Phase_Roadmap | Full NOW/NEXT/LATER roadmap: 23 tasks, files, verify commands, time estimates | Sprint planning, investor roadmap, Hermes build order
Key Project Facts (from v4 Master Plan + CLAUDE.md)
Repo path | ~/Desktop/LexFlow/LexFlow Review Build/
Railway project | https://railway.com/project/1fe25c7a-6a68-4c21-b27f-50c3e69daaf3
Active services | lexflow-mvp (Flask) · web-production (Next.js) · lexflow-chatbot · PostgreSQL
Chatbot (✅ ONLINE) | https://lexflow-chatbot-production.up.railway.app/
MVP (❌ BROKEN) | https://lexflow-mvp-production.up.railway.app/
DB | PostgreSQL on Railway — tables partial — flask db current needed
Stack | Flask + SQLAlchemy + PostgreSQL + Next.js (Lovable) + Resend + Railway + Netlify (LP)
Source of truth | Master Plan v4 xlsx → CLAUDE.md → AVibe_Debug_Skill_v2.md
Generated | 2026-06-19 13:46 CEST

## 1_Railway_Status
LexFlow Railway Deployment — Status Diagnosis & Fix Plan
Service Status Overview
Service | URL | Status | Symptom | Root Cause (Most Likely) | Priority Fix
lexflow-mvp (Flask API) | https://lexflow-mvp-production.up.railway.app/ | ❌ FAILING | Application failed to respond / Request ID error | Missing Procfile or gunicorn; $PORT not bound; missing env vars at runtime | 🔴 FIX FIRST — Add Procfile, bind $PORT, verify env vars
web-production (Next.js) | https://web-production.up.railway.app/ | ⚠️ NOT RESPONDING | No response at all; build may be failing silently | apps/web missing start command or build output; ROOT_DIR not set in Railway | 🟠 FIX SECOND — Set Root Directory to apps/web, verify npm run build
lexflow-chatbot | https://lexflow-chatbot-production.up.railway.app/ | ✅ ONLINE | Returns {"ok":true,"routes":["/health","/chat"]} | Working correctly — chatbot backend is healthy | ✅ No action needed — verify /chat endpoint with a test payload
PostgreSQL (Railway) | (internal Railway service) | ✅ ONLINE | Tables exist but completeness unknown | Schema may be partial — migrations may not have run fully | 🟡 VERIFY — Run flask db current and compare to v4 Master Plan
Ordered Fix Plan — Execute Locally Then Push to GitHub → Railway
Step | Action | File / Location | Command / Detail | Verify With | Risk
1 | Backup repo first | LexFlow Review Build/ | Copy-Item -Recurse . ../backup_lexflow_2026_06_19 | dir ../backup_lexflow_2026_06_19 | LOW
2 | Add / fix Procfile | LexFlow Review Build/Procfile | web: gunicorn app:app --bind 0.0.0.0:$PORT --workers 2 | cat Procfile — confirm gunicorn line | LOW
3 | Bind $PORT in app.py | LexFlow Review Build/app.py | app.run(host='0.0.0.0', port=int(os.environ.get('PORT', 5000))) | flask run — no crash on start | LOW
4 | Verify requirements.txt has gunicorn | LexFlow Review Build/requirements.txt | Add line: gunicorn>=21.0.0 (if missing) | pip install -r requirements.txt | LOW
5 | Verify Railway env vars | Railway Dashboard → lexflow-mvp → Variables | Must have: DATABASE_URL, RESEND_API_KEY, NODE_ENV=production, X_ADMIN_TOKEN | Railway Variables tab — all 4 keys visible | MEDIUM
6 | Test Flask locally | LexFlow Review Build/ | flask run --debug → curl http://localhost:5000/health | Browser: localhost:5000/health returns {ok:true} | LOW
7 | Fix Next.js (apps/web) | apps/web/ | Railway: Root Directory = apps/web, Build = npm run build, Start = npm start | Railway deploy logs — no build error | MEDIUM
8 | Verify DB migrations | LexFlow Review Build/migrations/ | flask db current → flask db upgrade | flask db current shows head | MEDIUM — never edit old migrations
9 | Git checkpoint & push to staging | repo root | git add . && git commit -m 'fix: Railway port bind and Procfile' && git push origin staging | Railway staging service auto-deploys → check deploy logs | LOW
10 | Merge to main (production) | main branch | Open PR: staging → main → merge after staging passes | https://lexflow-mvp-production.up.railway.app/health returns 200 | LOW after staging confirmed
HERMES PROMPT 1 — Railway Debug (copy-paste ready)
Switch to PLANNER mode. Do not write any code yet. Working directory: ~/Desktop/LexFlow/LexFlow Review Build Read these files: Procfile (or confirm missing), app.py (check $PORT binding), requirements.txt (check gunicorn), .env.example, migrations/versions/ (list files). Then check Railway config for service lexflow-mvp: Root Directory, Build Command, Start Command, and all environment variable NAMES (not values). Produce PLAN v1: A) What is built and confirmed working locally B) Exact cause of "Application failed to respond" on Railway C) What is missing or misconfigured for production deploy D) Next 5 fix tasks in exact order with file names Output plan only. Wait for: APPROVED - BUILD

## 2_Build_Gap_Analysis
LexFlow MVP — What Is Built vs What Is Missing (as of June 19 2026)
Component-by-Component Gap Analysis
Layer | Component | Built? | Location | Works Locally? | Works on Railway? | Missing / Next Action
Backend | app.py — intake form handler | ✅ YES | LexFlow Review Build/app.py | ✅ YES | ❌ FAILING | Fix $PORT + Procfile (Step 2-3)
Backend | Flask CRM routes (contacts, cases, tasks) | ⚠️ PARTIAL | app.py + crm/ | ⚠️ PARTIAL | ❌ NOT DEPLOYED | Complete crm/ blueprint, register in app.py
Backend | SQLAlchemy models (v4 schema) | ⚠️ PARTIAL | crm/models/ | ⚠️ PARTIAL | ❌ NOT DEPLOYED | Add case_participants, contact_relationships stubs
Backend | Flask-Migrate / Alembic migrations | ⚠️ PARTIAL | migrations/versions/ | ⚠️ PARTIAL | ❓ UNKNOWN | Run flask db current — verify head matches v4 schema
Backend | JWT auth (X-Admin-Token Phase 1) | ⚠️ NOT STARTED | — | ❌ NO | ❌ NO | Add Flask-JWT-Extended, protect CRM routes
Backend | Gunicorn + Procfile (Railway production) | ❌ MISSING | Procfile | N/A | ❌ CAUSE OF CRASH | Create Procfile with gunicorn binding $PORT — FIX NOW
Backend | Email notifications (Resend) | ⚠️ PARTIAL | app.py (intake email) | ✅ YES | ❓ UNKNOWN | Extend to case status changes and deadlines
Backend | WhatsApp notifications | ❌ NOT STARTED | — | ❌ NO | ❌ NO | Phase 2 — integrate Twilio or WhatsApp Cloud API
Frontend | Next.js web app shell (apps/web) | ✅ YES | apps/web/ | ✅ YES | ⚠️ NOT RESPONDING | Fix Railway Root Directory = apps/web
Frontend | Lovable CRM UI (Task Manager) | ⚠️ PARTIAL | Lovable project | ✅ YES | ⚠️ WIRED TO SUPABASE | Re-wire hooks to Railway Flask API (see Tasks MNG doc)
Frontend | Client intake form (public-facing) | ✅ YES | app.py /intake route | ✅ YES | ❌ DOWN (MVP crash) | Will work once MVP Railway fix applied
Frontend | AI chatbot widget | ✅ YES | lexflow-chatbot service | ✅ YES | ✅ ONLINE | Wire to frontend — chatbot backend is healthy
Database | PostgreSQL on Railway | ✅ YES | Railway PostgreSQL service | ✅ YES | ✅ ONLINE | Verify all v4 tables exist — run flask db current
Database | contacts table | ✅ YES | Railway DB | ✅ YES | ✅ YES | Add relationship_capture_status column (v4 rule)
Database | cases table | ✅ YES | Railway DB | ✅ YES | ✅ YES | Verify contact_id FK, stage field
Database | case_participants table | ⚠️ PARTIAL | Migration pending | ❓ UNKNOWN | ❌ NOT APPLIED | Write migration 002 — add case_participants
Database | contact_relationships table | ❌ NOT STARTED | — | ❌ NO | ❌ NO | Phase 2 — after case_participants ships
Database | tasks / activities tables | ⚠️ PARTIAL | Railway DB (partial) | ❓ UNKNOWN | ❓ UNKNOWN | Verify schema matches v4 field list
DevOps | Railway deploy (staging branch) | ⚠️ NOT USED | GitHub / Railway | N/A | N/A | Set up staging service linked to staging branch — RULE
DevOps | .env.example up to date | ⚠️ OUTDATED | repo root | N/A | N/A | Add DATABASE_URL, RESEND_API_KEY, NODE_ENV, X_ADMIN_TOKEN
DevOps | CLAUDE.md source of truth | ✅ YES | repo root CLAUDE.md | N/A | N/A | Keep updated after each sprint — no drift
Build Completion Summary
Status | Count | % of Total | Next Action Focus
✅ Built & Working | 8 |  | Monitor — keep working
⚠️ Partial / Needs Fix | 9 |  | ← Most of your work is here
❌ Not Started | 4 |  | Phase 2 items
TOTAL |  | 100%

## 3_Local_Docs_Map
Q3.0 — Where Are Your Most Complete Project Docs Locally?
Source of Truth Hierarchy (use in this order)
Priority | Document | Local Path | What It Contains | Status | Action
#1 ⭐ MASTER | LexTaskFlow_Master_Plan_v4_UPDATED.xlsx | ~/Desktop/LexFlow/ (Space files) | ALL decisions: schema, stack, auth, frontend, DB, phase order, risks, v4 overrides, May 27-28 updates | ✅ ACTIVE | Give to Hermes FIRST before any build session
#2 ⭐ ACTIVE | CLAUDE.md | LexFlow Review Build/ (repo root) | Stack, repo structure, commands, env conventions, protected files, deploy model — Hermes reads this on startup | ✅ ACTIVE | Keep updated after every sprint — never let it drift from reality
#3 | AVibe_Debug_Skill_v2.md | ~/Desktop/LexFlow/ (Space files) | Full debug playbook: Flask architecture, folder structure, URL routing, Railway fix checklist, migration rules | ✅ ACTIVE | Pass to Hermes when debugging — contains preferred Flask folder structure
#4 | Flask/backend Starter document | Space files (Perplexity Space) | Approved schema field list, API contracts, migration sequence — second source of truth after Master Plan v4 | ✅ ACTIVE | Used alongside Master Plan v4 — if conflict, v4 wins
#5 | LexFlow_Full_Session_Ref__Chat-bot-and-LP.md | Space files (Perplexity Space) | Chatbot architecture, landing page deploy decisions, Railway vs Netlify decision log | ✅ REFERENCE | Use for chatbot wiring and LP context
#6 | Perplexity_WebApp_BuildingSpace.md | Space files (Perplexity Space) | Model-routing and session protocol — which AI to use for which task | ✅ REFERENCE | Use when setting up new Hermes or Claude Code sessions
ARCHIVE ⚠️ | Older CSV schema fragments / v3 plan | Various local files | Superseded field decisions — DO NOT use for new migrations or API contracts | ❌ ARCHIVE | Mark as ARCHIVE — do not pass to Hermes as active docs
Hermes Session Startup — Feed Docs in This Exact Order
Step | Action | Source | Why
1 | Open Hermes Desktop App | — | Start new session
2 | Attach CLAUDE.md | repo root | Drag file into Hermes — this becomes the project context
3 | Attach Master Plan v4 xlsx | ~/Desktop/LexFlow/ | Gives Hermes the complete schema and decision history
4 | Attach AVibe_Debug_Skill_v2.md | Space files | Gives Hermes the Flask architecture and debug playbook
5 | Paste Hermes Prompt 1 from Sheet 1 | — | Ask for PLAN first — do not say BUILD yet
6 | Review plan, then type: APPROVED - BUILD | — | Autonomous mode begins — Hermes works without asking again

## 4_Competitor_Apps
Q3.1 & Q4 — Best Live Legal Intake + CRM SaaS (LexFlow Feature Match)
Top 3 Commercial Competitors — Live Apps (with Direct Links)
# | Product | Live App Link | GitHub / OSS Link | Intake Form | AI Chatbot | Auto-assign Lawyer | Email+WA Notify | Status Updates | Calendar+Kanban | GDPR/ISO
1 ⭐ | Clio Manage + Clio Grow | https://app.clio.com | https://github.com/cliolegaltechnology | ✅ Full intake forms + chatbot | ✅ Clio Duo AI | ✅ Matter assignment | ✅ Email / ❌ WA native | ✅ Client portal updates | ✅ Calendar + Tasks | ✅ GDPR, SOC2
2 | MyCase | https://app.mycase.com | https://github.com/topics/mycase | ✅ Online intake forms | ⚠️ Limited AI | ⚠️ Manual assignment | ✅ Email + SMS / ❌ WA | ✅ Client portal | ✅ Calendar + Kanban | ✅ GDPR
3 | Filevine (LOIS AI) | https://app.filevine.com | https://github.com/filevine | ✅ Smart intake | ✅ LOIS AI Agent (full agentic) | ✅ AI auto-assign | ✅ Email+SMS / ❌ WA | ✅ Real-time status | ✅ Full PM suite | ✅ GDPR, SOC2, HIPAA
Best Open-Source Repos for Hermes to Study/Clone-Build
# | Repo Name | GitHub Link | Live Demo | Stack | Best For LexFlow | Stars ~ | Last Active | Clone Fit
1 ⭐ | Legal-Ease (sujal-pawar) | https://github.com/sujal-pawar/Legal-Ease | https://github.com/sujal-pawar/Legal-Ease#demo | React + Node.js + MongoDB | Full case lifecycle, virtual hearings, judicial tracking — closest feature match | ~180 | 2025 | ⭐⭐⭐⭐⭐ BEST MATCH
2 ⭐ | AI-Chatbot-for-Lawyer | https://github.com/danieladdisonorg/AI-Chatbot-for-Lawyer | No live demo — run locally | Python + Groq LLM + FAISS + Streamlit | Intake chatbot, doc analysis, multi-language — matches LexFlow chatbot module | ~90 | 2025 | ⭐⭐⭐⭐ CHATBOT MODULE
3 | LawGlance | https://github.com/lawglance/lawglance | https://lawglance.com | Python + RAG + FastAPI | AI legal assistant + case management — privacy-first, open source | ~60 | 2024 | ⭐⭐⭐ REFERENCE
4 | SuiteCRM | https://github.com/SuiteCRM/SuiteCRM | https://suitecrm.com/download/ | PHP + MySQL | Enterprise CRM base — good for studying contact/case relationship models | ~4,100 | Active | ⭐⭐ STUDY ONLY — not legal-specific
5 | Iuris-Soft | https://github.com/createrivabu/Iuris-Soft | No live demo | Java | Open-source legal management — older but has contact+case+document model | ~30 | 2018 | ⭐ ARCHIVE REFERENCE
LexFlow Feature Coverage vs Clio (Your Direct Competitor)
Feature | Clio | LexFlow NOW | LexFlow Phase 2 | LexFlow Phase 3 | Priority
Online intake form | ✅ | ✅ Built | — | — | 🔴 SHIP NOW
AI intake chatbot | ✅ | ✅ Backend online | Wire to frontend | — | 🔴 SHIP NOW
Auto-assign lawyer (AI) | ✅ | ❌ Not built | ✅ Build | — | 🟠 Phase 2
CRM (contacts + cases) | ✅ | ⚠️ Partial | ✅ Complete | — | 🔴 SHIP NOW
Email notifications | ✅ | ⚠️ Intake only | ✅ Full pipeline | — | 🟠 Phase 2
WhatsApp notifications | ❌ Native | ❌ Not built | ✅ Twilio/WA API | — | 🟠 Phase 2
Client status updates | ✅ | ❌ Not built | ✅ Portal/email | — | 🟠 Phase 2
Deadline reminders | ✅ | ❌ Not built | ✅ Tasks module | — | 🟠 Phase 2
Calendar | ✅ | ❌ Not built | ✅ Build | — | 🟡 Phase 3
Kanban task board | ✅ | ⚠️ Lovable shell | ✅ Wire to API | — | 🟠 Phase 2
GDPR compliance | ✅ | ⚠️ Design only | ✅ Implement | — | 🟠 Phase 2
ISO 27001 | ✅ | ❌ Not started | — | ✅ Phase 3 | 🟡 Phase 3
Billing / invoicing | ✅ | ❌ Not started | — | ✅ Phase 3 | 🟡 Phase 3
Multi-language UI | ⚠️ Limited | ⚠️ LP only (IT/EN) | ✅ App i18n | — | 🟠 Phase 2

## 5_Hermes_Prompts
Hermes Prompts — Complete Session Playbook (June 2026)
Q5 — Does 'Show Plan First' Conflict With Hermes Auto-Approve?
Question | Does asking Hermes to show a plan conflict with the autonomous mode instruction?
Answer | NO CONFLICT — Hermes respects session-scoped overrides. Adding 'show plan first, then wait for APPROVED - BUILD' for this session only is a standard planning gate, not a contradiction of autonomy.
How it works | Hermes is fully autonomous AFTER approval. The plan step is a one-time checkpoint at the START of the session. Once you type APPROVED - BUILD, Hermes works without asking again.
Rule to add | In Hermes system prompt or first message: 'For this session only: produce PLAN before coding. Wait for explicit APPROVED - BUILD. After that, proceed fully autonomously without further confirmation requests.'
Risk if skipped | Hermes may build in the wrong order, hit the same Railway error again, or modify files outside scope. The plan gate costs 5 minutes and saves 2-3 hours of rework.
HERMES PROMPT 1 — Railway Debug + Gap Analysis (PLANNER MODE)
Switch to PLANNER mode. Do not write any code yet. Working directory: ~/Desktop/LexFlow/LexFlow Review Build Step 1 — Read these files: - Procfile (check if exists, check gunicorn + $PORT binding) - app.py (check: os.environ.get('PORT'), gunicorn import, all routes registered) - requirements.txt (check: gunicorn, flask, flask-sqlalchemy, flask-migrate, flask-jwt-extended present) - .env.example (list all variable names) - migrations/versions/ (list all migration files) Step 2 — Check Railway service config for: lexflow-mvp, web-production - Root Directory setting - Build Command - Start Command - Environment variable NAMES (not values) — confirm DATABASE_URL, RESEND_API_KEY, NODE_ENV, X_ADMIN_TOKEN present Step 3 — Produce PLAN v1 with exactly these sections: A) What is confirmed built and working locally B) Exact root cause of "Application failed to respond" on Railway MVP C) Exact root cause of web-production not responding D) What DB tables exist vs what v4 Master Plan requires (list any missing) E) Next 8 fix tasks in priority order with: file name, exact change, verification command Output PLAN only. Do NOT write any code or make any file changes. Wait for: APPROVED - BUILD
HERMES PROMPT 2 — Build Mode (send AFTER approving the plan)
APPROVED - BUILD. Proceed fully autonomously. No further confirmation needed for this session. Execute the plan in order. Rules: 1. Backup before any file change: Copy-Item -Recurse . ../backup_$(Get-Date -Format 'yyyyMMdd_HHmm') 2. One change at a time — test locally after each step 3. Never edit existing migration files — create new ones only 4. After each fix: show exact verification command and its output 5. Git checkpoint after every working step: git add . && git commit -m '[fix description]' 6. Push to staging branch first: git push origin staging 7. Only push to main after staging Railway deploy confirms green Start with: Step 1 — Procfile + $PORT fix End session with: push to staging + summary of what was fixed, what is still open
BONUS: VS Code Python Env Error Fix (from your June 18 log)
Error seen | pet Failed to find handler for method info ¦ Conda not found
Root cause | VS Code Python Envs extension (ms-python.vscode-python-envs 1.34.0) is trying to find Conda — you don't have it. The .venv at LexFlow Review Build/.venv was found correctly (Python 3.11.15).
Fix 1 | Ignore the Conda error — it's non-blocking. Your .venv is discovered correctly. Select it in VS Code: Cmd+Shift+P → Python: Select Interpreter → choose .venv
Fix 2 | If the 'pet Failed to find handler' error spams the log: in VS Code settings, disable the Python Envs extension and use the older ms-python.python extension instead
Active interpreter | ~/Desktop/LexFlow/LexFlow Review Build/.venv (Python 3.11.15 — confirmed discovered)

## 6_Phase_Roadmap
LexFlow MVP — Complete Phase Roadmap (Based on v4 Master Plan)
NOW — Fix Railway + Ship MVP Core
Task | File / Module | How (1 line) | Verify With | Est. Time | Priority
Fix Procfile + $PORT binding | app.py, Procfile | gunicorn boot + $PORT | lexflow-mvp responds on Railway | 1 hour | 🔴
Fix web-production Railway config | apps/web Railway settings | Root Dir = apps/web | Next.js frontend loads on Railway | 30 min | 🔴
Complete CRM blueprint (contacts, cases) | crm/ folder | GET/POST routes + SQLAlchemy models | curl /api/v1/contacts returns 200 | 3-4 hours | 🔴
Run flask db upgrade — verify v4 schema | migrations/ | flask db current → flask db upgrade | flask db current shows head | 30 min | 🔴
Re-wire Lovable frontend hooks to Flask API | Lovable project | Replace Supabase hooks with Railway API calls | Task list loads from Flask API | 2-3 hours | 🔴
Wire chatbot widget to frontend | apps/web + chatbot | Embed chatbot widget, point to Railway chatbot URL | Chatbot appears on LP and app | 1 hour | 🔴
Push to staging, verify, merge to main | GitHub + Railway | git push origin staging → PR to main | All 4 Railway services green | 1 hour | 🔴
NEXT — Phase 2 Features
Task | File / Module | How (1 line) | Verify With | Est. Time | Priority
JWT auth (Flask-JWT-Extended) | app/, auth blueprint | Login/logout/me routes + token validation | Protected CRM routes return 401 without token | 4-5 hours | 🟠
AI auto-assign lawyer | cases blueprint + AI route | POST /api/v1/cases/assign — call OpenRouter model | New case gets lawyer_id assigned automatically | 3-4 hours | 🟠
Email notifications — full pipeline | Resend + activities | Status change → Resend email to client + lawyer | Client receives email on case stage change | 3 hours | 🟠
WhatsApp notifications | Twilio or WA Cloud API | New service: notification worker on Railway | Client receives WA message on intake + status change | 4-5 hours | 🟠
case_participants migration (002) | migrations/versions/ | flask db migrate + upgrade | case_participants table in DB | 1 hour | 🟠
Kanban board wiring | Lovable + Flask API | PATCH /api/v1/cases/:id/stage → Kanban card moves | Drag case card → stage updates in DB | 2-3 hours | 🟠
Deadline reminders (tasks module) | tasks blueprint + worker | Background job: check deadlines → send email | Lawyer gets reminder 48h before deadline | 3-4 hours | 🟠
GDPR compliance basics | All routes + DB | Consent field on contacts, right-to-delete endpoint | DELETE /api/v1/contacts/:id purges all data | 2-3 hours | 🟠
contact_relationships migration (003) | migrations/versions/ | Add contact_relationships table | Directors/shareholders linked via table not notes | 1 hour | 🟠
Multi-language app UI (IT/EN) | apps/web | i18n with next-intl or react-i18next | Toggle switches all app labels IT ↔ EN | 3-4 hours | 🟠
LATER — Phase 3 (Post-MVP, Revenue)
Task | File / Module | How (1 line) | Verify With | Est. Time | Priority
Calendar view (full) | apps/web + cases | Calendar component linked to deadlines + hearings | Lawyer sees all deadlines on calendar | 5-6 hours | 🟡
ISO 27001 compliance audit | All services | Security review, access logs, audit trail | Pass compliance checklist | TBD | 🟡
Billing / invoicing module | New billing blueprint | Time tracking → invoice generation → payment | Lawyer logs time → PDF invoice sent to client | 8-10 hours | 🟡
Multi-tenant (firm_id isolation) | All models + routes | Add firm_id to all tables, row-level security | Firm A cannot see Firm B data | 5-6 hours | 🟡
Advanced AI (document analysis) | AI service on Railway | Upload contract → AI extracts key clauses | Lawyer sees extracted clauses in case view | 6-8 hours | 🟡
Mobile app or PWA | apps/web or React Native | PWA manifest + offline support OR native app | Lawyer uses LexFlow on phone | 10+ hours | 🟡