## 🗺 Upgraded Plan V5
LEXFLOW V2 — UPGRADED PLAN (v5, June 19 2026)
# | Phase | Step | Action | Owner | Branch | Deploy Target | Status | Risk | Notes
0.1 | REPO SETUP | Create new private GitHub repo | LexFlow-App-V2 | Hermes | — | GitHub | ⬜ TODO | LOW | Name: LexFlow-App-V2, private, init with README
0.2 | REPO SETUP | Push full Flask backend to new repo | Hermes / Olesia | Hermes | main | GitHub | ⬜ TODO | MED | Copy all backend files from current 'LexFlow Review Build' folder
0.3 | REPO SETUP | Verify .gitignore covers .env, .venv, uploads/ | Hermes | main | GitHub | ⬜ TODO | LOW | Never commit secrets
1.1 | LOVABLE SYNC | Connect new repo to Lovable (GitHub integration) | Olesia | — | Lovable | Lovable | ⬜ TODO | LOW | Lovable > Settings > GitHub > select LexFlow-App-V2
1.2 | LOVABLE SYNC | Create new Lovable project from connected repo | Olesia | — | Lovable | Lovable | ⬜ TODO | LOW | NOT remix — fresh project reading the repo
1.3 | LOVABLE BUILD | Send Lovable Prompt 1 (STYLE SYSTEM — see Sheet 3) | Olesia | — | Lovable | Lovable | ⬜ TODO | LOW | Copy-paste from Sheet 3 exactly
1.4 | LOVABLE BUILD | Send Lovable Prompt 2 (API CONFIG — see Sheet 3) | Olesia | — | Lovable | Lovable | ⬜ TODO | LOW | Sets src/config.ts with correct routes
1.5 | LOVABLE BUILD | Send Lovable Prompt 3 (SCREENS — see Sheet 3) | Olesia | — | Lovable | Lovable | ⬜ TODO | MED | All 6 screens wired to backend in one prompt
1.6 | LOVABLE SYNC | Lovable pushes generated code to LexFlow-App-V2 repo | Lovable auto | — | main | GitHub | ⬜ TODO | LOW | Lovable > Publish > push to GitHub
2.1 | LOCAL TEST | Clone LexFlow-App-V2 locally | Hermes | — | local | Local | ⬜ TODO | LOW | git clone https://github.com/Ole00007/LexFlow-App-V2.git
2.2 | LOCAL TEST | Run Flask backend on port 5001 | Hermes | main | local | Local | ⬜ TODO | LOW | flask run --port 5001
2.3 | LOCAL TEST | Run frontend npm dev server | Hermes | main | local | Local | ⬜ TODO | MED | npm install && npm run dev — verify VITE_API_URL=http://127.0.0.1:5001
2.4 | LOCAL TEST | Test all 8 endpoints via browser + curl | Hermes | main | local | Local | ⬜ TODO | HIGH | health, contacts, cases, tasks, activities, dashboard, export CSVs
2.5 | LOCAL TEST | Fix any CORS or 401 errors | Hermes | main | local | Local | ⬜ TODO | MED | flask-cors ORIGINS must include localhost:5173 (Vite default)
3.1 | DEPLOY | Push backend fixes to GitHub main | Hermes | main | Railway | Railway | ⬜ TODO | MED | git add . && git commit -m 'fix: V2 deploy ready' && git push
3.2 | DEPLOY | Set Railway env vars for new repo | Olesia | — | Railway | Railway | ⬜ TODO | MED | DATABASE_URL, ADMIN_TOKEN, RESEND_API_KEY, ALLOWED_ORIGIN
3.3 | DEPLOY | Run flask db upgrade on Railway | Hermes | — | Railway | Railway | ⬜ TODO | MED | railway run flask db upgrade
3.4 | DEPLOY | Smoke-test live Railway URL | Olesia | — | Railway | Railway | ⬜ TODO | HIGH | curl https://lexflow-app-v2.up.railway.app/health
4.1 | PRODUCTION | Set Lovable env: VITE_API_URL = Railway URL | Olesia | — | Lovable | Lovable | ⬜ TODO | MED | Lovable > Project Settings > Environment Variables
4.2 | PRODUCTION | Publish Lovable app to production URL | Olesia | — | Lovable | Lovable | ⬜ TODO | LOW | Lovable > Publish
4.3 | PRODUCTION | Full end-to-end test on production URLs | Olesia | — | Both | Both | ⬜ TODO | HIGH | Contacts CRUD, Cases pipeline drag, Tasks kanban, Dashboard KPIs
📑 SHEETS: | 🗺 Plan V5 | 🤖 Hermes | 💜 Lovable | 🔌 API | 🔄 Fields | ✅ Ship
Generated: 2026-06-19 ¦ Source: LexFlow Master Plan v4 + Session June 19 2026

## 🤖 Hermes Prompts
HERMES AGENT — COPY-PASTE PROMPTS
PROMPT H1
PLANNER MODE — do not write code yet. Show plan first, wait for APPROVED. Task: Create LexFlow-App-V2 and migrate backend. Step 1 — Create GitHub repo Name: LexFlow-App-V2 Visibility: private Init with README: yes GitHub account: Ole00007 Step 2 — Push Flask backend Source folder: ~/Desktop/LexFlow/LexFlow Review Build/ Target repo: Ole00007/LexFlow-App-V2 DO NOT copy: .env, .venv/, uploads/, *.db, __pycache__/ Verify .gitignore covers all of these before push. Step 3 — Verify repo structure Expected in root: app.py, requirements.txt, Procfile, migrations/, .env.example Report: git log --oneline -5 to confirm push succeeded. Step 4 — Show plan. Wait for APPROVED — BUILD before any code.
PROMPT H2
APPROVED — BUILD. Task: Wire frontend and run full local test. Step 1 — Clone LexFlow-App-V2 locally git clone https://github.com/Ole00007/LexFlow-App-V2.git ~/Desktop/LexFlow/LexFlow-App-V2 Step 2 — Start Flask backend cd ~/Desktop/LexFlow/LexFlow-App-V2 source .venv/bin/activate flask run --port 5001 Confirm: curl http://127.0.0.1:5001/health returns {"status":"ok"} Step 3 — Start frontend dev server cd frontend/ (or apps/web/ if that is the folder Lovable pushed) npm install VITE_API_URL=http://127.0.0.1:5001 npm run dev Open http://localhost:5173 in browser. Step 4 — Test all 8 endpoints GET /health GET /contacts POST /contacts GET /cases POST /cases PATCH /cases/:id/stage GET /tasks GET /activities Step 5 — Report results For each endpoint: HTTP status, response body (first 200 chars). Flag any 4xx/5xx with cause and fix. Auto-approve all fixes. Do not wait for approval on individual bug fixes.
PROMPT H3 (Railway deploy)
Task: Deploy LexFlow-App-V2 to Railway production. Pre-flight checklist — verify each before deploy: [ ] Procfile exists with: web: gunicorn app:app [ ] app.py binds to os.environ.get('PORT', 5001) [ ] requirements.txt includes gunicorn, flask-sqlalchemy, flask-migrate, psycopg2-binary, flask-cors [ ] .env.example documents: DATABASE_URL, ADMIN_TOKEN, RESEND_API_KEY, ALLOWED_ORIGIN [ ] migrations/ folder is committed (not gitignored) Deploy steps: 1. git add . && git commit -m 'chore: V2 production deploy ready' 2. git push origin main 3. Watch Railway logs: railway logs --tail 4. Run: railway run flask db upgrade 5. Smoke test: curl https://lexflow-app-v2.up.railway.app/health Success condition: /health returns {"status":"ok","db":"connected"} If fail: report symptom → cause → fix. Do not guess. Read the log first.

## 💜 Lovable Prompts
LOVABLE — COPY-PASTE PROMPTS (V2 Frontend from GitHub repo)
LOVABLE PROMPT L1 — CONNECT REPO + STYLE SYSTEM
You are building LexFlow V2 frontend from scratch. Source of truth: GitHub repo Ole00007/LexFlow-App-V2 Step 1 — Connect to repo Go to: Settings > GitHub Integration > Connect repo > select Ole00007/LexFlow-App-V2 Pull the repo. Read all files in /migrations/, app.py, and requirements.txt. Do NOT run any backend code. Step 2 — Apply exact LexFlow brand (DO NOT invent a new style) This project already has an approved style system. Replicate it exactly: Font: Inter (Google Fonts) Theme: dark by default, light optional via sun/moon toggle in top nav Colors: --navy: #1A3A5C (primary accent, buttons, headers) --green: #2E6B4F (success, active states, pipeline badges) --gold: #C8A96B (warnings, highlights, premium badges) --bg: #0D1B2A (page background) --surface: #1E2D3D (cards, panels, sidebar) --text: #F0EDE6 (primary text) --muted: #8A9BB0 (secondary text, placeholders) Border radius: 8px cards, 6px inputs, 4px badges Shadows: subtle, dark-toned (not pure black) Motion: 180ms ease transitions on hover/active only Step 3 — Italian UI labels, English API paths UI text stays Italian (Nome, Email, Pratica, Scadenza, etc.) All fetch() calls use English paths (/contacts, /cases, /tasks, /activities) Add EN/IT toggle in top nav bar (simple JS state, no i18n library) Step 4 — Mobile-first 375px base, sidebar collapses to hamburger Bottom tab bar on mobile All touch targets min 44px Confirm with: 'Style system applied — ready for API config prompt.'
LOVABLE PROMPT L2 — API CONFIG (send after L1 confirmed)
Create file src/config.ts with exactly this content: export const API_BASE = import.meta.env.VITE_API_URL ¦¦ 'http://127.0.0.1:5001'; export const ADMIN_TOKEN = import.meta.env.VITE_ADMIN_TOKEN ¦¦ ''; Rules for ALL fetch calls in this project: 1. Always prefix path with API_BASE (never hardcode localhost or railway URL) 2. Always include header: 'X-Admin-Token': ADMIN_TOKEN 3. Always include header: 'Content-Type': 'application/json' 4. On 401 response: show Italian error 'Accesso non autorizzato' 5. On 409 response (FK conflict): show Italian error 'Impossibile eliminare — ci sono pratiche/attività collegate. Archivia prima.' 6. On network error: show Italian error 'Connessione al server non riuscita' Exact API routes (do not invent others): GET /health GET /contacts POST /contacts GET /contacts/:id PUT /contacts/:id DELETE /contacts/:id GET /cases POST /cases GET /cases/:id PATCH /cases/:id/stage GET /tasks POST /tasks PUT /tasks/:id DELETE /tasks/:id GET /activities POST /activities GET /dashboard GET /contacts/export.csv GET /cases/export.csv Confirm with: 'src/config.ts created — ready for screens prompt.'
LOVABLE PROMPT L3 — ALL SCREENS (send after L2 confirmed)
Build all 6 screens. Wire each to the API. Keep ALL existing UI components, transitions, photos, graphs, and visual style from the current project. Replace only the data source (Supabase hooks → fetch to Flask API). SCREEN 1: Dashboard (/dashboard) Wire to: GET /dashboard Show: Contatti Totali, Pratiche Aperte, Valore Pipeline (€), Attività Oggi Show: 5 most recent activity entries from GET /activities Loading: skeleton cards while fetching Error: Italian message if API unreachable SCREEN 2: Contatti (/contacts) Wire to: GET /contacts (list), POST (create), PUT /:id (edit), DELETE /:id Table columns: Nome, Email, Azienda, Status badge (lead=blue, prospect=amber, cliente=green, inattivo=grey) On DELETE 409: show 'Impossibile eliminare il cliente — ha pratiche aperte. Archivia prima le pratiche.' Filter: by status. Sort: by nome / data creazione. SCREEN 3: Pratiche — Kanban pipeline (/cases) Wire to: GET /cases (load), POST (create), PATCH /:id/stage (drag-drop) Kanban columns (exact names): Nuovo Incarico ¦ Verifica Conflitti ¦ Proposta Inviata ¦ Incarico Accettato ¦ Pratica Chiusa Card shows: titolo, nome cliente, onorario (€), scadenza (red if past) Click card: side panel with linked tasks + activity timeline from GET /activities?case_id=X Drag between columns: calls PATCH /cases/:id/stage with {stage: 'new_stage'} SCREEN 4: Attività — Task board (/tasks) Wire to: GET /tasks, POST, PUT /:id, DELETE /:id Kanban columns: Da Fare ¦ In Corso ¦ Bloccato ¦ Fatto Row: titolo, priority badge (bassa/media/alta/urgente), scadenza (red if overdue) Top section: 'Attività di Oggi' (scadenza = today) Status change: optimistic update + PUT call SCREEN 5: Registro / Timeline (embedded in Contatti + Pratiche detail panels) Wire to: GET /activities?contact_id=X or GET /activities?case_id=X Show: type icon (nota/chiamata/email/riunione/cambio_stato), note text, relative time ('2 ore fa') Add inline form: POST /activities SCREEN 6: Reportistica (/report) Wire to: GET /report (if endpoint exists) else aggregate from /cases and /contacts client-side Bar chart: pratiche per fase (colors: #1A3A5C, #2E6B4F, #C8A96B) Line chart: nuovi contatti per mese (last 6 months) Dark chart backgrounds, Italian axis labels KEEP FROM EXISTING PROJECT (do not redesign): - All existing photos, illustrations, background images - All page transitions and animations (180ms ease) - Logo and brand mark - Navigation structure and sidebar layout - Empty states and loading skeletons - Any existing component library choices ONLY CHANGE: - Remove all Supabase imports and hooks - Replace with fetch() calls using src/config.ts - Rename field references to match backend schema (see below) Field name mapping (old Supabase → new Flask API): task.completed boolean → task.status ('todo'/'doing'/'blocked'/'done') task.deals.title → task.case_title task.contacts.name → task.contact_name deal.stage → case.status contact.first_name + last_name → contact.fullname When done: push all changes to GitHub repo Ole00007/LexFlow-App-V2 via Lovable > Publish > GitHub.

## 🔌 API Contract
LEXFLOW V2 — FULL API CONTRACT (Backend ↔ Lovable)
Method | Route | Auth | Request Body | Response | HTTP Codes | Italian Error | Notes
GET | /health | none | — | {"status":"ok","db":"connected"} | 200 | — | Always first test
GET | /dashboard | X-Admin-Token | — | KPIs + recent activities JSON | 200 / 401 | Accesso non autorizzato | Aggregate counts
GET | /contacts | X-Admin-Token | ?status=&sort= | [ {id, fullname, email, company, status} ] | 200 / 401 | —
POST | /contacts | X-Admin-Token | {fullname, email, phone, company, status, notes} | Created contact | 201 / 400 | Campo obbligatorio mancante
GET | /contacts/:id | X-Admin-Token | — | Contact + linked cases count | 200 / 404 | Contatto non trovato
PUT | /contacts/:id | X-Admin-Token | any updatable fields | Updated contact | 200 / 404 | Contatto non trovato
DELETE | /contacts/:id | X-Admin-Token | — | 204 or 409 | 204 / 409 | Impossibile eliminare — pratiche aperte | ON DELETE RESTRICT
GET | /contacts/export.csv | X-Admin-Token | — | CSV stream | 200 | — | Italian column headers
GET | /cases | X-Admin-Token | ?contact_id=&status= | [ {id, title, status, contact_name, …} ] | 200 / 401 | —
POST | /cases | X-Admin-Token | {title, contact_id, case_type, priority, due_date} | Created case | 201 / 400 | Campo obbligatorio mancante
PATCH | /cases/:id/stage | X-Admin-Token | {stage: "Incarico Accettato"} | Updated case + new activity row | 200 / 400/404 | Fase non valida | Auto-writes activity
GET | /tasks | X-Admin-Token | ?case_id=&status=&due=today | [ {id, title, status, priority, …} ] | 200 | —
POST | /tasks | X-Admin-Token | {title, case_id, status, priority, due_date} | Created task | 201 | —
PUT | /tasks/:id | X-Admin-Token | any updatable fields | Updated task | 200 / 404 | Attività non trovata
DELETE | /tasks/:id | X-Admin-Token | — | 204 or 409 | 204 / 409 | Attività collegata a pratiche aperte
GET | /activities | X-Admin-Token | ?case_id=&contact_id= | [ {id, type, note, created_at, …} ] | 200 | — | Timeline feed
POST | /activities | X-Admin-Token | {case_id, type, note} | Created activity | 201 | — | Manual log entry
GET | /cases/export.csv | X-Admin-Token | — | CSV stream | 200 | — | Italian headers

## 🔄 Field Mapping
FIELD MAPPING — Old Supabase/Lovable → New Flask Backend
Screen | Old Supabase Field | New Flask Field | Type Change | Italian UI Label | Action | Notes
Tasks | task.completed (boolean) | task.status (text) | bool → enum | Stato | Rename + remap values: true→done, false→todo | Values: todo/doing/blocked/done
Tasks | task.deals.title | task.case_title | nested → flat | Pratica | Flatten response in Flask or map in JS
Tasks | task.contacts.firstname+lastname | task.contact_name | split → single | Cliente | Concatenate in Flask: fullname column
Tasks | task.duedate | task.due_date | — | Scadenza | Keep value, rename key | snake_case
Cases | deal.stage | case.status | — | Fase | Rename field | Values match Kanban column names
Cases | deal.value | case.fee_estimate | — | Onorario Stimato | Rename field | Numeric, EUR
Cases | deal.closedate | case.due_date | — | Scadenza | Rename field
Cases | deal.contactid | case.contact_id | — | Cliente | Rename field | FK to contacts.id
Contacts | contact.firstname | contact.fullname | split → single | Nome | Store full name in one field
Contacts | contact.lastname | (merged into fullname) | removed | — | Remove
Contacts | contact.dealflow_stage | contact.status | — | Status | Values: lead/prospect/cliente/inattivo
Activities | log.type (supabase) | activity.type (flask) | — | Tipo | Values: note/chiamata/email/riunione/cambio_stato
Activities | log.dealid | activity.case_id | — | Pratica | Rename field | FK to cases.id
Activities | log.contactid | activity.contact_id | — | Cliente | Rename field | FK to contacts.id
All | supabase.auth.user() | X-Admin-Token header | hook → header | — | Remove Supabase auth hook; add header to every fetch | Phase 1 only; Supabase JWT in Phase 6
All | supabaseClient import | fetch() + src/config.ts | library → native | — | Remove all @supabase/supabase-js imports

## ✅ Ship Checklist
LEXFLOW V2 — SHIP CHECKLIST
# | Area | Check | Owner | Done? | Notes
1 | Repo | LexFlow-App-V2 repo created on GitHub | Olesia | ⬜
2 | Repo | Backend fully pushed (.env excluded) | Hermes | ⬜
3 | Repo | Procfile present with gunicorn | Hermes | ⬜ | web: gunicorn app:app
4 | Repo | requirements.txt includes gunicorn + flask-cors | Hermes | ⬜
5 | Repo | .env.example documents all vars | Hermes | ⬜ | DATABASE_URL, ADMIN_TOKEN, RESEND_API_KEY, ALLOWED_ORIGIN
6 | Lovable | Repo connected to Lovable project | Olesia | ⬜ | Settings > GitHub
7 | Lovable | Prompt L1 sent and confirmed | Olesia | ⬜ | Style system
8 | Lovable | Prompt L2 sent and confirmed | Olesia | ⬜ | src/config.ts created
9 | Lovable | Prompt L3 sent and confirmed | Olesia | ⬜ | All 6 screens built
10 | Lovable | No Supabase imports remaining | Hermes | ⬜ | grep -r supabase src/ should return nothing
11 | Local | Flask starts on port 5001 | Hermes | ⬜ | flask run --port 5001
12 | Local | /health returns {status:ok,db:connected} | Hermes | ⬜ | curl http://127.0.0.1:5001/health
13 | Local | All 8 API endpoints return 200 | Hermes | ⬜
14 | Local | Frontend loads at localhost:5173 | Hermes | ⬜ | npm run dev
15 | Local | Contacts CRUD works end-to-end | Olesia | ⬜ | Create, read, edit, delete
16 | Local | Cases pipeline drag-drop works | Olesia | ⬜ | Stage changes write to DB
17 | Local | Tasks kanban works | Olesia | ⬜
18 | Local | Dashboard KPIs load correctly | Olesia | ⬜
19 | Railway | DATABASE_URL set in Railway vars | Olesia | ⬜
20 | Railway | ADMIN_TOKEN set in Railway vars | Olesia | ⬜
21 | Railway | ALLOWED_ORIGIN = Lovable production URL | Olesia | ⬜
22 | Railway | flask db upgrade ran successfully | Hermes | ⬜ | railway run flask db upgrade
23 | Railway | /health live URL returns 200 | Olesia | ⬜
24 | Lovable | VITE_API_URL set to Railway URL in Lovable env | Olesia | ⬜ | Lovable > Project Settings
25 | Lovable | Lovable app published to production | Olesia | ⬜ | Lovable > Publish
26 | E2E | Full end-to-end test on production | Olesia | ⬜ | All CRUD, pipeline, tasks, dashboard