## 3-Day Plan
HERMES + LEXFLOW + WMF — 3-DAY EXECUTION PLAN ¦ Jun 21–23, 2026
# | Day / Date | Time Block | Task | Agent / Tool | Status | Priority
DAY 1 — SUNDAY JUN 21
1 | Sun Jun 21 | Morning 09:00–11:00 | Install/verify Hermes Desktop CLI; run hermes setup --portal; confirm Tool Gateway active | operator-installer | ⬜ Todo | 🔴 CRITICAL
2 | Sun Jun 21 | Morning 09:00–11:00 | Run hermes chat — verify CLI responds with Nous models | operator-installer | ⬜ Todo | 🔴 CRITICAL
3 | Sun Jun 21 | Morning 09:00–11:00 | Upload profile/soul/memory/skills MDs for operator-installer | operator-installer | ⬜ Todo | 🔴 CRITICAL
4 | Sun Jun 21 | Morning 11:00–13:00 | Add MCP #1: filesystem — point to /projects; test with file list | operator-installer | ⬜ Todo | 🔴 CRITICAL
5 | Sun Jun 21 | Morning 11:00–13:00 | Add MCP #2: github — add token; test repo read | operator-installer | ⬜ Todo | 🔴 CRITICAL
6 | Sun Jun 21 | Afternoon 14:00–16:00 | Add MCP #3: postgres — connect LexFlow DB; test schema query | operator-installer / lexflow-builder | ⬜ Todo | 🔴 CRITICAL
7 | Sun Jun 21 | Afternoon 14:00–16:00 | Create lexflow-builder profile; upload its 4 MDs | operator-installer | ⬜ Todo | 🔴 CRITICAL
8 | Sun Jun 21 | Afternoon 14:00–16:00 | Run hermes gateway setup → Telegram; get BotFather token; test round-trip | telegram-utility | ⬜ Todo | 🔴 CRITICAL
9 | Sun Jun 21 | Afternoon 16:00–18:00 | Create telegram-utility profile; upload 4 MDs | operator-installer | ⬜ Todo | 🟡 HIGH
10 | Sun Jun 21 | Afternoon 16:00–18:00 | Create agency-growth profile; upload 4 MDs | operator-installer | ⬜ Todo | 🟡 HIGH
11 | Sun Jun 21 | Evening 18:00–20:00 | Start Alona Krot site audit (playwright MCP); draft SEO/AEO brief outline | agency-growth | ⬜ Todo | 🟡 HIGH
12 | Sun Jun 21 | Evening 18:00–20:00 | Add MCP #4: playwright; test browser action | operator-installer | ⬜ Todo | 🟡 HIGH
DAY 2 — MONDAY JUN 22
13 | Mon Jun 22 | Morning 09:00–11:00 | LexFlow CRM module: design schema — contacts, companies, pipeline stages, activities | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
14 | Mon Jun 22 | Morning 09:00–11:00 | LexFlow CRM module: write migrations and Flask routes | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
15 | Mon Jun 22 | Morning 11:00–13:00 | LexFlow task manager: schema — tasks, assignments, due dates, status | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
16 | Mon Jun 22 | Morning 11:00–13:00 | LexFlow task manager: Flask routes + React components | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
17 | Mon Jun 22 | Afternoon 14:00–16:00 | LexFlow email automation: template schema, trigger rules, sequence logic | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
18 | Mon Jun 22 | Afternoon 14:00–16:00 | Add MCP #5: agentmail or resend; test email send | operator-installer | ⬜ Todo | 🟡 HIGH
19 | Mon Jun 22 | Afternoon 14:00–16:00 | Create sales-crm profile; upload 4 MDs | operator-installer | ⬜ Todo | 🟡 HIGH
20 | Mon Jun 22 | Afternoon 16:00–18:00 | LexFlow React frontend: CRM view + task view + email view wire-up | lexflow-builder | ⬜ Todo | 🟡 HIGH
21 | Mon Jun 22 | Afternoon 16:00–18:00 | Create content-creator profile; upload 4 MDs | operator-installer | ⬜ Todo | 🟢 MED
22 | Mon Jun 22 | Evening 18:00–20:00 | Add MCP #6: Google Workspace (OAuth); test Gmail + Calendar | operator-installer | ⬜ Todo | 🟢 MED
23 | Mon Jun 22 | Evening 18:00–20:00 | Create personal-assistant profile; upload 4 MDs | operator-installer | ⬜ Todo | 🟢 MED
24 | Mon Jun 22 | Evening 18:00–20:00 | Alona Krot SEO: complete audit; draft entity map + FAQ brief | agency-growth | ⬜ Todo | 🟡 HIGH
DAY 3 — TUESDAY JUN 23
25 | Tue Jun 23 | Morning 09:00–11:00 | LexFlow integration test: CRM + tasks + email end-to-end | lexflow-builder | ⬜ Todo | 🔴 CRITICAL
26 | Tue Jun 23 | Morning 09:00–11:00 | Deploy LexFlow staging to Railway; verify environment | lexflow-builder / operator-installer | ⬜ Todo | 🔴 CRITICAL
27 | Tue Jun 23 | Morning 11:00–13:00 | Create customer-relationship-manager, marketing-analyst, ads-expert profiles | operator-installer | ⬜ Todo | 🟡 HIGH
28 | Tue Jun 23 | Morning 11:00–13:00 | Create librarian, memory-curator profiles; run first memory consolidation | operator-installer / memory-curator | ⬜ Todo | 🟡 HIGH
29 | Tue Jun 23 | Afternoon 14:00–16:00 | Set up cron jobs: daily marketing brief 07:00, memory review Sunday 08:00 | operator-installer / marketing-analyst | ⬜ Todo | 🟢 MED
30 | Tue Jun 23 | Afternoon 14:00–16:00 | Telegram bot final test: route a LexFlow task, a reminder, and an SEO question | telegram-utility | ⬜ Todo | 🔴 CRITICAL
31 | Tue Jun 23 | Afternoon 14:00–16:00 | Prepare WMF demo: screen recording / live demo of Hermes + LexFlow + Telegram | content-creator | ⬜ Todo | 🔴 CRITICAL
32 | Tue Jun 23 | Afternoon 16:00–18:00 | Prepare WMF pitch: 5-slide deck + one-pager | content-creator / lexflow-builder | ⬜ Todo | 🔴 CRITICAL
33 | Tue Jun 23 | Afternoon 16:00–18:00 | Schedule Jun 24 LinkedIn + Instagram post (Hermes demo or LexFlow teaser) | content-creator | ⬜ Todo | 🟡 HIGH
34 | Tue Jun 23 | Evening 18:00–20:00 | Backup all Hermes configs, MDs, and memory files | operator-installer | ⬜ Todo | 🟡 HIGH
35 | Tue Jun 23 | Evening 18:00–20:00 | Pack for conference: printed one-pager, phone charger, demo URL, BotFather link | personal-assistant | ⬜ Todo | 🟡 HIGH
WMF CONFERENCE — JUN 24–26
36 | Wed Jun 24 | All day | AI Global Summit: attend key AI / legal-tech / SaaS sessions; note contacts | personal-assistant | ⬜ Todo | 🔴 CRITICAL
37 | Wed Jun 24 | All day | Demo Hermes workspace live to contacts; collect leads via Telegram bot | telegram-utility | ⬜ Todo | 🔴 CRITICAL
38 | Thu Jun 25 | All day | VC & Open Innovation Fest / World Startup Fest — pitch LexFlow to investors | personal-assistant | ⬜ Todo | 🔴 CRITICAL
39 | Thu Jun 25 | All day | Agency growth conversations — offer free SEO audit using agency-growth workflow | agency-growth | ⬜ Todo | 🟡 HIGH
40 | Fri Jun 26 | All day | Follow-up outreach drafted by sales-crm while at conference; post recap content | sales-crm / content-creator | ⬜ Todo | 🟡 HIGH

## Agent Registry
HERMES AGENT REGISTRY — 12 SPECIALIST AGENTS
Agent | Purpose | Key Skills | MCP Tools | Gateway / Channel | Create Day | Priority | Status
operator-installer | Creates/installs all agents, MCPs, gateways; routing, guardrails, observability | setup-sequencer, agent-factory, mcp-rollout, cost-guardrails | ALL (audit) | CLI / Desktop | Day 1 | 🔴 FIRST | ⬜ Todo
lexflow-builder | Builds LexFlow SaaS: CRM, task mgr, email automation, code, deploy, websites | feature-spec-writer, crm-module-design, deployment-checklist | filesystem, github, postgres, playwright | CLI / Desktop | Day 1 | 🔴 CRITICAL | ⬜ Todo
telegram-utility | Telegram bot: quick replies, routing, reminders, status checks | quick-reply, routing-dispatch, reminder-capture | telegram | Telegram gateway | Day 1 | 🔴 CRITICAL | ⬜ Todo
agency-growth | SEO/AEO, content ops, Alona Krot + client website improvements | seo-aeo-briefing, site-audit, competitor-analysis | playwright, filesystem, google-workspace | CLI / operator | Day 1 | 🟡 HIGH | ⬜ Todo
sales-crm | Lead triage, outreach drafts, CRM hygiene, email automation | lead-qualifier, outreach-draft-builder, email-automation-designer | postgres, agentmail, filesystem | CLI / email gateway | Day 2 | 🟡 HIGH | ⬜ Todo
content-creator | Blog posts, landing copy, hooks, captions, reels scripts, newsletters | blog-post-writer, hooks-and-captions, reel-script-writer | filesystem, google-workspace, canva-mcp | CLI / Telegram | Day 2 | 🟡 HIGH | ⬜ Todo
customer-rel-manager | Answers DMs and messages across Telegram, WhatsApp, Insta, email | inbound-triage, approved-reply-drafter, escalation-router | telegram, agentmail, postgres | All social gateways | Day 3 | 🟡 HIGH | ⬜ Todo
marketing-analyst | Daily competitor research, market trends, news briefings | daily-news-briefing, competitor-tracker, trend-scanner | playwright, perplexity, filesystem | Cron / Telegram | Day 3 | 🟢 MED | ⬜ Todo
ads-expert | Google Ads + Meta Ads: copy, structure, targeting, performance | google-ads-copy, meta-ads-brief, ab-test-copy-variants | google-ads-mcp, meta-mcp, filesystem | CLI / Telegram | Day 3 | 🟢 MED | ⬜ Todo
personal-assistant | Calendar, reminders, travel logistics, daily admin (biz + personal) | calendar-manager, reminder-system, travel-logistics | google-workspace, telegram | Telegram / Gmail | Day 3 | 🟢 MED | ⬜ Todo
librarian | File taxonomy, SOPs, knowledge retrieval across Notion/Drive/filesystem | file-taxonomy-designer, sop-writer, knowledge-retrieval | filesystem, notion-mcp, google-workspace | CLI / Telegram | Day 3 | 🟢 MED | ⬜ Todo
memory-curator | Memory cleanup, prompt extraction, skill hardening, profile hygiene | memory-deduper, prompt-extractor, skill-promoter | ALL profiles (read) | CLI only | Day 3 | 🟢 MED | ⬜ Todo

## WMF Conference
WMF 2026 — BolognaFiere Jun 24–26 ¦ 73,000+ attendees, 3,000+ startups & investors
Day | Goal | What to Demo / Say | Target Person/Event | Action
Jun 24 | Get visible — find collaborators | Live Hermes agent demo: Telegram bot routing a task in real time | AI Global Summit talks; AI-native devs and builders | Collect LinkedIn; invite to try Telegram bot
Jun 24 | Community and network | Show LexFlow staging: CRM + task manager working | Legal-tech adjacent founders and devs | Exchange contacts; schedule follow-up call
Jun 25 | Find investors | LexFlow 60-sec pitch: problem / solution / traction / ask | VC & Open Innovation Fest; World Startup Fest EIT roundtable | Get investor intro or application link
Jun 25 | Find customers | Free SEO/AEO audit offer using agency-growth workflow | SME founders, marketing leads, legal firms | Book discovery call; collect email
Jun 25 | Part-time job / partnership | Hermes multi-agent architecture demo — shows orchestration skill | AI-native startups, dev agencies, product studios | Ask about fractional CTO, product, or BD role
Jun 26 | Follow up and convert | Post live demo reel from conference | All contacts met Jun 24–25 | sales-crm drafts follow-ups; content-creator posts recap
PRE-DEPARTURE CHECKLIST (complete by Jun 23 evening)
☐ LexFlow MVP staging deployed to Railway
☐ Telegram bot live and demo-ready
☐ Hermes workspace: 3+ agents running
☐ 5-slide deck prepared (PDF on phone + printed)
☐ One-pager printed (10 copies)
☐ Short demo video / screen recording (offline backup)
☐ LinkedIn updated: LexFlow + Hermes agency positioning
☐ Instagram post/reel scheduled for Jun 24 09:00
☐ Phone charged; backup charger packed
☐ BotFather bot link ready to share on the spot

## MCP Rollout
MCP SERVER ROLLOUT — Add one at a time. Test. Then add the next.
# | Server | Purpose + Key Tools | Assign to Agents | Add Day | Status
1 | filesystem | Read/write project files. Key: list_files, read_file, write_file | lexflow-builder, agency-growth, librarian, content-creator | Day 1 | ⬜ Todo
2 | github | Repo management. Key: read issues, commits, PRs, CI status | lexflow-builder, operator-installer (audit) | Day 1 | ⬜ Todo
3 | postgres | LexFlow DB. Key: schema queries, migrations, CRM/task reads | lexflow-builder, sales-crm, customer-rel-manager | Day 1 | ⬜ Todo
4 | playwright | Browser automation. Key: site audit, scraping, UI testing | agency-growth, lexflow-builder, marketing-analyst | Day 1 | ⬜ Todo
5 | telegram | Telegram bot. Key: send_message, receive_update, set_webhook | telegram-utility, customer-rel-manager | Day 1 | ⬜ Todo
6 | agentmail / resend | Email automation. Key: send_email, list_templates, trigger_sequence | sales-crm, customer-rel-manager | Day 2 | ⬜ Todo
7 | google-workspace | Gmail + Calendar + Drive + Docs. Key: send_email, create_event, upload_doc | personal-assistant, agency-growth, content-creator, librarian | Day 2 | ⬜ Todo
8 | perplexity | AI research. Key: search, summarise, fact-check | marketing-analyst, agency-growth | Day 2 | ⬜ Todo
9 | notion | Knowledge base. Key: create_page, search_pages, update_database | librarian, agency-growth | Day 3 | ⬜ Todo
10 | cloudflare | DNS, pages, workers. Key: list_zones, create_page, purge_cache | lexflow-builder, operator-installer | Day 3 | ⬜ Todo
11 | openrouter | Model routing overflow. Key: chat completion with any model | operator-installer (overflow only) | Day 3 | ⬜ Todo
12 | google-ads-mcp | Google Ads management. Key: list_campaigns, create_ad, get_report | ads-expert | Post-WMF | ⬜ Todo
13 | meta-mcp | Meta Business Ads. Key: list_campaigns, create_ad, get_insights | ads-expert, customer-rel-manager | Post-WMF | ⬜ Todo
14 | instagram-mcp | Instagram DMs and posts (custom adapter) | customer-rel-manager, content-creator | Post-WMF | ⬜ Todo
15 | canva-mcp | Design exports, templates (when plugin available) | content-creator, ads-expert | Post-WMF | ⬜ Todo

## Gateway Setup
GATEWAY SETUP — Step-by-Step ¦ Chat surfaces use gateway; tools use MCP
# | Platform | Steps | Prerequisites | Setup Command | Priority
1 | Telegram | 1. Get bot token from @BotFather 2. hermes gateway setup → pick Telegram 3. Enter token + allowed user IDs 4. hermes gateway start 5. Test with /start | Telegram account, BotFather access | hermes gateway setup | 🔴 FIRST
2 | WhatsApp | 1. hermes gateway setup → pick WhatsApp 2. Follow guided walk-through (no Meta dev account needed for personal) 3. Scan QR code to link number 4. hermes gateway start | WhatsApp account | hermes gateway setup | 🟡 Day 2
3 | WhatsApp Business Cloud API | 1. Meta dev account + Business verification 2. Create WhatsApp Business App 3. Get public HTTPS webhook URL (use ngrok or Railway) 4. Configure webhook in Meta dashboard 5. hermes gateway setup → WhatsApp Business Cloud | Meta developer account, public HTTPS URL | hermes gateway setup | 🟢 Post-WMF
4 | Email (Gmail) | 1. hermes gateway setup → Email 2. Use Google Workspace OAuth OR app password 3. Configure SMTP/IMAP settings 4. Test inbound + outbound | Gmail account, Google Workspace OAuth creds | hermes gateway setup | 🟡 Day 2
5 | Discord | 1. Create Discord bot in Developer Portal 2. Get bot token and server ID 3. hermes gateway setup → Discord 4. Enter token + guild ID | Discord account, Developer Portal access | hermes gateway setup | 🟢 Post-WMF
6 | Google Workspace (Gmail/Drive/Cal) | 1. Create Google Cloud project 2. Enable Gmail, Calendar, Drive, Sheets, Docs APIs 3. Create OAuth 2.0 Desktop credentials 4. hermes → install google-workspace skill 5. Run OAuth flow, authorize scopes | Google Cloud account, OAuth 2.0 credentials | Hermes skill install | 🟡 Day 2
7 | Instagram DM | Native Hermes adapter not confirmed. 1. Use Meta Business Suite API (requires business account) 2. Build or use instagram-mcp custom server 3. Assign to customer-rel-manager agent only | Meta Business account, custom MCP server | Custom adapter or MCP | 🟢 Post-WMF
8 | Meta Business / Google Business | Not a native Hermes gateway platform. 1. Use Meta Marketing API via meta-mcp 2. Connect via ads-expert agent 3. Assign permissions per agent scope | Meta Business / Google Ads account | MCP server | 🟢 Post-WMF
9 | Notion | Not a gateway platform — use MCP. 1. Get Notion API key + integration 2. Add notion-mcp to config.yaml 3. Assign to librarian + agency-growth | Notion account, API key | MCP server | 🟢 Day 3
10 | Railway / Netlify | Not a gateway — use MCP or CLI. 1. Use Railway CLI / Netlify CLI 2. Wrap as MCP server or call directly from lexflow-builder 3. Require operator approval for deploys | Railway / Netlify account + CLI token | MCP or CLI | 🟢 Day 3