## Today_Action_Plan
Time Slot | Action
09:00-09:30 | Run Prompt 1 (Installer): verify/install Hermes skills
09:30-10:00 | Run Prompt 2: connect GSC to alenakrot.com
10:00-10:15 | Run Prompt 3: connect ChatSEO free tier, test query
10:15-10:45 | Run Prompt 4: resolve Flazio access issue (parallel, may need Alena's input)
10:45-11:30 | Run Prompts 5a/5b: pull GSC indexing, CWV, query gaps
11:30-12:00 | Run Prompt 6: ChatSEO diagnosis on flagged queries
12:00-13:00 | Run Prompt 7: build entity/topical cluster map
14:00-15:00 | Run Prompt 8: on-page technical audit
15:00-15:30 | Run Prompts 9a/9b: set up weekly + monthly CRON jobs
15:30-16:30 | Run Prompts 10a/10b: configure SEO Swarm roles + cost/traction tracking
16:30-17:00 | Review outputs, log first entries in Cost_Traction_Log

## Agent_Task_Matrix
Step | Agent | Phase | Task | Timing | Dependency
1 | Installer (Hermes) | Setup | Bootstrap Hermes agent, install missing skills/tools, verify environment | Today AM | None
2 | Installer (Hermes) | Setup | Connect Google Search Console API + OAuth for alenakrot.com | Today AM | GSC verified on site
3 | Installer (Hermes) | Setup | Connect ChatSEO (free tier) via GSC login, test query | Today AM | GSC connected
4 | Installer (Hermes) | Setup | Resolve Flazio admin access issue (ownership transfer) | Today AM | Alena/Flazio support
5 | GSC Analyst (Hermes) | Data | Pull indexing status, top queries, CWV report | Today PM | Task 2 done
6 | ChatSEO Analyst (Hermes) | Data | Ask natural-language questions only for gaps GSC can't answer (e.g. content quality diagnosis) | Today PM | Task 3 done
7 | Content Strategist (Hermes) | Content | Build entity map + topical clusters from GSC queries | Today PM | Task 5 done
8 | Technical Auditor (Hermes) | Technical | Run on-page technical checklist against alenakrot.com | Today PM | Flazio access or manual crawl
9 | Scheduler (Hermes) | Automation | Create CRON jobs for weekly GSC pull + monthly full audit | Today PM | Tasks 5-8 done
10 | Swarm Orchestrator (Hermes) | Automation | Configure SEO Swarm: Researcher + Auditor + Writer + Verifier roles | This week | Tasks 1-9 done

## Prompts_Library
Agent/Phase | Step Ref | Prompt Name | Prompt Text
Installer Setup | 1 | Verify Hermes install and skills | Check my Hermes agent installation. List installed skills. If missing, install: web-research, seo-audit, seo-writing, seo-content-optimizer, execution-planning. Report status as a checklist.
Installer Setup | 2 | Connect GSC | Set up an authenticated connection to Google Search Console for property alenakrot.com (or https://alenakrot.com/home). Confirm scopes: Search Analytics read, Sitemaps read, URL Inspection. Report connection status.
Installer Setup | 3 | Connect ChatSEO | Connect ChatSEO free tier using the same Google account authorized on GSC for alenakrot.com. Run a first test query: '@gsc top 10 pages last 28 days'. Report the output and confirm the integration works.
Installer Setup | 4 | Flazio access troubleshooting | I was granted admin access to alenakrot.com on Flazio via email from krot_elena@icloud.com but I only see templates, not the site management gear icon. List step-by-step troubleshooting actions: correct login method, account matching, contacting Flazio support, and what info to request from Alena to confirm the invite was sent to the right account.
GSC Analyst | 5a | Indexing & CWV pull | @gsc Pull current indexing status for alenakrot.com: total indexed pages, excluded pages with reasons, Core Web Vitals summary (mobile), and top 20 queries by impressions in the last 28 days. Output as a table.
GSC Analyst | 5b | Query gap detection | @gsc List queries where alenakrot.com has impressions but average position worse than 10, sorted by impressions descending. Flag any related to Genova, Ventimiglia, or Palermo treatments.
ChatSEO Analyst | 6 | Content diagnosis (GSC gap) | @gsc data shows [paste query list]. For queries GSC can't explain (e.g. why CTR is low despite good position), analyze likely on-page/content reasons and suggest fixes for each page.
Content Strategist | 7 | Entity & cluster map | Using the GSC query export, group all queries into topical clusters (by treatment type and city: Genova, Ventimiglia, Palermo). For each cluster, list: primary keyword, 3-5 supporting keywords, existing page (if any), and one new page to create.
Technical Auditor | 8 | On-page technical audit | Crawl alenakrot.com/home and key subpages. Check: title tags, meta descriptions, H1 structure, image alt text, internal links, sitemap presence, robots.txt, HTTPS, mobile usability. Output as a prioritized issue list with severity.
Scheduler | 9a | Weekly GSC CRON job | Create a CRON job that runs every Monday 8:00 AM: pull last 7 days GSC data (clicks, impressions, avg position, new queries), compare to prior week, and post a summary comment with 3 action items.
Scheduler | 9b | Monthly full audit CRON job | Create a CRON job that runs on the 1st of each month: run full technical + content audit combining GSC and ChatSEO data, output as the standard HTML audit template, and log tool usage/cost for the month.
Swarm Orchestrator | 10a | Define SEO Swarm roles | Set up an SEO Swarm with 4 roles: Researcher (pulls GSC/ChatSEO data), Auditor (checks technical/content quality and flags issues), Writer (drafts new pages/briefs from approved clusters), Verifier (checks Writer output against SEO checklist before marking done). Define handoff order and require Verifier approval before publishing.
Swarm Orchestrator | 10b | Cost & traction tracking | For every tool used (GSC, ChatSEO, future Serpstat), log per task: tool used, task type, time saved estimate, and any cost. Aggregate weekly into a cost-vs-traffic-impact table linking tool usage to ranking/traffic changes.

## Tool_Routing_Rules
Need/Question Type | Tool to Use | Why
Indexing status | GSC | Native, free, authoritative source
Query/impressions/CTR/position data | GSC | Native, free, authoritative source
Core Web Vitals (field data) | GSC | Native report available
Sitemap & crawl errors | GSC | Native report available
Natural-language diagnosis of WHY a page underperforms | ChatSEO | GSC has no reasoning layer; ChatSEO interprets GSC data conversationally
Content quality / on-page gap explanation | ChatSEO | Adds analysis GSC can't provide natively
Competitor keyword/backlink data | Serpstat (future) | Not covered by GSC or ChatSEO; add when budget allows
SERP feature / ranking volatility tracking | Serpstat (future) | Not covered by GSC (GSC only shows own site)

## MultiLLM_Architecture
Layer | Component | Role
Orchestrator | Hermes (self-hosted) | Routes tasks to sub-agents, manages memory, triggers CRON jobs
Data Layer 1 | Google Search Console API | Free, first-priority source for all on-site performance data
Data Layer 2 | ChatSEO (free tier) | Used only for gaps GSC can't answer; conversational analysis layer
Data Layer 3 (future) | Serpstat API | Add when competitor/backlink/SERP-feature data is needed
Reasoning Layer | Perplexity PRO | Used for research, synthesis, cross-checking, and report writing
Execution Sub-Agents | Hermes Swarm: Researcher, Auditor, Writer, Verifier | Each with scoped skill sets and approval gates
Automation Layer | CRON jobs inside Hermes | Weekly GSC pulls, monthly full audits, cost/traction logging
Logging/Tracking | Shared cost & traction log (this workbook, Sheet: Cost_Traction_Log) | Tracks tool, task, cost, time saved, and traffic/ranking impact

## Cost_Traction_Log
Date | Tool Used | Task Type | Page/Cluster Affected | Cost (EUR) | Time Saved (est. min) | Ranking Before | Ranking After | Traffic Before | Traffic After | Notes