## Action Plan
HERMES DEBUG & ACTION PLAN — Jul 12 2026
# | AREA | YESTERDAY (Jul 11) | STATUS | TODAY (Jul 12) | PRIORITY | OWNER
1 | Port conflict | Killed zombie proxy PID 10473 holding port 8642 since Sunday | ✅ DONE | — | — | Terminal
2 | User allowlist | Added TELEGRAM_ALLOWED_USERS=1372207688 to profile env | ✅ DONE | — | — | Terminal
3 | Wrong env file | Moved all fixes to ~/.hermes/profiles/operator-installer/.env | ✅ DONE | — | — | Terminal
4 | Duplicate token | Deduplicated TELEGRAM_BOT_TOKEN entries with awk | ✅ DONE | — | — | Terminal
5 | API Server Key | Added API_SERVER_KEY to profile env | ✅ DONE | — | — | Terminal
6 | Pairing lockout | Cleared _lockout:telegram from rate_limits.json | ✅ DONE | — | — | Terminal
7 | Bot running | Confirmed bot responds in Telegram UI | ✅ DONE | — | — | Verified
8 | Debug file | Created debugging log + uploaded to Hermes memory | ✅ DONE | — | — | Hermes
9 | Final pairing | Bot runs but pairing approval still pending | ✅ DONE | Bot confirmed paired — responds to messages ✅ |  | Terminal
10 | MCP bloat | 30+ unused MCP servers flood logs on every boot | ⚠️ PENDING | Disable unused MCPs | 🟡 MED | Terminal
11 | Gateway launchd | Gateway runs manually only — not loaded via launchd | ⚠️ PENDING | Check: launchctl list ¦ grep hermes — then run: hermes -p operator-installer gateway install-service | 🟡 MED | Terminal
12 | Cron jobs | Morning Telegram briefing not yet configured | ⏳ NEW | Set up 8am daily cron | 🟡 MED | Hermes
13 | Email API | Yahoo/Google API not connected to Hermes | ⏳ NEW | Connect read-only email API | 🟠 MED | Hermes
14 | Email Agent | Read-only agent: summarise + draft + tag | ⏳ NEW | Design prompt + guardrails | 🟢 LOW | Hermes
15 | Content pipeline | Blog drafts → Copywriter agent → Telegram notify | ⏳ NEW | Architecture design only | 🟢 LOW | Hermes
16 | Obsidian/Notion | Agent updates daily log + sends Telegram link | ⏳ NEW | Configure agent task | 🟢 LOW | Hermes

## Diagnosis Blueprint
HERMES GATEWAY — FAST DIAGNOSIS BLUEPRINT
When something breaks, run these checks IN ORDER. Stop at first hit.
STEP | CHECK | COMMAND | WHAT TO LOOK FOR
1 | Gateway status | hermes -p operator-installer gateway status | Is Telegram listed as connected? Is launchd loaded?
2 | Port conflict | sudo lsof -i :8642 | Any PID holding 8642 that is NOT the current gateway?
3 | Zombie process | ps aux ¦ grep hermes | Old 'proxy start' or stale gateway PIDs from previous sessions?
4 | Env file check | grep -v '^#' ~/.hermes/profiles/operator-installer/.env ¦ grep -v '^$' ¦ grep -i telegram | One TELEGRAM_BOT_TOKEN + one TELEGRAM_ALLOWED_USERS. No duplicates.
5 | Pairing list | hermes -p operator-installer pairing list | Any pending codes? If empty after sending /start = gateway not receiving msgs
6 | Live logs | hermes -p operator-installer gateway run | Watch for telegram: connected vs telegram: error
7 | Lockout check | cat ~/.hermes/platforms/pairing/_rate_limits.json | _lockout:telegram present? Delete file to reset.
8 | Launchd check | launchctl list ¦ grep -i hermes | Is ai.hermes.gateway-operator-installer loaded?
FAST FIXES CHEATSHEET:
PROBLEM | FIX
Port in use | kill -9 $(sudo lsof -ti :8642)
Lockout | rm ~/.hermes/platforms/pairing/_rate_limits.json
Duplicate env entries | awk '!seen[$0]++' ~/.hermes/profiles/operator-installer/.env > /tmp/c && mv /tmp/c ~/.hermes/profiles/operator-installer/.env
Gateway not loading | hermes -p operator-installer gateway restart
Pairing code expired | Send /start in Telegram → immediately run pairing list
Wrong profile | Always add -p operator-installer to every hermes command
TOOLS USED IN THIS SESSION:
TOOL | PURPOSE
lsof | Find which process holds a port
ps aux | List all running processes
launchctl | Manage macOS background services
awk | Deduplicate lines in a file
sed | Delete specific lines from a file
grep | Search file contents
kill -9 | Force-kill a process by PID
python3 -c | Run inline Python to edit JSON files
BOT SILENCE DEBUGGING — CAUSE / CHECK / FIX
CAUSE | CHECK / NOTES | FIX
Telegram user ID not whitelisted | Most common cause of total silence — check TELEGRAM_ALLOWED_USERS in .env | Get your ID from @userinfobot in Telegram, add it to TELEGRAM_ALLOWED_USERS in .env
Wrong or revoked bot token | Did you regenerate the token in BotFather after initial setup? | Update TELEGRAM_BOT_TOKEN in .env, restart gateway
Gateway not actually running | hermes -p operator-installer gateway status | hermes -p operator-installer gateway start
Duplicate process polling same bot | Two gateways fighting over one token — check: ps aux ¦ grep hermes | kill -9 <PID of duplicate> — see port conflict fix above (row 16)

## Phases & Roadmap
HERMES AUTOMATION PHASES — ROADMAP
Phase | Name | Task | Tools / Commands | Status
PHASE 1 — Fix & Stabilise (Today — ~30 min)
1.1 | Complete Telegram pairing | Send /start in Telegram → hermes -p operator-installer pairing list → approve code | Terminal + Telegram | ✅ DONE
1.2 | Disable MCP bloat | hermes mcp disable <name> for each unused server (aws, stripe, paypal, figma, canva, cloudflare, atlassian, linear, asana, dune, coingecko, tradingview, thirdweb, solana-agent-kit, davinci-resolve, higgsfield, meigen-ai-design, airtable, the-graph, brave-search, postgres, neon, supabase, gmail, google-calendar) | Terminal | ⚠️ PENDING
1.3 | Fix launchd auto-start | hermes -p operator-installer gateway start (load as launchd service so it survives Mac reboots) | Terminal | ⚠️ PENDING
PHASE 2 — Cron + Morning Briefing (~1 hr)
2.1 | Set up 8am daily Telegram briefing | hermes cron add '0 8 * * *' 'Send daily briefing to Telegram' | Hermes cron + Telegram | ⏳ NEW
2.2 | Define briefing content | Urgent emails + project blockers + deadlines today + weather Genova | Agent prompt | ⏳ NEW
PHASE 3 — Email API Connection (~1 hr)
3.1 | Create Yahoo API key | https://developer.yahoo.com/oauth2/guide/ — OAuth2 read-only scope | Yahoo Developer Console | ⏳ NEW
3.2 | Add to Hermes env | echo 'YAHOO_EMAIL_TOKEN=xxx' >> ~/.hermes/profiles/operator-installer/.env | Terminal | ⏳ NEW
3.3 | Set guardrails | Read + tag + organise + unsubscribe ONLY. No send. No delete without confirm. | Hermes config | ⏳ NEW
PHASE 4 — Email Agent Design (~1 hr)
4.1 | Email Agent permissions | READ: yes ¦ DRAFT: yes ¦ SEND: NO ¦ DELETE: confirm only ¦ FORWARD: NO | Hermes agent prompt | ⏳ NEW
4.2 | Email Agent tasks | Summarise inbox daily ¦ Tag important ¦ Unsubscribe spam ¦ Draft replies ¦ Draft blog posts | Agent prompt | ⏳ NEW
4.3 | Human-in-loop for replies | Draft saved → notify via Telegram: 'Reply drafted for X, check & send manually' | Telegram cron | ⏳ NEW
PHASE 5 — Content Pipeline
5.1 | Email Agent drafts blog posts | From email context for: Alena Krot site, Avibe agency, LexFlow | Email Agent → Notion/Obsidian | ⏳ NEW
5.2 | Copywriter Agent reviews | Iterate + improve draft → mark as ready | Copywriter Agent | ⏳ NEW
5.3 | Publish + notify | Publish to CMS (or queue) → send Telegram link to Olesia | Telegram bot | ⏳ NEW
PHASE 6 — Obsidian/Notion Daily Update
6.1 | Agent reads email + projects | Summarise what is done + what needs Olesia's attention today | Hermes agent | ⏳ NEW
6.2 | Update Notion/Obsidian | Write daily log page with project statuses | Notion/Obsidian API | ⏳ NEW
6.3 | Send Telegram digest | Urgent items only (blockers + risks + sensitive) + link to full Notion page | Telegram bot | ⏳ NEW