## 1. Summary
Hermes Multi-Agent Ops Plan — Cloud, Software Factory, Multi-Provider
Generated for: Olesia ¦ LexFlow + AVibe Agency ¦ Updated Sep 15, 2026 (session 2)
Topic | Verdict | Key Fact | Action Required | Owner
Hermes Cloud billing | Confirmed pay-as-you-go | Billed from Nous credit balance; idle instances can be very cheap per Nous's own comparison | Do not deploy Cloud yet — pilot only after LexFlow+AVibe deploy stable | Olesia
Local vs Cloud efficiency | No independent benchmark exists | Cloud = availability/always-on, not a smarter model | Treat as ops choice, not performance upgrade | Olesia
Software Factory (isolate-build-prove-ship) | Valid, with 1 hard rule | Git blocks 2 worktrees on same branch — one branch per task, always, enforced by pre-flight script | Use safe-worktree-add.sh before every new task | Orchestrator agent
Hardware split | MacBook 8GB is bottleneck | Prior OOM kill (zsh: killed) already occurred on this Mac | Move all parallel/heavy agent work to ASUS 64GB; Mac = orchestration only | Olesia
Multi-provider (Nous Portal + OpenRouter simultaneously) | Confirmed possible | Hermes profiles are fully isolated (own config/creds/memory) | Set explicit provider per profile in config.yaml | Olesia + agents
Nous OAuth shared-token break | Occurred this session — fixed | Known bug: refresh token reuse detected after days of runtime, breaks shared-session profiles | Run auth reset + auth add nous sequence (Sheet 7) | Olesia
Profile distributions (package once, clone to ASUS) | Confirmed feature | distribution.yaml + git repo + 'hermes profile install <url>' | Package current profile as distro before ASUS rollout | Olesia
Merge safety | 5/5 score is not auto-merge | Score = evidence completeness, not permission to merge unattended | Human approval required on every merge, no exceptions | Olesia

## 2. Hardware Plan
Device Roles & RAM Safety Plan
Device | Role | Max concurrent Hermes profiles | Allowed workloads | Forbidden workloads | Risk if violated
MacBook Pro M2, 8GB RAM | Orchestrator / control desk | 1 (2 max, briefly) | Task planning, Obsidian, GitHub PR review, browser check, Hindsight read | Parallel builders, Docker, multiple dev servers, resumed large sessions | High — prior OOM kill already occurred
ASUS Zenbook, 64GB RAM | Builder / tester / reviewer factory | 3 to start; max 6 after 2 stable cycles | Git worktrees, test runners, browsers for visual proof, local dev servers | Storing production secrets long-term unvaulted; unbounded agent count | Medium — monitor Task Manager first week
Railway (Hindsight) | Shared memory bus | N/A (not a workstation) | Cross-device memory sync, approved decision records | Raw session dumps, unreviewed agent chatter, secrets | Medium — config edits redeploy the service

## 3. Factory Workflow
Isolate → Build → Prove → Review → Ship Gates
Gate | Points | Evidence Required | Who Verifies | Fail Action
1. Scoped implementation | 1 | Diff touches only agreed files; matches task brief scope | Reviewer profile | Return to Build
2. Automated checks | 1 | Test/lint/build command output, full pass | Tester profile | Return to Build
3. Functional verification | 1 | Before/after screenshots, video, or response payload; reproducible steps | Tester profile | Return to Prove
4. Regression/security review | 1 | Independent reviewer profile finds no blocking issue | Reviewer profile (different from builder) | Return to Build
5. Delivery readiness | 1 | PR description, rollback note, evidence links attached, no unknowns | Olesia (human) | Hold PR
Rule: Merge to main ONLY at 5/5. A 4/5 returns to the specific failed gate — never merge on partial score.

## 4. Profile Roster
Hermes Profile Roster — Providers, Permissions, Tools
Profile name | Provider | Model tier | Write access | Allowed MCPs (minimal set) | Device | Notes
orchestrator | Nous Portal | Standard Nous model | Read-only + create branches/task briefs | Git (read), filesystem, GitHub (read) | MacBook | Central coordination only
lexflow-builder | OpenRouter | Coding-focused paid model | Write only in assigned worktree | Git, filesystem, test runner | ASUS | Never touches main directly
lexflow-tester | OpenRouter (:free first) | Free/low-cost model | Write test artifacts only | Browser/test tools, filesystem (read) | ASUS | Escalate to paid model only if free model fails
lexflow-reviewer | Nous Portal or strong OpenRouter model | Higher-reasoning model | PR comments only, no code writes | GitHub (read), Git (read) | ASUS or Mac | Must be different session from builder
memory-curator | OpenRouter (:free) | Cheap/small-context model | Writes only to Agent Ops Inbox + Hindsight | Hindsight API, Obsidian staging folder only | ASUS | PENDING TASK this session: audit Obsidian architecture (see Sheet 7)

## 5. Risk Register
Consolidated Risk Register
Risk | Source | Likelihood | Impact | Mitigation | Status
MacBook OOM kill during agent session | Hardware | High | Medium (downtime, no data loss) | Keep Mac to 1 orchestrator session; move heavy work to ASUS | Open
Cloud instance left running unintentionally | Q1 Hermes Cloud | Medium | Low-Medium (cost only) | Stop instance after each scheduled run; track cost separately | Open
Cloud pricing page changes vs quoted figures | Q1 Hermes Cloud | Medium | Low | Re-verify at portal.nousresearch.com/cloud before budgeting | Open
Two worktrees attempt same branch | Q2 Software Factory | Medium | Low (Git blocks it) | safe-worktree-add.sh pre-flight check before every task (Sheet 7) | Mitigated — script added
Builder reviews own PR | Q2 Software Factory | Medium | High (bad code merged) | Reviewer must be separate profile/session, never same agent | Open — enforce in task brief
Agent merges at self-declared 5/5 without human check | Q2 Software Factory | Medium | High (production risk) | Human approval mandatory on every merge; GitHub branch protection | Open — configure GitHub rule
Nous OAuth refresh token reuse detected, locks profiles | Q3 Multi-provider | High (occurred this session) | High (blocked frontend/dev work) | auth reset + auth add nous sequence; re-auth each affected profile individually (Sheet 7) | Fixed this session — monitor for recurrence
Unused MCP servers consuming RAM/CPU via retry loops | Hardware | High (recurring) | Medium | Enable only MCPs required per profile | Recurring — recheck monthly
Client/legal data exposed to generic Cloud or test agents | LexFlow | Low-Medium | High (privacy/compliance) | Use scrubbed sample data only; no real legal docs in test/Cloud | Open
Production Railway env var edited incorrectly | Railway | Low | Medium (service downtime) | Copy current env vars before any edit | Open

## 6. Rollout Timeline
Two-Week Rollout Plan
Phase | Days | Actions | Success Criteria | Go/No-Go Gate
Stabilise | 1-2 | Backup Git bundle on Mac; push baseline to GitHub; clean clone on ASUS; test Hindsight read/write from both devices; fix Nous auth | Clean clone builds and runs on ASUS; Hindsight note visible in Obsidian inbox; all profiles show 'logged in' | Do not proceed if backup, clone, or auth fails
Single worktree test | 3-4 | One narrow non-production LexFlow task; builder -> tester -> reviewer; produce PR, no merge yet | PR created with evidence; RAM/CPU stable on ASUS | Do not scale if any profile crashes or hangs
Three-station run | 5-7 | One builder + one tester + one reviewer in parallel on separate worktrees; serial production tasks only | One clean PR merged manually after 5/5 evidence review | Do not add profiles if merges require repeated rework
Controlled scaling | 8-14 | Trial 4 concurrent roles; package profiles as distributions for ASUS reuse; Mac stays single-session | Two clean 5/5 PRs merged without operational incident | Only then consider Hermes Cloud pilot or CI automation

## 7. Session Fixes
Session Fixes — Auth Repair, Worktree Rule, Distributions, Folder Naming
A. Why '80 Agent Ops' is numbered 80
Item | Explanation
Convention | Johnny Decimal-style numbering: areas in blocks of 10 (00-09, 10-19 ... 80-89, 90-99), each holding up to 10 categories
Why 80 specifically | Arbitrary placement between Projects (10-19) and Archive (90-99), leaving 20-79 free for future PARA areas
Can it change | Yes — renumber freely, e.g. '50 Agent Ops' if you plan more Resource-type areas
B. Nous Portal auth fix — shared refresh token broke other profiles
Step | Command | Purpose
1 | hermes auth list nous | Confirm current pool state and which credential is exhausted/expired
2 | hermes auth reset nous | Clear all cooldown/exhaustion flags on the Nous credential pool
3 | hermes auth add nous --type oauth | Re-run OAuth login to mint a fresh refresh token
4 | hermes portal info | Verify Portal connection is restored and credits/plan show correctly
5 | hermes -p <affected-profile> auth status nous | Repeat per affected profile until each shows logged in
Root cause (known bug) | Nous refresh-token rotation isn't always persisted; after ~4-10 days of runtime, refresh returns 'invalid_grant: Refresh token reuse detected'. Profiles sharing the Nous OAuth session get locked out together.
C. Worktree branch-collision hard rule (enforced, not just documented)
Rule | Enforcement mechanism
Every task gets a unique branch name | Task ID embedded in branch name: feat/<TASK-ID>-<slug>, never reused
Orchestrator checks before assigning | Orchestrator runs 'git worktree list' before creating any new worktree or assigning a task
Pre-flight script blocks collisions | safe-worktree-add.sh checks branch is not already checked out before running git worktree add
On collision error | Do not force-checkout; run 'git worktree list', resolve conflict or pick a new branch name
D. Profile distributions — package agent once, clone onto ASUS
Step | Action | Command / Link
1 | Open official docs | https://hermes-agent.nousresearch.com/docs/user-guide/profile-distributions
2 | On MacBook: create manifest in profile dir | distribution.yaml with at least 'name' and 'version' fields
3 | Init and push distro repo | git init && git add -A && git commit -m 'profile distro' && git remote add origin <URL> && git push -u origin main
4 | On ASUS: install the distribution | hermes profile install <your-repo-url> --alias
5 | Or clone existing local profile directly | hermes profile create <name> --clone (config/.env/SOUL.md/skills/curated memories only)
E. Memory-curator prompt — Obsidian architecture audit
Full prompt text is in the companion Markdown file, section 'Memory-curator prompt'. Deliverable: an audit note, not a restructure — no vault changes without Olesia's approval.